## Release Cal
MMIS Release | Release - Defects & CR Scope Freeze | Development Start | Development Code Check-In | Code Cut-Off (Week2) | Deploy - ment to 76 | SIT Deployment Cutoff (Week2) | SIT Regression Testing Start (Week1) Deployments Allowed | SIT Regression Testing Complete (Week2) No Deployments | UAT Deployment (Week1) | UAT BF (Week1) | UAT End Date | Go No-Go Decision | Production Deployment (Week2)
ND.02.03.83.00 | 2016-08-02 | 2016-08-03 |  | 2016-08-11 | Daily | 2016-08-11 | 2016-08-12 | 2016-08-16 | 2016-08-16 | 2016-08-17 | 2016-08-23 | 2016-08-24 | 2016-08-25
ND.02.03.84.00 | 2016-08-16 | 2016-08-17 |  | 2016-08-25 | Daily | 2016-08-25 | 2016-08-26 | 2016-08-30 | 2016-08-30 | 2016-08-31 | 2016-09-06 | 2016-09-07 | 2016-09-08
ND.02.03.85.00 | 2016-08-30 | 2016-08-31 |  | 2016-09-08 | Daily | 2016-09-08 | 2016-09-09 | 2016-09-13 | 2016-09-13 | 2016-09-14 | 2016-09-20 | 2016-09-21 | 2016-09-22
ND.02.03.86.00 | 2016-09-13 | 2016-09-14 |  | 2016-09-22 | Daily | 2016-09-22 | 2016-09-23 | 2016-09-27 | 2016-09-27 | 2016-09-28 | 2016-10-04 | 2016-10-05 | 2016-10-06
ND.02.03.87.00 | 2016-09-29 | 2016-09-30 |  | 2016-10-13 | Daily | 2016-10-13 | 2016-10-14 | 2016-10-25 | 2016-10-25 | 2016-10-26 | 2016-11-08 | 2016-11-09 | 2016-11-10
ND.02.03.88.00 | 2016-10-27 | 2016-10-28 |  | 2016-11-10 | Daily | 2016-11-10 | 2016-11-11 | 2016-11-22 | 2016-11-22 | 2016-11-23 | 2016-12-20 | 2016-12-21 | 2016-12-22
ND.02.03.88.01 | NA | NA |  | NA | NA | NA | NA | NA | NA | NA | NA | NA | 2016-12-28
ND.02.03.88.02 | NA | NA |  | NA | NA | NA | NA | NA | NA | NA | NA | NA | 2017-01-02
ND.02.03.88.03 | NA | NA |  | NA | NA | NA | NA | NA | NA | NA | NA | NA | 2017-01-17
ND.02.03.88.04 | NA | NA |  | NA | NA | NA | NA | NA | NA | NA | NA | NA | 2017-01-18
ND.02.03.89.00 | 2016-11-24 | 2016-11-25 |  | 2016-12-08 | Daily | 2016-12-08 | 2016-12-09 | 2017-01-03 | 2017-01-03 | 2017-01-04 | 2017-01-24 | 2017-01-25 | 2017-01-26
ND.02.03.89.01 | NA | NA |  | NA | NA | NA | NA | NA | NA | NA | NA | NA | 2017-01-31
ND.02.03.90.00 | 2017-01-05 | 2017-01-06 |  | 2017-01-19 | Daily | 2017-01-19 | 2017-01-20 | 2017-01-31 | 2017-01-31 | 2017-02-01 | 2017-02-14 | 2017-02-15 | 2017-02-16
ND.02.03.90.01 | NA | NA |  | NA | NA | NA | NA | NA | NA | NA | NA | NA | 2017-02-23
ND.02.03.91.00 | 2017-02-02 | 2017-02-03 |  | 2017-02-16 | Daily | 2017-02-16 | 2017-02-17 | 2017-03-01 | 2017-03-01 | 2017-03-02 | 2017-03-14 | 2017-03-15 | 2017-03-16
ND.02.03.92.00 | 2017-03-02 | 2017-03-03 |  | 2017-03-13 | Daily | 2017-03-13 | 2017-03-14 | 2017-03-21 | 2017-03-21 | 2017-03-22 | 2017-04-04 | 2017-04-05 | 2017-04-06
ND.02.03.93.00 | 2017-03-23 | 2017-03-24 |  | 2017-04-06 | Daily | 2017-04-06 | 2017-04-07 | 2017-04-18 | 2017-04-18 | 2017-04-19 | 2017-05-02 | 2017-05-03 | 2017-05-04
ND.02.03.94.00 | 2017-04-20 | 2017-04-21 |  | 2017-05-08 | Daily | 2017-05-08 | 2017-05-09 | 2017-05-23 | 2017-05-23 | 2017-05-24 | 2017-06-06 | 2017-06-07 | 2017-06-08
ND.02.03.95.00 | 2017-05-25 | 2017-05-26 |  | 2017-06-12 | Daily | 2017-06-12 | 2017-06-13 | 2017-06-27 | 2017-06-27 | 2017-06-28 | 2017-07-18 | 2017-07-19 | 2017-07-20
ND.02.03.96.00 | 2017-06-29 | 2017-06-30 |  | 2017-07-17 | Daily | 2017-07-17 | 2017-07-18 | 2017-08-01 | 2017-08-01 | 2017-08-02 | 2017-08-15 | 2017-08-16 | 2017-08-17
ND.02.03.97.00 | 2017-08-03 | 2017-08-04 |  | 2017-08-16 | Daily | 2017-08-16 | 2017-08-17 | 2017-08-29 | 2017-08-29 | 2017-08-30 | 2017-09-12 | 2017-09-13 | 2017-09-14
ND.02.03.98.00 | 2017-08-31 | 2017-09-01 |  | 2017-09-13 | Daily | 2017-09-13 | 2017-09-14 | 2017-09-26 | 2017-09-26 | 2017-09-27 | 2017-10-10 | 2017-10-11 | 2017-10-12
ND.02.03.99.00 | 2017-09-28 | 2017-09-29 |  | 2017-10-11 | Daily | 2017-10-11 | 2017-10-12 | 2017-10-24 | 2017-10-24 | 2017-10-25 | 07-Nov-17 Tue | 07-Nov-17 Tue | 08-Nov-17 Wed
ND.02.04.00.00 | 2017-10-26 | 2017-10-27 |  | 2017-11-13 | Daily | 2017-11-13 | 2017-11-14 | 2017-11-28 | 2017-11-28 | 2017-11-29 | 2017-12-12 | 2017-12-13 | 2017-12-14
ND.02.04.01.00 | 2017-11-30 | 2017-12-01 |  | 2017-12-13 | Daily | 2017-12-13 | 2017-12-14 | 2017-12-26 | 2017-12-26 | 2017-12-27 | 2018-01-09 | 2018-01-10 | 2018-01-11
ND.02.04.02.00 | 2017-12-28 | 2017-12-29 |  | 2018-01-10 | Daily | 2018-01-10 | 2018-01-11 | 2018-01-23 | 2018-01-23 | 2018-01-24 | 2018-02-06 | 2018-02-07 | 2018-02-08
ND.02.04.03.00 | 2018-01-25 | 2018-01-26 |  | 2018-02-07 | Daily | 2018-02-07 | 2018-02-08 | 2018-02-20 | 2018-02-20 | 2018-02-21 | 2018-03-06 | 2018-03-07 | 2018-03-08
ND.02.04.04.00 | 2018-02-22 | 2018-02-23 |  | 2018-03-12 | Daily | 2018-03-12 | 2018-03-13 | 2018-03-23 | 2018-03-24 | 2018-03-26 | 2018-04-03 | 2018-04-04 | 2018-04-05
ENC Ph 2 & ND.02.04.05.00 | 2018-04-05 | 2018-04-06 |  | 2018-04-18 | Daily | 2018-04-18 | 2019-04-19 | 2018-04-27 | 2018-04-27 | 2018-04-28 | 04-Jun-18 Mon | 2018-06-05 | 06-Jun-18 Wed
ND.02.04.06.00 | 2018-05-03 | 2018-05-04 |  | 2018-05-21 | Daily | 2018-05-21 | 2018-05-22 | 2018-06-05 | 2018-06-07 | 2018-06-08 | 2018-06-19 | 2018-06-20 | 2018-06-21
ND.02.04.07.00 | 2018-06-07 | 2018-06-08 |  | 2018-06-20 | Daily | 2018-06-20 | 2018-06-21 | 2018-07-04 | 2018-07-04 | 2018-07-05 | 2018-07-17 | 2018-07-18 | 2018-07-19
ND.02.04.08.00 | 2018-07-05 | 2018-07-06 |  | 2018-07-18 | Daily | 2018-07-18 | 2018-07-19 | 2018-07-31 | 2018-07-31 | 2018-08-01 | 2018-08-14 | 2018-08-15 | 2018-08-16
ND.02.04.08.01 | 2018-07-05 | 2018-07-06 |  | 2018-07-18 | Daily | 2018-07-18 | 2018-07-19 | 2018-08-03 | 2018-08-17 | 2018-08-20 | 2018-08-30 | 2018-08-30 | 2018-08-30
ND.02.04.09.00 | 2018-07-18 | 2018-07-19 |  | 2018-08-20 | Daily | 2018-08-20 | 2018-08-21 | 2018-09-04 | 2018-09-04 | 2018-09-05 | 2018-09-18 | 2018-09-19 | 2018-09-20
ND.02.04.10.00 | 2018-08-20 | 2018-08-21 |  | 2018-09-19 | Daily | 2018-09-19 | 2018-09-20 | 2018-10-02 | 01-Oct-18 Mon 03-Oct 18 Wed | 2018-10-02 | 2018-10-16 | 2018-10-17 | 2018-10-18
ND.02.04.11.00 | 2018-09-19 | 2018-09-20 |  | 2018-10-17 | Daily | 2018-10-17 | 2018-10-18 | 2018-10-30 | 2018-10-30 | 2018-10-31 | 2018-11-13 | 2018-11-14 | 2018-11-20
ND.02.04.12.00 | 2018-10-17 | 2018-10-18 |  | 2018-11-14 | Daily | 2018-11-14 | 2018-11-15 | 2018-11-27 | 2018-11-27 | 2018-11-28 | 2018-12-11 | 2018-12-12 | 2018-12-13
ND.02.05.01.00 | 2018-11-21 | 2018-11-22 |  | 2018-12-19 | Daily | 2018-12-19 | 2018-12-20 | 2019-01-02 | 2019-01-02 | 2019-01-03 | 2019-01-15 | 2019-01-16 | 2019-01-17
ND.02.05.02.00 | 2018-12-19 | 2018-12-20 |  | 2019-01-16 | Daily | 2019-01-16 | 2019-01-17 | 2019-01-29 | 2019-01-29 | 2019-01-30 | 2019-02-12 | 2019-02-13 | 2019-04-17
ND.02.05.03.00 | 2019-01-16 | 2019-01-17 |  | 2019-02-13 | Daily | 2019-02-13 | 2019-02-14 | 2019-02-26 | 2019-02-26 | 2019-02-27 | 2019-03-12 | 2019-03-13 | 2019-04-17
Super Release ND.02.05.04.00 | 2018-12-19 | 2018-12-20 |  | 2019-02-13 | Daily | 2019-02-13 | 2019-02-14 | 2019-03-12 | 2019-03-12 | 2019-03-13 | 2019-04-15 | 2019-04-16 | 2019-04-17
ND.02.05.05.00 | 2019-02-13 | 2019-02-14 |  | 2019-04-03 | Daily | 2019-04-03 | 2019-04-04 | 2019-04-23 | 2019-04-23 | 2019-04-24 | 2019-05-14 | 2019-05-15 | 2019-05-19
ND.02.05.06.00 | 2019-04-03 | 2019-04-04 |  | 2019-05-15 | Daily | 2019-05-15 | 2019-05-16 | 2019-05-28 | 2019-05-28 | 2019-05-29 | 2019-06-11 | 2019-06-12 | 2019-06-13
ND.02.05.07.00 | 2019-05-15 | 2019-05-16 |  | 2019-06-12 | Daily | 2019-06-12 | 2019-06-13 | 2019-06-25 | 2019-06-25 | 2019-06-26 | 2019-07-09 | 2019-07-10 | 2019-07-11
ND.02.05.08.00 | 2019-06-12 | 2019-06-13 |  | 2019-07-10 | Daily | 2019-07-10 | 2019-07-11 | 2019-07-23 | 2019-07-23 | 2019-07-24 | 2019-08-06 | 2019-08-07 | 2019-08-08
ND.02.05.09.00 | 2019-07-10 | 2019-07-11 |  | 2019-08-14 | Daily | 2019-08-14 | 2019-08-15 | 2019-08-27 | 2019-08-27 | 2019-08-28 | 2019-09-10 | 2019-09-11 | 2019-09-12
ND.02.05.10.00 | 2019-08-14 | 2019-08-15 |  | 2019-09-11 | Daily | 2019-09-11 | 2019-09-12 | 2019-09-24 | 2019-09-24 | 2019-09-25 | 2019-10-08 | 2019-10-09 | 2019-10-10
ND.02.05.11.00 | 2019-09-11 | 2019-09-12 |  | 2019-10-09 | Daily | 2019-10-09 | 2019-10-10 | 2019-10-22 | 2019-10-22 | 2019-10-23 | 12-Nov-19 Tue | 13-Nov-19 Wed | 14-Nov-19 Thu
ND.02.05.11.01 | 2019-10-09 | 2019-10-10 | 23-Oct-19 Wed | 2019-11-14 | Daily | 2019-11-14 | 2019-11-15 | 2019-11-22 | 2019-11-22 | 2019-11-23 | 2019-12-04 | 2019-12-04 | 2019-12-05
ND.02.05.12.00 | 2019-10-09 | 2019-10-10 | 23-Oct-19 Wed | 2019-11-20 | Daily | 2019-11-20 | 2019-11-21 | 2019-12-05 | 2019-12-05 | 2019-12-06 | 2019-12-18 | 2019-12-18 | 2019-12-19
ND.02.06.01.00 | 2019-11-20 | 2019-11-21 | 6-Dec-19 Fri | 2019-12-24 | Daily | 2019-12-24 | 2019-12-26 | 2020-01-07 | 2020-01-07 | 2020-01-08 | 2020-01-21 | 2020-01-22 | 2020-01-23
ND.02.06.02.00 | 2019-12-25 | 2019-12-26 | 2020-01-08 | 2020-01-15 | Daily | 2020-01-15 | 2020-01-16 | 2020-01-28 | 2020-01-28 | 2020-01-29 | 2020-02-11 | 2020-02-12 | 2020-02-13
ND.02.06.03.00 | 2020-01-15 | 2020-01-16 | 2020-01-29 | 2020-02-12 | Daily | 2020-02-12 | 2020-02-13 | 2020-02-25 | 2020-02-25 | 2020-02-26 | 2020-03-10 | 2020-03-11 | 2020-03-12
ND.02.06.04.00 | 2020-02-12 | 2020-02-13 | 2020-02-26 | 2020-03-11 | Daily | 2020-03-11 | 2020-03-12 | 2020-03-24 | 2020-03-24 | 2020-03-25 | 2020-04-07 | 2020-04-08 | 2020-04-09
ND.02.06.05.00 | 2020-03-11 | 2020-03-12 | 2020-03-25 | 2020-04-15 | Daily | 2020-04-15 | 2020-04-16 | 2020-04-28 | 2020-04-28 | 2020-04-29 | 2020-05-12 | 2020-05-13 | 2020-05-14
ND.02.06.06.00 | 2020-04-15 | 2020-04-16 | 2020-04-29 | 2020-05-13 | Daily | 2020-05-13 | 2020-05-14 | 2020-05-26 | 2020-05-26 | 2020-05-27 | 2020-06-09 | 2020-06-10 | 2020-06-11
ND.02.06.07.00 | 2020-05-13 | 2020-05-14 | 2020-05-27 | 2020-06-10 | Daily | 2020-06-10 | 2020-06-11 | 2020-06-23 | 2020-06-23 | 2020-06-24 | 2020-07-14 | 2020-07-15 | 2020-07-16
ND.02.06.08.00 | 2020-06-10 | 2020-06-11 | 2020-06-24 | 2020-07-15 | Daily | 2020-07-15 | 2020-07-16 | 2020-07-28 | 2020-07-28 | 2020-07-29 | 2020-08-11 | 2020-08-12 | 2020-08-13
ND.02.06.09.00 | 2020-07-15 | 2020-07-16 | 2020-07-29 | 2020-08-12 | Daily | 2020-08-12 | 2020-08-13 | 2020-08-25 | 2020-08-25 | 2020-08-26 | 2020-09-08 | 2020-09-09 | 2020-09-10
ND.02.06.10.00 | 2020-08-12 | 2020-08-13 | 2020-08-26 | 2020-09-09 | Daily | 2020-09-09 | 2020-09-10 | 2020-09-22 | 2020-09-22 | 2020-09-23 | 2020-10-06 | 2020-10-07 | 2020-10-08
ND.02.06.11.00 | 2020-09-09 | 2020-09-10 | 2020-09-23 | 2020-10-14 | Daily | 2020-10-14 | 2020-10-15 | 2020-10-27 | 2020-10-27 | 2020-10-28 | 2020-11-10 | 2020-11-11 | 2020-11-12
ND.02.06.12.00 | 2020-10-14 | 2020-10-15 | 2020-10-28 | 2020-11-18 | Daily | 2020-11-18 | 2020-11-19 | 2020-12-01 | 2020-12-01 | 2020-12-02 | 2020-12-15 | 2020-12-16 | 2020-12-17
ND.02.07.01.00 | 2020-11-18 | 2020-11-19 | 2020-12-02 | 16-Dec-20 Wed | Daily | 16-Dec-20 Wed | 17-Dec-20 Thu | 29-Dec-20 Tue | 29-Dec-20 Tue | 30-Dec-20 Wed | 12-Jan-21 Tue | 12-Jan-21 Tue | 13-Jan-21 Wed
ND.02.07.02.00 | 2020-12-16 | 17-Dec-20 Thu | 30-Dec-20 Wed | 13-Jan-21 Wed | Daily | 13-Jan-21 Wed | 14-Jan-21 Thu | 25-Jan-21 Mon | 25-Jan-21 Mon | 26-Jan-21 Tue | 9-Feb-21 Tue | 10-Feb-21 Wed | 11-Feb-21 Thu
ND.02.07.03.00 | 2021-01-13 | 14-Jan-21 Thu | 26-Jan-21 Tue | 10-Feb-21 Wed | Daily | 10-Feb-21 Wed | 11-Feb-21 Thu | 23-Feb-21 Tue | 23-Feb-21 Tue | 24-Feb-21 Wed | 9-Mar-21 Tue | 9-Mar-21 Tue | 10-Mar-21 Wed
ND.02.07.04.00 | 2021-02-10 | 11-Feb-21 Thu | 24-Feb-21 Wed | 10-Mar-21 Wed | Daily | 10-Mar-21 Wed | 11-Mar-21 Thu | 23-Mar-21 Tue | 23-Mar-21 Tue | 24-Mar-21 Wed | 6 - Apr - 21 Tue | 7 - Apr - 21 Wed | 8-Apr-21 Thu
ND.02.07.05.00 | 2021-03-10 | 11-Mar-21 Thu | 24-Mar-21 Wed | 14-Apr-21 Wed | Daily | 14-Apr-21 Wed | 15-Apr-21 Thu | 27-Apr-21 Tue | 27-Apr-21 Tue | 28-Apr-21 Wed | 11-May-21 Tue | 12-May-21 Wed | 13-May-21 Thu
ND.02.07.06.00 | 2021-04-14 | 15-Apr-21 Thu | 28-Apr-21 Wed | 12-May-21 Wed | Daily | 12-May-21 Wed | 13-May-21 Thu | 25-May-21 Tue | 25-May-21 Tue | 26-May-21 Wed | 8 - Jun - 21 Tue | 9 - Jun - 21 Wed | 10-Jun-21 Thu
ND.02.07.07.00 | 2021-05-12 | 13-May-21 Thu | 26-May-21 Wed | 9-Jun-21 Wed | Daily | 9-Jun-21 Wed | 10-Jun-21 Thu | 22-Jun-21 Tue | 22-Jun-21 Tue | 23-Jun-21 Wed | 6 - Jul - 21 Tue | 7 - Jul - 21 Wed | 8- Jul-21 Thu
ND.02.07.08.00 | 2021-06-09 | 10-Jun-21 Thu | 23-Jun-21 Wed | 14-Jul-21 Wed | Daily | 14-Jul-21 Wed | 15-Jul-21 Thu | 27-Jul-21 Tue | 27-Jul-21 Tue | 28-Jul-21 Wed | 10 - Aug - 21 Tue | 11 - Aug - 21 Wed | 12 -Aug-21 Thu
ND.02.07.09.00 | 2021-07-14 | 15-Jul-21 Thu | 28-Jul-21 Wed | 11-Aug-21 Wed | Daily | 11-Aug-21 Wed | 12-Aug-21 Thu | 24-Aug-21 Tue | 24-Aug-21 Tue | 25-Aug-21 Wed | 7 - Sep - 21 Tue | 7 - Sep - 21 Tue | 8 -Sep- 21 Wed
ND.02.07.10.00 | 2021-08-11 | 12-Aug-21 Thu | 25-Aug-21 Wed | 15-Sep-21 Wed | Daily | 15-Sep-21 Wed | 16-Sep-21 Thu | 28-Sep-21 Tue | 28-Sep-21 Tue | 29-Sep-21 Wed | 12 - Oct - 21 Tue | 12 - Oct - 21 Tue | 13- Oct-21 Wed
ND.02.07.11.00 | 2021-09-15 | 16-Sep-21 Thu | 29-Sep-21 Wed | 13-Oct-21 Wed | Daily | 13-Oct-21 Wed | 14-Oct-21 Thu | 26-Oct-21 Tue | 26-Oct-21 Tue | 27-Oct-21 Wed | 9 - Nov - 21 Tue | 10 - Nov - 21 Wed | 11-Nov-21 Thu
ND.02.07.12.00 | 2021-10-13 | 14-Oct-21 Thu | 27-Oct-21 Wed | 17-Nov-21 Wed | Daily | 17-Nov-21 Wed | 18-Nov-21 Thu | 30-Nov-21 Tue | 30-Nov-21 Tue | 01-Dec-21 Wed | 14- Dec-21 Tue | 15 - Dec - 21 Wed | 16-Dec-21 Thu
ND.02.08.01.00 | 2021-11-17 | 18-Nov-21 Thu | 01-Dec-21 Wed | 2021-12-15 | Daily | 2021-12-15 | 2021-12-16 | 2021-12-28 | 2021-12-28 | 2021-12-29 | 2022-01-11 | 2022-01-11 | 2022-01-12
ND.02.08.02.00 | 2021-12-15 | 2021-12-16 | 2021-12-29 | 2022-01-11 | Daily | 2022-01-11 | 2022-01-12 | 2022-01-24 | 2022-01-24 | 2022-01-25 | 2022-02-08 | 2022-02-09 | 2022-02-10
ND.02.08.03.00 | 2022-01-11 | 2022-01-12 | 2022-01-25 | 2022-02-09 | Daily | 2022-02-09 | 2022-02-10 | 2022-02-22 | 2022-02-22 | 2022-02-23 | 2022-03-08 | 2022-03-09 | 2022-03-10
ND.02.08.04.00 | 2022-02-09 | 2022-02-10 | 2022-02-23 | 9-Mar-22 Wed | Daily | 9-Mar-22 Wed | 10-Mar-22 Thu | 2022-03-22 | 2022-03-22 | 2022-03-23 | 2022-04-05 | 2022-04-06 | 2022-04-07
ND.02.08.05.00 | 2022-03-09 | 2022-03-10 | 2022-03-23 | 2022-04-13 | Daily | 2022-04-13 | 2022-04-14 | 2022-04-26 | 2022-04-26 | 2022-04-27 | 2022-05-10 | 2022-05-11 | 2022-05-12
ND.02.08.06.00 | 2022-04-13 | 2022-04-14 | 2022-04-27 | 2022-05-11 | Daily | 2022-05-11 | 2022-05-12 | 2022-05-24 | 2022-05-24 | 2022-05-25 | 2022-06-07 | 2022-06-08 | 2022-06-09
ND.02.08.07.00 | 2022-05-11 | 2022-05-12 | 2022-05-25 | 2022-06-15 | Daily | 2022-06-15 | 2022-06-16 | 2022-06-28 | 2022-06-28 | 2022-06-29 | 2022-07-12 | 2022-07-13 | 2022-07-14
ND.02.08.08.00 | 2022-06-15 | 2022-06-16 | 2022-06-29 | 2022-07-13 | Daily | 2022-07-13 | 2022-07-14 | 2022-07-26 | 2022-07-26 | 2022-07-27 | 2022-08-09 | 2022-08-10 | 2022-08-11
ND.02.08.09.00 | 2022-07-13 | 2022-07-14 | 2022-07-27 | 2022-08-10 | Daily | 2022-08-10 | 2022-08-11 | 2022-08-23 | 2022-08-23 | 2022-08-24 | 2022-09-06 | 2022-09-07 | 2022-09-08
ND.02.08.10.00 | 2022-08-10 | 2022-08-11 | 2022-08-24 | 2022-09-14 | Daily | 2022-09-14 | 2022-09-15 | 2022-09-27 | 2022-09-27 | 2022-09-28 | 2022-10-11 | 2022-10-12 | 2022-10-13
ND.02.08.11.00 | 2022-09-14 | 2022-09-15 | 2022-09-28 | 2022-10-12 | Daily | 2022-10-12 | 2022-10-13 | 2022-10-25 | 2022-10-25 | 2022-10-26 | 2022-11-08 | 2022-11-08 | 2022-11-09
ND.02.08.12.00 | 2022-10-12 | 2022-10-13 | 2022-10-26 | 2022-11-16 | Daily | 2022-11-16 | 2022-11-17 | 2022-11-29 | 2022-11-29 | 2022-11-30 | 2022-12-13 | 2022-12-14 | 2022-12-15
ND.02.09.01.00 | 2022-11-16 | 2022-11-17 | 2022-11-30 | 2022-12-14 | Daily | 2022-12-14 | 2022-12-15 | 2022-12-27 | 2022-12-27 | 2022-12-28 | 2023-01-10 | 2023-01-11 | 2023-01-12
ND.02.09.02.00 | 2022-12-14 | 2022-12-15 | 2022-12-28 | 2023-01-11 | Daily | 2023-01-11 | 2023-01-12 | 2023-01-24 | 2023-01-24 | 2023-01-25 | 2023-02-07 | 2023-02-08 | 2023-02-09
ND.02.09.03.00 | 2023-01-11 | 2023-01-12 | 2023-01-25 | 2023-02-08 | Daily | 2023-02-08 | 2023-02-09 | 2023-02-21 | 2023-02-21 | 2023-02-22 | 2023-03-07 | 2023-03-08 | 2023-03-09
ND.02.09.04.00 | 2023-02-08 | 2023-02-09 | 2023-02-22 | 2023-03-15 | Daily | 2023-03-15 | 2023-03-16 | 2023-03-28 | 2023-03-28 | 2023-03-29 | 2023-04-11 | 2023-04-12 | 2023-04-13
ND.02.09.05.00 | 2023-03-15 | 2023-03-16 | 2023-03-29 | 2023-04-12 | Daily | 2023-04-12 | 2023-04-13 | 2023-04-25 | 2023-04-25 | 2023-04-26 | 2023-05-09 | 2023-05-10 | 2023-05-11
ND.02.09.06.00 | 2023-04-12 | 2023-04-13 | 2023-04-26 | 2023-05-10 | Daily | 2023-05-10 | 2023-05-11 | 2023-05-23 | 2023-05-23 | 2023-05-24 | 2023-06-06 | 2023-06-07 | 2023-06-08
ND.02.09.07.00 | 2023-05-10 | 2023-05-11 | 2023-05-24 | 2023-06-14 | Daily | 2023-06-14 | 2023-06-15 | 2023-06-27 | 2023-06-27 | 2023-06-28 | 2023-07-11 | 2023-07-12 | 2023-07-13
ND.02.09.08.00 | 2023-06-14 | 2023-06-15 | 2023-06-28 | 2023-07-12 | Daily | 2023-07-12 | 2023-07-13 | 2023-07-25 | 2023-07-25 | 2023-07-26 | 2023-08-08 | 2023-08-09 | 2023-08-10
ND.02.09.08.00 | 14-Jun-23 Wed | 15-Jun-23 Thu | 28-Jun-23 Wed | 2023-07-26 | Daily | 2023-07-26 | 2023-07-27 | 2023-08-08 | 2023-08-08 | 2023-08-09 | 2023-08-22 | 2023-08-23 | 2023-08-24
ND.02.09.09.00 | 2023-07-12 | 2023-07-13 | 2023-07-26 | 2023-08-09 | Daily | 2023-08-09 | 2023-08-10 | 2023-09-12 | 2023-09-12 | 2023-09-13 | 2023-09-26 | 2023-09-27 | 2023-09-28
ND.02.09.10.00 | 2023-08-09 | 2023-08-10 | 2023-09-13 | 2023-09-20 | Daily | 2023-09-20 | 2023-09-21 | 2023-10-03 | 2023-10-03 | 2023-10-04 | 2023-10-17 | 2023-10-18 | 2023-10-19
ND.02.09.11.00 | 2023-09-20 | 2023-09-21 | 2023-10-04 | 2023-10-11 | Daily | 2023-10-11 | 2023-10-12 | 2023-10-23 | 2023-10-23 | 2023-10-25 | 2023-11-07 | 2023-11-07 | 8-Nov-23 Wed
ND.02.09.12.00 | 2023-10-11 | 2023-10-12 | 2023-10-25 | 2023-11-15 | Daily | 2023-11-15 | 2023-11-16 | 2023-11-28 | 2023-11-28 | 2023-11-29 | 2023-12-12 | 2023-12-13 | 2023-12-14
ND.02.10.01.00 | 2023-11-15 | 2023-11-16 | 2023-11-29 | 13-Dec-23 Wed | Daily | 13-Dec-23 Wed | 14-Dec-23 Thu | 26-Dec-23 Tue | 26-Dec-23 Tue | 27-Dec-23 Wed | 9-Jan-24 Tue | 10-Jan-24 Wed | 11-Jan-24 Thu
ND.02.10.02.00 | 13-Dec-23 Wed | 14-Dec-23 Thu | 27-Dec-23 Wed | 10-Jan-24 Wed | Daily | 10-Jan-24 Wed | 11-Jan-24 Thu | 23-Jan-24 Tue | 23-Jan-24 Tue | 24-Jan-24 Wed | 6-Feb-24 Tue | 7-Feb-24 Wed | 8-Feb-24 Thu
ND.02.10.03.00 | 10-Jan-24 Wed | 11-Jan-24 Thu | 24-Jan-24 Wed | 14-Feb-24 Wed | Daily | 14-Feb-24 Wed | 15-Feb-24 Thu | 27-Feb-24 Tue | 27-Feb-24 Tue | 28-Feb-24 Wed | 12-Mar-24 Tue | 13-Mar-24 Wed | 14-Mar-24 Thu
ND.02.10.04.00 | 14-Feb-24 Wed | 15-Feb-24 Thu | 28-Feb-24 Wed | 13-Mar-24 Wed | Daily | 13-Mar-24 Wed | 14-Mar-24 Thu | 26-Mar-24 Tue | 26-Mar-24 Tue | 27-Mar-24 Wed | 9-Apr-24 Tue | 10-Apr-24 Wed | 11-Apr-24 Thu
ND.02.10.05.00 | 13-Mar-24 Wed | 14-Mar-24 Thu | 27-Mar-24 Wed | 10-Apr-24 Wed | Daily | 10-Apr-24 Wed | 11-Apr-24 Thu | 23-Apr-24 Tue | 23-Apr-24 Tue | 24-Apr-24 Wed | 14-May-24 Tue | 15-May-24 Wed | 16-May-24 Thu
ND.02.10.06.00 | 10-Apr-24 Wed | 11-Apr-24 Thu | 24-Apr-24 Wed | 15-May-24 Wed | Daily | 15-May-24 Wed | 16-May-24 Thu | 28-May-24 Tue | 28-May-24 Tue | 29-May-24 Wed | 11-Jun-24 Tue | 12-Jun-24 Wed | 13-Jun-24 Thu
ND.02.10.07.00 | 15-May-24 Wed | 16-May-24 Thu | 29-May-24 Wed | 12-Jun-24 Wed | Daily | 12-Jun-24 Wed | 13-Jun-24 Thu | 25-Jun-24 Tue | 25-Jun-24 Tue | 26-Jun-24 Wed | 9-Jul-24 Tue | 10-Jul-24 Wed | 11-Jul-24 Thu
ND.02.10.08.00 | 12-Jun-24 Wed | 13-Jun-24 Thu | 26-Jun-24 Wed | 10-Jul-24 Wed | Daily | 10-Jul-24 Wed | 11-Jul-24 Thu | 23-Jul-24 Tue | 23-Jul-24 Tue | 24-Jul-24 Wed | 6-Aug-24 Tue | 7-Aug-24 Wed | 8-Aug-24 Thu
ND.02.10.09.00 | 10-Jul-24 Wed | 11-Jul-24 Thu | 24-Jul-24 Wed | 14-Aug-24 Wed | Daily | 14-Aug-24 Wed | 15-Aug-24 Thu | 27-Aug-24 Tue | 27-Aug-24 Tue | 28-Aug-24 Wed | 10-Sep-24 Tue | 11-Sep-24 Wed | 12-Sep-24 Thu
ND.02.10.10.00 | 14-Aug-24 Wed | 15-Aug-24 Thu | 28-Aug-24 Wed | 11-Sep-24 Wed | Daily | 11-Sep-24 Wed | 12-Sep-24 Thu | 24-Sep-24 Tue | 24-Sep-24 Tue | 25-Sep-24 Wed | 8-Oct-24 Tue | 9-Oct-24 Wed | 10-Oct-24 Thu
ND.02.10.11.00 | 11-Sep-24 Wed | 12-Sep-24 Thu | 25-Sep-24 Wed | 16-Oct-24 Wed | Daily | 16-Oct-24 Wed | 17-Oct-24 Thu | 29-Oct-24 Tue | 29-Oct-24 Tue | 30-Oct-24 Wed | 12-Nov-24 Tue | 13-Nov-24 Wed | 14-Nov-24 Thu
ND.02.10.12.00 | 16-Oct-24 Wed | 17-Oct-24 Thu | 30-Oct-24 Wed | 13-Nov-24 Wed | Daily | 13-Nov-24 Wed | 14-Nov-24 Thu | 26-Nov-24 Tue | 26-Nov-24 Tue | 27-Nov-24 Wed | 10-Dec-24 Tue | 11-Dec-24 Wed | 12-Dec-24 Thu
ND.02.11.01.00 | 13-Nov-24 Wed | 14-Nov-24 Thu | 27-Nov-24 Wed | 11-Dec-24 Wed | Daily | 11-Dec-24 Wed | 12-Dec-24 Thu | 23-Dec-24 Mon | 23-Dec-24 Mon | 24-Dec-24 Tue | 14-Jan-25 Tue | 15-Jan-25 Wed | 22-Jan-25 Thu
ND.02.11.02.00 | 11-Dec-24 Wed | 12-Dec-24 Thu | 2024-12-24 | 22-Jan-25 Wed | Daily | 22-Jan-25 Wed | 23-Jan-25 Thu | 4-Feb-25 Tue | 4-Feb-25 Tue | 5-Feb-25 Wed | 18-Feb-25 Tue | 19-Feb-25 Wed | 20-Feb-25 Thu
ND.02.11.03.00 | 22-Jan-25 Wed | 23-Jan-25 Thu | 5-Feb-25 Wed | 12-Feb-25 Wed | Daily | 12-Feb-25 Wed | 13-Feb-25 Thu | 25-Feb-25 Tue | 25-Feb-25 Tue | 26-Feb-25 Wed | 11-Mar-25 Tue | 12-Mar-25 Wed | 13-Mar-25 Thu
ND.02.11.04.00 | 12-Feb-25 Wed | 13-Feb-25 Thu | 26-Feb-25 Wed | 12-Mar-25 Wed | Daily | 12-Mar-25 Wed | 13-Mar-25 Thu | 25-Mar-25 Tue | 25-Mar-25 Tue | 26-Mar-25 Wed | 8-Apr-25 Tue | 9-Apr-25 Wed | 10-Apr-25 Thu
ND.02.11.05.00 | 12-Mar-25 Wed | 13-Mar-25 Thu | 26-Mar-25 Wed | 16-Apr-25 Wed | Daily | 16-Apr-25 Wed | 17-Apr-25 Thu | 29-Apr-25 Tue | 29-Apr-25 Tue | 30-Apr-25 Wed | 13-May-25 Tue | 14-May-25 Wed | 15-May-25 Thu
ND.02.11.06.00 | 16-Apr-25 Wed | 17-Apr-25 Thu | 30-Apr-25 Wed | 14-May-25 Wed | Daily | 14-May-25 Wed | 15-May-25 Thu | 27-May-25 Tue | 27-May-25 Tue | 28-May-25 Wed | 10-Jun-25 Tue | 11-Jun-25 Wed | 12-Jun-25 Thu
ND.02.11.07.00 | 14-May-25 Wed | 15-May-25 Thu | 28-May-25 Wed | 11-Jun-25 Wed | Daily | 11-Jun-25 Wed | 12-Jun-25 Thu | 24-Jun-25 Tue | 24-Jun-25 Tue | 25-Jun-25 Wed | 8-Jul-25 Tue | 9-Jul-25 Wed | 10-Jul-25 Thu
ND.02.11.08.00 | 11-Jun-25 Wed | 12-Jun-25 Thu | 25-Jun-25 Wed | 16-Jul-25 Wed | Daily | 16-Jul-25 Wed | 17-Jul-25 Thu | 29-Jul-25 Tue | 29-Jul-25 Tue | 30-Jul-25 Wed | 12-Aug-25 Tue | 13-Aug-25 Wed | 14-Aug-25 Thu
ND.02.11.09.00 | 16-Jul-25 Wed | 17-Jul-25 Thu | 30-Jul-25 Wed | 13-Aug-25 Wed | Daily | 13-Aug-25 Wed | 14-Aug-25 Thu | 26-Aug-25 Tue | 26-Aug-25 Tue | 27-Aug-25 Wed | 9-Sep-25 Tue | 10-Sep-25 Wed | 11-Sep-25 Thu
ND.02.11.10.00 | 13-Aug-25 Wed | 14-Aug-25 Thu | 27-Aug-25 Wed | 10-Sep-25 Wed | Daily | 10-Sep-25 Wed | 11-Sep-25 Thu | 23-Sep-25 Tue | 23-Sep-25 Tue | 24-Sep-25 Wed | 7-Oct-25 Tue | 8-Oct-25 Wed | 9-Oct-25 Thu
ND.02.11.11.00 | 10-Sep-25 Wed | 11-Sep-25 Thu | 24-Sep-25 Wed | 15-Oct-25 Wed | Daily | 15-Oct-25 Wed | 16-Oct-25 Thu | 28-Oct-25 Tue | 28-Oct-25 Tue | 29-Oct-25 Wed | 12-Nov-25 Wed 12pm CT | 12-Nov-25 Wed | 13-Nov-25 Thu
ND.02.11.12.00 | 15-Oct-25 Wed | 16-Oct-25 Thu | 29-Oct-25 Wed | 12-Nov-25 Wed | Daily | 12-Nov-25 Wed | 13-Nov-25 Thu | 25-Nov-25 Tue | 25-Nov-25 Tue | 26-Nov-25 Wed | 9-Dec-25 Tue | 10-Dec-25 Wed | 11-Dec-25 Thu
ND.02.12.01.00 | 2025-11-12 | 2025-11-13 | 2025-11-26 | 2025-12-17 | Daily | 2025-12-17 | 2025-12-18 | 2025-12-30 | 2025-12-30 | 2025-12-31 | 2026-01-13 | 2026-01-14 | 2026-01-15
ND.02.12.02.00 | 2025-12-17 | 2025-12-18 | 2025-12-31 | 2026-01-14 | Daily | 2026-01-14 | 2026-01-15 | 2026-01-27 | 2026-01-27 | 2026-01-28 | 2026-02-10 | 2026-02-11 | 2026-02-12
ND.02.12.03.00 | 2026-01-14 | 2026-01-15 | 2026-01-28 | 2026-02-11 | Daily | 2026-02-11 | 2026-02-12 | 2026-02-24 | 2026-02-24 | 2026-02-25 | 2026-03-10 | 2026-03-11 | 2026-03-12
ND.02.12.04.00 | 2026-02-11 | 2026-02-12 | 2026-02-25 | 2026-03-11 | Daily | 2026-03-11 | 2026-03-12 | 2026-03-24 | 2026-03-24 | 2026-03-25 | 2026-04-07 | 2026-04-08 | 2026-04-09
ND.02.12.05.00 | 2026-03-11 | 2026-03-12 | 2026-03-25 | 2026-04-15 | Daily | 2026-04-15 | 2026-04-16 | 2026-04-28 | 2026-04-28 | 2026-04-29 | 2026-05-12 | 2026-05-13 | 2026-05-14
ND.02.12.06.00 | 2026-04-15 | 2026-04-16 | 2026-04-29 | 2026-05-13 | Daily | 2026-05-13 | 2026-05-14 | 2026-05-26 | 2026-05-26 | 2026-05-27 | 2026-06-09 | 2026-06-10 | 2026-06-11
ND.02.12.07.00 | 2026-05-13 | 2026-05-14 | 2026-05-27 | 2026-06-10 | Daily | 2026-06-10 | 2026-06-11 | 2026-06-23 | 2026-06-23 | 2026-06-24 | 2026-07-07 | 2026-07-08 | 2026-07-09
ND.02.12.08.00 | 2026-06-10 | 2026-06-11 | 2026-06-24 | 2026-07-15 | Daily | 2026-07-15 | 2026-07-16 | 2026-07-28 | 2026-07-28 | 2026-07-29 | 2026-08-11 | 2026-08-12 | 2026-08-13
ND.02.12.09.00 | 2026-07-15 | 2026-07-16 | 2026-07-29 | 2026-08-12 | Daily | 2026-08-12 | 2026-08-13 | 2026-08-25 | 2026-08-25 | 2026-08-26 | 2026-09-08 | 2026-09-09 | 2026-09-10
ND.02.12.10.00 | 2026-08-12 | 2026-08-13 | 2026-08-26 | 2026-09-09 | Daily | 2026-09-09 | 2026-09-10 | 2026-09-22 | 2026-09-22 | 2026-09-23 | 2026-10-06 | 2026-10-07 | 2026-10-08
ND.02.12.11.00 | 2026-09-09 | 2026-09-10 | 2026-09-23 | 2026-10-14 | Daily | 2026-10-14 | 2026-10-15 | 2026-10-27 | 2026-10-27 | 2026-10-28 | 2026-11-10 | 2026-11-11 | 2026-11-12
ND.02.12.12.00 | 2026-10-14 | 2026-10-15 | 2026-10-28 | 2026-11-11 | Daily | 2026-11-11 | 2026-11-12 | 2026-11-24 | 2026-11-24 | 2026-11-25 | 2026-12-08 | 2026-12-09 | 2026-12-10
Formulas:
Release - Defects & CR Scope Freeze = [Development Start]-1
Development Start = [NA, row above]
Development Code Check-In = [UAT BF (Week1), row above]