## MileStones & KeyNotes
Date | MileStones | Discussion Point | Action Item

## Key Dates Format
14.4 | Scope Freeze \ Req Approval \ Design Review |  | 7/7-7/25 | 14.4 | Scope Freeze \ Req Approval \ Design Review |  | 7/7-7/25
| ENV52 | MMIS Dev | 7/28-8/29 |  | ENV52 | MMIS Dev | 7/28-8/29
|  | P1 | 10/6-10/17 |  |  | P1 | 10/6-10/17
| ENV57 | MMIS SIT | 8/25-9/19 |  | ENV57 | MMIS SIT | 8/25-9/19
|  | P1 | 10/6-10/17 |  |  | P1 | 10/6-10/17
| ENV53 | Regression | 9/22-10/3 |  | ENV53 | Regression | 9/22-10/3
|  | P1 | 10/15-10/17 |  |  | P1 | 10/15-10/17
| ENV04 | UAT | 10/6-10/31 |  | ENV04 | UAT | 10/6-10/31
|  | P1 | 10/20-10/31 |  |  | P1 | 10/20-10/31
| ENV05 | Prod | 2025-11-02 |  | ENV05 | Prod | 2025-11-02
14.5 | Scope Freeze \ Req Approval \ Design Review |  | 8/11-8/29 | 14.5 | Scope Freeze \ Req Approval \ Design Review |  | 8/11-8/29
| ENV52 | MMIS Dev | 9/1-10/3 |  | ENV52 | MMIS Dev | 9/1-10/3
|  | P1 | 11/10-11/21 |  |  | P1 | 11/10-11/21
| ENV57 | MMIS SIT | 9/29-10/24 |  | ENV57 | MMIS SIT | 9/29-10/24
|  | P1 | 11/10-11/21 |  |  | P1 | 11/10-11/21
| ENV53 | Regression | 10/27-11/7 |  | ENV53 | Regression | 10/27-11/7
|  | P1 | 11/19-11/21 |  |  | P1 | 11/19-11/21
| ENV04 | UAT | 11/10-12/5 |  | ENV04 | UAT | 11/10-12/5
|  | P1 | 11/24-12/5 |  |  | P1 | 11/24-12/5
| ENV05 | Prod | 2025-12-07 |  | ENV05 | Prod | 2025-12-07
14.6 | Scope Freeze \ Req Approval \ Design Review |  | 9/15-10/3 | 14.6 | Scope Freeze \ Req Approval \ Design Review |  | 9/15-10/3
| ENV52 | MMIS Dev | 10/6-11/7 |  | ENV52 | MMIS Dev | 10/6-11/7
|  | P1 | 12/15-12/26 |  |  | P1 | 12/15-12/26
| ENV57 | MMIS SIT | 11/3-11/28 |  | ENV57 | MMIS SIT | 11/3-11/28
|  | P1 | 12/15-12/26 |  |  | P1 | 12/15-12/26
| ENV53 | Regression | 12/1-12/12 |  | ENV53 | Regression | 12/1-12/12
|  | P1 | 12/24-12/26 |  |  | P1 | 12/24-12/26
| ENV04 | UAT | 12/15-1/9 |  | ENV04 | UAT | 12/15-1/9
|  | P1 | 12/29-1/9 |  |  | P1 | 12/29-1/9
| ENV05 | Prod | 2026-01-11 |  | ENV05 | Prod | 2026-01-11
14.7 | Scope Freeze \ Req Approval \ Design Review |  | 10/20-11/7 | 14.7 | Scope Freeze \ Req Approval \ Design Review |  | 10/20-11/7
| ENV52 | MMIS Dev | 11/10-12/12 |  | ENV52 | MMIS Dev | 11/10-12/12
|  | P1 | 1/19-1/30 |  |  | P1 | 1/19-1/30
| ENV57 | MMIS SIT | 12/8-1/2 |  | ENV57 | MMIS SIT | 12/8-1/2
|  | P1 | 1/19-1/30 |  |  | P1 | 1/19-1/30
| ENV53 | Regression | 1/5-1/16 |  | ENV53 | Regression | 1/5-1/16
|  | P1 | 1/28-1/30 |  |  | P1 | 1/28-1/30
| ENV04 | UAT | 1/19-2/13 |  | ENV04 | UAT | 1/19-2/13
|  | P1 | 2/2-2/13 |  |  | P1 | 2/2-2/13
| ENV05 | Prod | 2026-02-15 |  | ENV05 | Prod | 2026-02-15
14.8 | Scope Freeze \ Req Approval \ Design Review |  | 11/24 - 12/12 | 14.8 | Scope Freeze \ Req Approval \ Design Review |  | 11/24 - 12/12
| ENV52 | MMIS Dev | 12/15-1/16 |  | ENV52 | MMIS Dev | 12/15-1/16
|  | P1 | 2/23-3/6 |  |  | P1 | 2/23-3/6
| ENV57 | MMIS SIT | 1/12-2/6 |  | ENV57 | MMIS SIT | 1/12-2/6
|  | P1 | 2/23-3/6 |  |  | P1 | 2/23-3/6
| ENV53 | Regression | 2/9-2/20 |  | ENV53 | Regression | 2/9-2/20
|  | P1 | 3/4-3/6 |  |  | P1 | 3/4-3/6
| ENV04 | UAT | 2/23-3/20 |  | ENV04 | UAT | 2/23-3/20
|  | P1 | 3/9-3/20 |  |  | P1 | 3/9-3/20
| ENV05 | Prod | 2026-03-22 |  | ENV05 | Prod | 2026-03-22
14.9 | Scope Freeze \ Req Approval \ Design Review |  | 12/29-1/16 | 14.9 | Scope Freeze \ Req Approval \ Design Review |  | 12/29-1/16
| ENV52 | MMIS Dev | 1/19-2/20 |  | ENV52 | MMIS Dev | 1/19-2/20
|  | P1 | 3/30-4/10 |  |  | P1 | 3/30-4/10
| ENV57 | MMIS SIT | 2/16-3/13 |  | ENV57 | MMIS SIT | 2/16-3/13
|  | P1 | 3/30-4/10 |  |  | P1 | 3/30-4/10
| ENV53 | Regression | 3/16-3/27 |  | ENV53 | Regression | 3/16-3/27
|  | P1 | 4/8-4/10 |  |  | P1 | 4/8-4/10
| ENV04 | UAT | 3/30-4/24 |  | ENV04 | UAT | 3/30-4/24
|  | P1 | 4/13-4/24 |  |  | P1 | 4/13-4/24
| ENV05 | Prod | 2026-04-26 |  | ENV05 | Prod | 2026-04-26
15 | Scope Freeze \ Req Approval \ Design Review |  | 2/2-2/20 | 15 | Scope Freeze \ Req Approval \ Design Review |  | 2/2-2/20
| ENV52 | MMIS Dev | 2/23-3/27 |  | ENV52 | MMIS Dev | 2/23-3/27
|  | P1 | 5/4-5/15 |  |  | P1 | 5/4-5/15
| ENV57 | MMIS SIT | 3/23-4/17 |  | ENV57 | MMIS SIT | 3/23-4/17
|  | P1 | 5/4-5/15 |  |  | P1 | 5/4-5/15
| ENV53 | Regression | 4/20-5/1 |  | ENV53 | Regression | 4/20-5/1
|  | P1 | 5/13-5/15 |  |  | P1 | 5/13-5/15
| ENV04 | UAT | 5/4-5/29 |  | ENV04 | UAT | 5/4-5/29
|  | P1 | 5/18-5/29 |  |  | P1 | 5/18-5/29
| ENV05 | Prod | 2026-05-31 |  | ENV05 | Prod | 2026-05-31
15.1 | Scope Freeze \ Req Approval \ Design Review |  | 3/9-3/27 | 15.1 | Scope Freeze \ Req Approval \ Design Review |  | 3/9-3/27
| ENV52 | MMIS Dev | 3/30-5/1 |  | ENV52 | MMIS Dev | 3/30-5/1
|  | P1 | 6/8-6/19 |  |  | P1 | 6/8-6/19
| ENV57 | MMIS SIT | 4/27-5/22 |  | ENV57 | MMIS SIT | 4/27-5/22
|  | P1 | 6/8-6/19 |  |  | P1 | 6/8-6/19
| ENV53 | Regression | 5/25-6/5 |  | ENV53 | Regression | 5/25-6/5
|  | P1 | 6/17-6/19 |  |  | P1 | 6/17-6/19
| ENV04 | UAT | 6/8-7/3 |  | ENV04 | UAT | 6/8-7/3
|  | P1 | 6/22-7/3 |  |  | P1 | 6/22-7/3
| ENV05 | Prod | 2026-07-05 |  | ENV05 | Prod | 2026-07-05
15.2 | Scope Freeze \ Req Approval \ Design Review |  | 4/13-5/1 | 15.2 | Scope Freeze \ Req Approval \ Design Review |  | 4/13-5/1
| ENV52 | MMIS Dev | 5/4-6/5 |  | ENV52 | MMIS Dev | 5/4-6/5
|  | P1 | 7/13-7/24 |  |  | P1 | 7/13-7/24
| ENV57 | MMIS SIT | 6/1-6/26 |  | ENV57 | MMIS SIT | 6/1-6/26
|  | P1 | 7/13-7/24 |  |  | P1 | 7/13-7/24
| ENV53 | Regression | 6/29-7/10 |  | ENV53 | Regression | 6/29-7/10
|  | P1 | 7/22-7/24 |  |  | P1 | 7/22-7/24
| ENV04 | UAT | 7/13-8/7 |  | ENV04 | UAT | 7/13-8/7
|  | P1 | 7/27-8/7 |  |  | P1 | 7/27-8/7
| ENV05 | Prod | 2026-08-09 |  | ENV05 | Prod | 2026-08-09
15.3 | Scope Freeze \ Req Approval \ Design Review |  | 5/18-6/5 | 15.3 | Scope Freeze \ Req Approval \ Design Review |  | 5/18-6/5
| ENV52 | MMIS Dev | 6/8-7/10 |  | ENV52 | MMIS Dev | 6/8-7/10
|  | P1 | 8/17-8/28 |  |  | P1 | 8/17-8/28
| ENV57 | MMIS SIT | 7/6-7/31 |  | ENV57 | MMIS SIT | 7/6-7/31
|  | P1 | 8/17-8/28 |  |  | P1 | 8/17-8/28
| ENV53 | Regression | 8/3-8/14 |  | ENV53 | Regression | 8/3-8/14
|  | P1 | 8/26-8/28 |  |  | P1 | 8/26-8/28
| ENV04 | UAT | 8/17-9/11 |  | ENV04 | UAT | 8/17-9/11
|  | P1 | 8/31-9/11 |  |  | P1 | 8/31-9/11
| ENV05 | Prod | 2026-09-13 |  | ENV05 | Prod | 2026-09-13
15.4 | Scope Freeze \ Req Approval \ Design Review |  | 6/22-7/10 | 15.4 | Scope Freeze \ Req Approval \ Design Review |  | 6/22-7/10
| ENV52 | MMIS Dev | 7/13-8/14 |  | ENV52 | MMIS Dev | 7/13-8/14
|  | P1 | 9/21-10/2 |  |  | P1 | 9/21-10/2
| ENV57 | MMIS SIT | 8/10-9/4 |  | ENV57 | MMIS SIT | 8/10-9/4
|  | P1 | 9/21-10/2 |  |  | P1 | 9/21-10/2
| ENV53 | Regression | 9/7-9/18 |  | ENV53 | Regression | 9/7-9/18
|  | P1 | 9/30-10/2 |  |  | P1 | 9/30-10/2
| ENV04 | UAT | 9/21-10/16 |  | ENV04 | UAT | 9/21-10/16
|  | P1 | 10/5-10/16 |  |  | P1 | 10/5-10/16
| ENV05 | Prod | 2026-10-18 |  | ENV05 | Prod | 2026-10-18
15.5 | Scope Freeze \ Req Approval \ Design Review |  | 7/27-8/14 | 15.5 | Scope Freeze \ Req Approval \ Design Review |  | 7/27-8/14
| ENV52 | MMIS Dev | 8/17-9/18 |  | ENV52 | MMIS Dev | 8/17-9/18
|  | P1 | 10/26-11/6 |  |  | P1 | 10/26-11/6
| ENV57 | MMIS SIT | 9/14-10/9 |  | ENV57 | MMIS SIT | 9/14-10/9
|  | P1 | 10/26-11/6 |  |  | P1 | 10/26-11/6
| ENV53 | Regression | 10/12-10/23 |  | ENV53 | Regression | 10/12-10/23
|  | P1 | 11/4-11/6 |  |  | P1 | 11/4-11/6
| ENV04 | UAT | 10/26-11/20 |  | ENV04 | UAT | 10/26-11/20
|  | P1 | 11/9-11/20 |  |  | P1 | 11/9-11/20
| ENV05 | Prod | 2026-11-22 |  | ENV05 | Prod | 2026-11-22
15.6 | Scope Freeze \ Req Approval \ Design Review |  | 8/31-9/18 | 15.6 | Scope Freeze \ Req Approval \ Design Review |  | 8/31-9/18
| ENV52 | MMIS Dev | 9/21-10/23 |  | ENV52 | MMIS Dev | 9/21-10/23
|  | P1 | 11/30-12/4 |  |  | P1 | 11/30-12/4
| ENV57 | MMIS SIT | 10/19-11/13 |  | ENV57 | MMIS SIT | 10/19-11/13
|  | P1 | 11/30-12/4 |  |  | P1 | 11/30-12/4
| ENV53 | Regression | 11/16-11/27 |  | ENV53 | Regression | 11/16-11/27
|  | P1 | 12/2-12/4 |  |  | P1 | 12/2-12/4
| ENV04 | UAT | 11/30-12/18 |  | ENV04 | UAT | 11/30-12/18
|  | P1 | 12/7-12/18 |  |  | P1 | 12/7-12/18
| ENV05 | Prod | 2026-12-20 |  | ENV05 | Prod | 2026-12-20
15.7 | Scope Freeze \ Req Approval \ Design Review |  | 10/5-10/23 | 15.7 | Scope Freeze \ Req Approval \ Design Review |  | 10/5-10/23
| ENV52 | MMIS Dev | 10/26-11/27 |  | ENV52 | MMIS Dev | 10/26-11/27
|  | P1 | 1/4-1/15 |  |  | P1 | 1/4-1/15
| ENV57 | MMIS SIT | 11/23-12/18 |  | ENV57 | MMIS SIT | 11/23-12/18
|  | P1 | 1/4-1/15 |  |  | P1 | 1/4-1/15
| ENV53 | Regression | 12/21-1/1 |  | ENV53 | Regression | 12/21-1/1
|  | P1 | 1/13-1/15 |  |  | P1 | 1/13-1/15
| ENV04 | UAT | 1/4-1/29 |  | ENV04 | UAT | 1/4-1/29
|  | P1 | 1/20-1/29 |  |  | P1 | 1/20-1/29
| ENV05 | Prod | 2027-01-31 |  | ENV05 | Prod | 2027-01-31

## 20251016
Release | ENV | Phase | 2025-07-01 |  |  |  | 2025-08-01 |  |  |  | 2025-09-01 |  |  |  |  | 2025-10-01 |  |  |  | 2025-11-01 |  |  |  | 2025-12-01 |  |  |  |  | 2026-01-01 |  |  |  | 2026-02-01 |  |  |  | 2026-03-01 |  |  |  |  | 2026-04-01 |  |  |  | 2026-05-01 |  |  |  |  | 2026-06-01 |  |  |  | 2026-07-01 |  |  |  |  | 2026-08-01 |  |  |  | 2026-09-01 |  |  |  | 2026-10-01 |  |  |  | 2026-11-01 |  |  |  |  | 2026-12-01 |  |  |  | 2027-01-01 |  |  |  | 2027-02-01
 | time axis 2025-07-07 to 2027-02-22
14.4 | Scope Freeze \ Req Approval \ Design Review |  | 2025-07-07: 7/7-7/25
| ENV52 | MMIS Dev | 2025-08-25: 7/28-8/29; 2025-10-06: P1
| ENV57 | MMIS SIT | 2025-08-25: 8/25-9/19; 2025-10-06: P1
| ENV53 | Regression | 2025-09-22: 9/22-10/3; 2025-10-13: P1(10/15-10/17)
| ENV04 | UAT | 2025-10-06: 10/6-10/31; 2025-10-20: P1(10/20-10/31)
| ENV05 | Prod | 2025-11-03: 2025-11-02
14.5 | Scope Freeze \ Req Approval \ Design Review |  | 2025-08-11: 8/11-8/29
| ENV52 | MMIS Dev | 2025-09-29: 9/1-10/3; 2025-11-10: P1
| ENV57 | MMIS SIT | 2025-09-29: 9/29-10/24; 2025-11-10: P1
| ENV53 | Regression | 2025-10-27: 10/27-11/7; 2025-11-17: P1(11/19-11/21)
| ENV04 | UAT | 2025-11-10: 11/10-12/5; 2025-11-24: P1(11/24-12/5)
| ENV05 | Prod | 2025-12-08: 2025-12-07
| SysDoc |  | 2025-11-24: Check out to QA - R14.4 & R14.5; 2025-12-08: Check in Doc \ NTT Data Review; 2025-12-22: Review \ Feedback \ Meetings \ Formatting Changes
14.6 | Scope Freeze \ Req Approval \ Design Review |  | 2025-09-15: 9/15-10/3
| ENV52 | MMIS Dev | 2025-11-03: 10/6-11/7; 2025-12-15: P1
| ENV57 | MMIS SIT | 2025-11-03: 11/3-11/28; 2025-12-15: P1
| ENV53 | Regression | 2025-12-01: 12/1-12/12; 2025-12-22: P1(12/24-12/26)
| ENV04 | UAT | 2025-12-15: 12/15-1/9; 2025-12-29: P1(12/29-1/9)
| ENV05 | Prod | 2026-01-12: 2026-01-11
14.7 | Scope Freeze \ Req Approval \ Design Review |  | 2025-10-20: 10/20-11/7
| ENV52 | MMIS Dev | 2025-12-08: 11/10-12/12; 2026-01-19: P1
| ENV57 | MMIS SIT | 2025-12-08: 12/8-1/2; 2026-01-19: P1
| ENV53 | Regression | 2026-01-05: 1/5-1/16; 2026-01-26: P1(1/28-1/30)
| ENV04 | UAT | 2026-01-19: 1/19-2/13; 2026-02-02: P1(2/2-2/13)
| ENV05 | Prod | 2026-02-16: 2026-02-15
| SysDoc |  | 2026-02-02: Check out to QA - R14.6 & R14.7; 2026-02-16: Check in Doc \ NTT Data Review; 2026-03-02: Review \ Feedback \ Meetings \ Formatting Changes
14.8 | Scope Freeze \ Req Approval \ Design Review |  | 2025-11-24: 11/24 - 12/12
| ENV52 | MMIS Dev | 2026-01-12: 12/15-1/16; 2026-02-23: P1
| ENV57 | MMIS SIT | 2026-01-12: 1/12-2/6; 2026-02-23: P1
| ENV53 | Regression | 2026-02-09: 2/9-2/20; 2026-03-02: P1(3/4-3/6)
| ENV04 | UAT | 2026-02-23: 2/23-3/20; 2026-03-09: P1(3/9-3/20)
| ENV05 | Prod | 2026-03-23: 2026-03-22
14.9 | Scope Freeze \ Req Approval \ Design Review |  | 2025-12-29: 12/29-1/16
| ENV52 | MMIS Dev | 2026-02-16: 1/19-2/20; 2026-03-30: P1
| ENV57 | MMIS SIT | 2026-02-16: 2/16-3/13; 2026-03-30: P1
| ENV53 | Regression | 2026-03-16: 3/16-3/27; 2026-04-06: P1(4/8-4/10)
| ENV04 | UAT | 2026-03-30: 3/30-4/24; 2026-04-13: P1(4/13-4/24)
| ENV05 | Prod | 2026-04-27: 2026-04-26
| SysDoc |  | 2026-04-13: Check out to QA - R14.8 & R14.9; 2026-04-27: Check in Doc \ NTT Data Review; 2026-05-11: Review \ Feedback \ Meetings \ Formatting Changes
15 | Scope Freeze \ Req Approval \ Design Review |  | 2026-02-02: 2/2-2/20
| ENV52 | MMIS Dev | 2026-03-23: 2/23-3/27; 2026-05-04: P1
| ENV57 | MMIS SIT | 2026-03-23: 3/23-4/17; 2026-05-04: P1
| ENV53 | Regression | 2026-04-20: 4/20-5/1; 2026-05-11: P1(5/13-5/15)
| ENV04 | UAT | 2026-05-04: 5/4-5/29; 2026-05-18: P1(5/18-5/29)
| ENV05 | Prod | 2026-06-01: 2026-05-31
15.1 | Scope Freeze \ Req Approval \ Design Review |  | 2026-03-09: 3/9-3/27
| ENV52 | MMIS Dev | 2026-04-27: 3/30-5/1; 2026-06-08: P1
| ENV57 | MMIS SIT | 2026-04-27: 4/27-5/22; 2026-06-08: P1
| ENV53 | Regression | 2026-05-25: 5/25-6/5; 2026-06-15: P1(6/17-6/19)
| ENV04 | UAT | 2026-06-08: 6/8-7/3; 2026-06-22: P1(6/22-7/3)
| ENV05 | Prod | 2026-07-06: 2026-07-05
| SysDoc |  | 2026-06-22: Check out to QA - R15.0 & R15.1; 2026-07-06: Check in Doc \ NTT Data Review; 2026-07-20: Review \ Feedback \ Meetings \ Formatting Changes
15.2 | Scope Freeze \ Req Approval \ Design Review |  | 2026-04-13: 4/13-5/1
| ENV52 | MMIS Dev | 2026-06-01: 5/4-6/5; 2026-07-13: P1
| ENV57 | MMIS SIT | 2026-06-01: 6/1-6/26; 2026-07-13: P1
| ENV53 | Regression | 2026-06-29: 6/29-7/10; 2026-07-20: P1(7/22-7/24)
| ENV04 | UAT | 2026-07-13: 7/13-8/7; 2026-07-27: P1(7/27-8/7)
| ENV05 | Prod | 2026-08-10: 2026-08-09
15.3 | Scope Freeze \ Req Approval \ Design Review |  | 2026-05-18: 5/18-6/5
| ENV52 | MMIS Dev | 2026-07-06: 6/8-7/10; 2026-08-17: P1
| ENV57 | MMIS SIT | 2026-07-06: 7/6-7/31; 2026-08-17: P1
| ENV53 | Regression | 2026-08-03: 8/3-8/14; 2026-08-24: P1(8/26-8/28)
| ENV04 | UAT | 2026-08-17: 8/17-9/11; 2026-08-31: P1(8/31-9/11)
| ENV05 | Prod | 2026-09-14: 2026-09-13
| SysDoc |  | 2026-08-31: Check out to QA - R15.2 & R15.3; 2026-09-14: Check in Doc \ NTT Data Review; 2026-09-28: Review \ Feedback \ Meetings \ Formatting Changes
15.4 | Scope Freeze \ Req Approval \ Design Review |  | 2026-06-22: 6/22-7/10
| ENV52 | MMIS Dev | 2026-08-10: 7/13-8/14; 2026-09-21: P1
| ENV57 | MMIS SIT | 2026-08-10: 8/10-9/4; 2026-09-21: P1
| ENV53 | Regression | 2026-09-07: 9/7-9/18; 2026-09-28: P1(9/30-10/2)
| ENV04 | UAT | 2026-09-21: 9/21-10/16; 2026-10-05: P1(10/5-10/16)
| ENV05 | Prod | 2026-10-19: 2026-10-18
15.5 | Scope Freeze \ Req Approval \ Design Review |  | 2026-07-27: 7/27-8/14
| ENV52 | MMIS Dev | 2026-09-14: 8/17-9/18; 2026-10-26: P1
| ENV57 | MMIS SIT | 2026-09-14: 9/14-10/9; 2026-10-26: P1
| ENV53 | Regression | 2026-10-12: 10/12-10/23; 2026-11-02: P1(11/4-11/6)
| ENV04 | UAT | 2026-10-26: 10/26-11/20; 2026-11-09: P1(11/9-11/20)
| ENV05 | Prod | 2026-11-23: 2026-11-22
| SysDoc |  | 2026-11-09: Check out to QA - R15.4 & R15.5; 2026-11-23: Check in Doc \ NTT Data Review; 2026-12-07: Review \ Feedback \ Meetings \ Formatting Changes
15.6 | Scope Freeze \ Req Approval \ Design Review |  | 2026-08-31: 8/31-9/18
| ENV52 | MMIS Dev | 2026-10-19: 9/21-10/23; 2026-11-30: P1
| ENV57 | MMIS SIT | 2026-10-19: 10/19-11/13; 2026-11-30: P1
| ENV53 | Regression | 2026-11-16: 11/16-11/27; 2026-11-30: P1(12/2-12/4)
| ENV04 | UAT | 2026-11-30: 11/30-12/18; 2026-12-07: P1(12/7-12/18)
| ENV05 | Prod | 2026-12-21: 2026-12-20
15.7 | Scope Freeze \ Req Approval \ Design Review |  | 2026-10-05: 10/5-10/23
| ENV52 | MMIS Dev | 2026-11-23: 10/26-11/27; 2027-01-04: P1
| ENV57 | MMIS SIT | 2026-11-23: 11/23-12/18; 2027-01-04: P1
| ENV53 | Regression | 2026-12-21: 12/21-1/1; 2027-01-11: P1(1/13-1/15)
| ENV04 | UAT | 2027-01-04: 1/4-1/29; 2027-01-18: P1(1/20-1/29)
| ENV05 | Prod | 2027-02-01: 2027-01-31
| SysDoc |  | 2027-01-18: Check out to QA - R15.6 & R15.7; 2027-02-01: Check in Doc \ NTT Data Review; 2027-02-15: Review \ Feedback \ Meetings \ Formatting Changes

## 20250121
Release | ENV | Phase | 2024-04-01 |  |  |  |  | 2024-05-01 |  |  |  | 2024-06-01 |  |  |  |  | 2024-07-01 |  |  |  | 2024-08-01 |  |  |  |  | 2024-09-01 |  |  |  | 2024-10-01 |  |  |  | 2024-11-01 |  |  |  | 2024-12-01 |  |  |  |  | 2025-01-01 |  |  |  | 2025-02-01 |  |  |  | 2025-03-01 |  |  |  |  | 2025-04-01 |  |  |  | 2025-05-01 |  |  |  | 2025-06-01 |  |  |  |  | 2025-07-01 |  |  |  | 2025-08-01 |  |  |  | 2025-09-01 |  |  |  |  | 2025-10-01 |  |  |  | 2025-11-01 |  |  |  | 2025-12-01 |  |  |  |  | 2026-01-01 |  |  |  | 2026-02-01 |  |  |  | 2026-03-01
 | time axis 2024-04-01 to 2026-03-30
13.5 | Scope Freeze \ Req Approval \ Design Review |  | 2024-08-26: 8/26-9/13
| ENV52 | MMIS Dev | 2024-10-14: 9/16-10/18; 2024-11-25: P1
| ENV57 | MMIS SIT | 2024-10-14: 10/14-11/8; 2024-11-25: P1
| ENV53 | Regression | 2024-11-11: 11/11-11/22; 2024-12-02: P1(12/4-12/6)
| ENV04 | UAT | 2024-11-25: 11/25-12/20; 2024-12-09: P1(12/9-12/20)
| ENV05 | Prod | 2024-12-23: 2024-12-22
| SysDoc |  | 2024-12-09: Check out to QA - R13.4 & R13.5; 2024-12-23: Check in Doc \ NTT Data Review; 2025-01-06: Review \ Feedback \ Meetings \ Formatting Changes
13.6 | Scope Freeze \ Req Approval \ Design Review |  | 2024-09-30: 9/30-10/18
| ENV52 | MMIS Dev | 2024-11-18: 10/21-11/22; 2024-12-30: P1
| ENV57 | MMIS SIT | 2024-11-18: 11/18-12/13; 2024-12-30: P1
| ENV53 | Regression | 2024-12-16: 12/16-12/27; 2025-01-06: P1(1/8-1/10)
| ENV04 | UAT | 2024-12-30: 12/30-1/24; 2025-01-20: P1(1/21-1/31)
| ENV05 | Prod | 2025-02-03: 2025-02-02
13.7 | Scope Freeze \ Req Approval \ Design Review |  | 2024-11-04: 11/4-11/22
| ENV52 | MMIS Dev | 2024-12-23: 11/25-12/27; 2025-02-03: P1
| ENV57 | MMIS SIT | 2024-12-23: 12/23-1/17; 2025-02-03: P1
| ENV53 | Regression | 2025-01-20: 1/20-1/31; 2025-02-10: P1(2/12-2/14)
| ENV04 | UAT | 2025-02-03: 2/5-2/28; 2025-02-17: P1(2/17-2/28)
| ENV05 | Prod | 2025-03-03: 2025-03-02
| SysDoc |  | 2025-02-17: Check out to QA - R13.6 & R13.7; 2025-03-03: Check in Doc \ NTT Data Review; 2025-03-17: Review \ Feedback \ Meetings \ Formatting Changes
13.8 | Scope Freeze \ Req Approval \ Design Review |  | 2024-12-09: 12/9-12/27
| ENV52 | MMIS Dev | 2025-01-27: 12/30-1/31; 2025-03-10: P1
| ENV57 | MMIS SIT | 2025-01-27: 1/27-2/21; 2025-03-10: P1
| ENV53 | Regression | 2025-02-24: 2/24-3/7; 2025-03-17: P1(3/19-3/21)
| ENV04 | UAT | 2025-03-10: 3/10-4/1; 2025-03-24: P1(3/24-4/4)
| ENV05 | Prod | 2025-04-07: 2025-04-06
13.9 | Scope Freeze \ Req Approval \ Design Review |  | 2025-01-13: 1/13-1/31
| ENV52 | MMIS Dev | 2025-03-03: 2/3-3/7; 2025-04-14: P1
| ENV57 | MMIS SIT | 2025-03-03: 3/3-3/28; 2025-04-14: P1
| ENV53 | Regression | 2025-03-31: 3/31-4/11; 2025-04-21: P1(4/23-4/25)
| ENV04 | UAT | 2025-04-14: 4/14-5/9; 2025-04-28: P1(4/28-5/9)
| ENV05 | Prod | 2025-05-12: 2025-05-11
| SysDoc |  | 2025-04-28: Check out to QA - R13.8 & R13.9; 2025-05-12: Check in Doc \ NTT Data Review; 2025-05-26: Review \ Feedback \ Meetings \ Formatting Changes
14 | Scope Freeze \ Req Approval \ Design Review |  | 2025-02-17: 2/17-3/7
| ENV52 | MMIS Dev | 2025-04-07: 3/10-4/11; 2025-05-19: P1
| ENV57 | MMIS SIT | 2025-04-07: 4/7-5/2; 2025-05-19: P1
| ENV53 | Regression | 2025-05-05: 5/5-5/16; 2025-05-26: P1(5/28-5/30)
| ENV04 | UAT | 2025-05-19: 5/19-6/13; 2025-06-02: P1(6/2-6/13)
| ENV05 | Prod | 2025-06-16: 2025-06-15
14.1 | Scope Freeze \ Req Approval \ Design Review |  | 2025-03-24: 3/24-4/11
| ENV52 | MMIS Dev | 2025-05-12: 4/14-5/16; 2025-06-23: P1
| ENV57 | MMIS SIT | 2025-05-12: 5/12-6/6; 2025-06-23: P1
| ENV53 | Regression | 2025-06-09: 6/9-6/20; 2025-06-30: P1(7/2-7/4)
| ENV04 | UAT | 2025-06-23: 6/23-7/18; 2025-07-07: P1(7/7-7/18)
| ENV05 | Prod | 2025-07-21: 2025-07-20
| SysDoc |  | 2025-07-07: Check out to QA - R14.0 & R14.1; 2025-07-21: Check in Doc \ NTT Data Review; 2025-08-04: Review \ Feedback \ Meetings \ Formatting Changes
14.2 | Scope Freeze \ Req Approval \ Design Review |  | 2025-04-28: 4/28-5/16
| ENV52 | MMIS Dev | 2025-06-16: 5/19-6/20; 2025-07-28: P1
| ENV57 | MMIS SIT | 2025-06-16: 6/16-7/11; 2025-07-28: P1
| ENV53 | Regression | 2025-07-14: 7/14-7/25; 2025-08-04: P1(8/6-8/8)
| ENV04 | UAT | 2025-07-28: 7/28-8/22; 2025-08-11: P1(8/11-8/22)
| ENV05 | Prod | 2025-08-25: 2025-08-24
14.3 | Scope Freeze \ Req Approval \ Design Review |  | 2025-06-02: 6/2-6/20
| ENV52 | MMIS Dev | 2025-07-21: 6/23-7/25; 2025-09-01: P1
| ENV57 | MMIS SIT | 2025-07-21: 7/21-8/15; 2025-09-01: P1
| ENV53 | Regression | 2025-08-18: 8/18-8/29; 2025-09-08: P1(9/10-9/12)
| ENV04 | UAT | 2025-09-01: 9/1-9/26; 2025-09-15: P1(9/15-9/26)
| ENV05 | Prod | 2025-09-29: 2025-09-28
| SysDoc |  | 2025-09-15: Check out to QA - R14.2 & R14.3; 2025-09-29: Check in Doc \ NTT Data Review; 2025-10-13: Review \ Feedback \ Meetings \ Formatting Changes
14.4 | Scope Freeze \ Req Approval \ Design Review |  | 2025-07-07: 7/7-7/25
| ENV52 | MMIS Dev | 2025-08-25: 7/28-8/29; 2025-10-06: P1
| ENV57 | MMIS SIT | 2025-08-25: 8/25-9/19; 2025-10-06: P1
| ENV53 | Regression | 2025-09-22: 9/22-10/3; 2025-10-13: P1(10/15-10/17)
| ENV04 | UAT | 2025-10-06: 10/6-10/31; 2025-10-20: P1(10/20-10/31)
| ENV05 | Prod | 2025-11-03: 2025-11-02
14.5 | Scope Freeze \ Req Approval \ Design Review |  | 2025-08-11: 8/11-8/29
| ENV52 | MMIS Dev | 2025-09-29: 9/1-10/3; 2025-11-10: P1
| ENV57 | MMIS SIT | 2025-09-29: 9/29-10/24; 2025-11-10: P1
| ENV53 | Regression | 2025-10-27: 10/27-11/7; 2025-11-17: P1(11/19-11/21)
| ENV04 | UAT | 2025-11-10: 11/10-12/5; 2025-11-24: P1(11/24-12/5)
| ENV05 | Prod | 2025-12-08: 2025-12-07
| SysDoc |  | 2025-11-24: Check out to QA - R14.4 & R14.5; 2025-12-08: Check in Doc \ NTT Data Review; 2025-12-22: Review \ Feedback \ Meetings \ Formatting Changes
14.6 | Scope Freeze \ Req Approval \ Design Review |  | 2025-09-15: 9/15-10/3
| ENV52 | MMIS Dev | 2025-11-03: 10/6-11/7; 2025-12-15: P1
| ENV57 | MMIS SIT | 2025-11-03: 11/3-11/28; 2025-12-15: P1
| ENV53 | Regression | 2025-12-01: 12/1-12/12; 2025-12-22: P1(12/24-12/26)
| ENV04 | UAT | 2025-12-15: 12/15-1/9; 2025-12-29: P1(12/29-1/9)
| ENV05 | Prod | 2026-01-12: 2026-01-11
14.7 | Scope Freeze \ Req Approval \ Design Review |  | 2025-10-20: 10/20-11/7
| ENV52 | MMIS Dev | 2025-12-08: 11/10-12/12; 2026-01-19: P1
| ENV57 | MMIS SIT | 2025-12-08: 12/8-1/2; 2026-01-19: P1
| ENV53 | Regression | 2026-01-05: 1/5-1/15; 2026-01-26: P1(1/28-1/30)
| ENV04 | UAT | 2026-01-19: 1/19-2/13; 2026-02-02: P1(2/2-2/13)
| ENV05 | Prod | 2026-02-16: 2026-02-15
| SysDoc |  | 2026-02-02: Check out to QA - R14.6 & R14.7; 2026-02-16: Check in Doc \ NTT Data Review; 2026-03-02: Review \ Feedback \ Meetings \ Formatting Changes

## 20241114
Release | ENV | Phase | 2024-04-01 |  |  |  |  | 2024-05-01 |  |  |  | 2024-06-01 |  |  |  |  | 2024-07-01 |  |  |  | 2024-08-01 |  |  |  |  | 2024-09-01 |  |  |  | 2024-10-01 |  |  |  | 2024-11-01 |  |  |  | 2024-12-01 |  |  |  |  | 2025-01-01 |  |  |  | 2025-02-01 |  |  |  | 2025-03-01 |  |  |  |  | 2025-04-01 |  |  |  | 2025-05-01 |  |  |  | 2025-06-01 |  |  |  |  | 2025-07-01 |  |  |  | 2025-08-01 |  |  |  | 2025-09-01 |  |  |  |  | 2025-10-01 |  |  |  | 2025-11-01 |  |  |  | 2025-12-01 |  |  |  |  | 2026-01-01 |  |  |  | 2026-02-01 |  |  |  | 2026-03-01
 | time axis 2024-04-01 to 2026-03-30
13.1 | Scope Freeze \ Req Approval \ Design Review |  | 2024-04-08: 4/8-4/26
| ENV52 | MMIS Dev | 2024-05-27: 4/29-5/31; 2024-07-08: P1
| ENV57 | MMIS SIT | 2024-05-27: 5/27-6/21; 2024-07-08: P1
| ENV53 | Regression | 2024-06-24: 6/24-7/5; 2024-07-15: P1(7/17-7/19)
| ENV04 | UAT | 2024-07-08: 7/8-8/2; 2024-07-22: P1(7/22-8/2)
| ENV05 | Prod | 2024-08-05: 2024-08-04
| SysDoc |  | 2024-07-22: Check out to QA - R13.0 & R13.1; 2024-08-05: Check in Doc \ NTT Data Review; 2024-08-19: Review \ Feedback \ Meetings \ Formatting Changes
13.2 | Scope Freeze \ Req Approval \ Design Review |  | 2024-05-13: 5/13-5/31
| ENV52 | MMIS Dev | 2024-07-01: 6/3-7/5; 2024-08-12: P1
| ENV57 | MMIS SIT | 2024-07-01: 7/1-7/26; 2024-08-12: P1
| ENV53 | Regression | 2024-07-29: 7/29-8/9; 2024-08-19: P1(8/21-8/23)
| ENV04 | UAT | 2024-08-12: 8/12-9/6; 2024-08-26: P1(8/26-9/6)
| ENV05 | Prod | 2024-09-09: 2024-09-08
13.3 | Scope Freeze \ Req Approval \ Design Review |  | 2024-06-17: 6/17-7/5
| ENV52 | MMIS Dev | 2024-08-05: 7/8-8/9; 2024-09-16: P1
| ENV57 | MMIS SIT | 2024-08-05: 8/5-8/30; 2024-09-16: P1
| ENV53 | Regression | 2024-09-02: 9/2-9/13; 2024-09-23: P1(9/25-9/27)
| ENV04 | UAT | 2024-09-16: 9/16-10/11; 2024-09-30: P1(9/30-10/11)
| ENV05 | Prod | 2024-10-14: 2024-10-13
| SysDoc |  | 2024-09-30: Check out to QA - R13.2 & R13.3; 2024-10-14: Check in Doc \ NTT Data Review; 2024-10-28: Review \ Feedback \ Meetings \ Formatting Changes
13.4 | Scope Freeze \ Req Approval \ Design Review |  | 2024-07-22: 7/22-8/9
| ENV52 | MMIS Dev | 2024-09-09: 8/12-9/13; 2024-10-21: P1
| ENV57 | MMIS SIT | 2024-09-09: 9/9-10/4; 2024-10-21: P1
| ENV53 | Regression | 2024-10-07: 10/7-10/18; 2024-10-28: P1(10/30-11/1)
| ENV04 | UAT | 2024-10-21: 10/21-11/15; 2024-11-04: P1(11/4-11/15)
| ENV05 | Prod | 2024-11-18: 2024-11-17
13.5 | Scope Freeze \ Req Approval \ Design Review |  | 2024-08-26: 8/26-9/13
| ENV52 | MMIS Dev | 2024-10-14: 9/16-10/18; 2024-11-25: P1
| ENV57 | MMIS SIT | 2024-10-14: 10/14-11/8; 2024-11-25: P1
| ENV53 | Regression | 2024-11-11: 11/11-11/22; 2024-12-02: P1(12/4-12/6)
| ENV04 | UAT | 2024-11-25: 11/25-12/20; 2024-12-09: P1(12/9-12/20)
| ENV05 | Prod | 2024-12-23: 2024-12-22
| SysDoc |  | 2024-12-09: Check out to QA - R13.4 & R13.5; 2024-12-23: Check in Doc \ NTT Data Review; 2025-01-06: Review \ Feedback \ Meetings \ Formatting Changes
13.6 | Scope Freeze \ Req Approval \ Design Review |  | 2024-09-30: 9/30-10/18
| ENV52 | MMIS Dev | 2024-11-18: 10/21-11/22; 2024-12-30: P1
| ENV57 | MMIS SIT | 2024-11-18: 11/18-12/13; 2024-12-30: P1
| ENV53 | Regression | 2024-12-16: 12/16-12/27; 2025-01-06: P1(1/8-1/10)
| ENV04 | UAT | 2024-12-30: 12/30-1/24; 2025-01-13: P1(1/13-1/24)
| ENV05 | Prod | 2025-01-27: 2025-01-26
13.7 | Scope Freeze \ Req Approval \ Design Review |  | 2024-11-04: 11/4-11/22
| ENV52 | MMIS Dev | 2024-12-23: 11/25-12/27; 2025-02-03: P1
| ENV57 | MMIS SIT | 2024-12-23: 12/23-1/17; 2025-02-03: P1
| ENV53 | Regression | 2025-01-20: 1/20-1/31; 2025-02-10: P1(2/12-2/14)
| ENV04 | UAT | 2025-02-03: 2/3-2/28; 2025-02-17: P1(2/17-2/28)
| ENV05 | Prod | 2025-03-03: 2025-03-02
| SysDoc |  | 2025-02-17: Check out to QA - R13.6 & R13.7; 2025-03-03: Check in Doc \ NTT Data Review; 2025-03-17: Review \ Feedback \ Meetings \ Formatting Changes
13.8 | Scope Freeze \ Req Approval \ Design Review |  | 2024-12-09: 12/9-12/27
| ENV52 | MMIS Dev | 2025-01-27: 12/30-1/31; 2025-03-10: P1
| ENV57 | MMIS SIT | 2025-01-27: 1/27-2/21; 2025-03-10: P1
| ENV53 | Regression | 2025-02-24: 2/24-3/7; 2025-03-17: P1(3/19-3/21)
| ENV04 | UAT | 2025-03-10: 3/10-4/1; 2025-03-24: P1(3/24-4/4)
| ENV05 | Prod | 2025-04-07: 2025-04-06
13.9 | Scope Freeze \ Req Approval \ Design Review |  | 2025-01-13: 1/13-1/31
| ENV52 | MMIS Dev | 2025-03-03: 2/3-3/7; 2025-04-14: P1
| ENV57 | MMIS SIT | 2025-03-03: 3/3-3/28; 2025-04-14: P1
| ENV53 | Regression | 2025-03-31: 3/31-4/11; 2025-04-21: P1(4/23-4/25)
| ENV04 | UAT | 2025-04-14: 4/14-5/9; 2025-04-28: P1(4/28-5/9)
| ENV05 | Prod | 2025-05-12: 2025-05-11
| SysDoc |  | 2025-04-28: Check out to QA - R13.8 & R13.9; 2025-05-12: Check in Doc \ NTT Data Review; 2025-05-26: Review \ Feedback \ Meetings \ Formatting Changes
14 | Scope Freeze \ Req Approval \ Design Review |  | 2025-02-17: 2/17-3/7
| ENV52 | MMIS Dev | 2025-04-07: 3/10-4/11; 2025-05-19: P1
| ENV57 | MMIS SIT | 2025-04-07: 4/7-5/2; 2025-05-19: P1
| ENV53 | Regression | 2025-05-05: 5/5-5/16; 2025-05-26: P1(5/28-5/30)
| ENV04 | UAT | 2025-05-19: 5/19-6/13; 2025-06-02: P1(6/2-6/13)
| ENV05 | Prod | 2025-06-16: 2025-06-15
14.1 | Scope Freeze \ Req Approval \ Design Review |  | 2025-03-24: 3/24-4/11
| ENV52 | MMIS Dev | 2025-05-12: 4/14-5/16; 2025-06-23: P1
| ENV57 | MMIS SIT | 2025-05-12: 5/12-6/6; 2025-06-23: P1
| ENV53 | Regression | 2025-06-09: 6/9-6/20; 2025-06-30: P1(7/2-7/4)
| ENV04 | UAT | 2025-06-23: 6/23-7/18; 2025-07-07: P1(7/7-7/18)
| ENV05 | Prod | 2025-07-21: 2025-07-20
| SysDoc |  | 2025-07-07: Check out to QA - R14.0 & R14.1; 2025-07-21: Check in Doc \ NTT Data Review; 2025-08-04: Review \ Feedback \ Meetings \ Formatting Changes
14.2 | Scope Freeze \ Req Approval \ Design Review |  | 2025-04-28: 4/28-5/16
| ENV52 | MMIS Dev | 2025-06-16: 5/19-6/20; 2025-07-28: P1
| ENV57 | MMIS SIT | 2025-06-16: 6/16-7/11; 2025-07-28: P1
| ENV53 | Regression | 2025-07-14: 7/14-7/25; 2025-08-04: P1(8/6-8/8)
| ENV04 | UAT | 2025-07-28: 7/28-8/22; 2025-08-11: P1(8/11-8/22)
| ENV05 | Prod | 2025-08-25: 2025-08-24
14.3 | Scope Freeze \ Req Approval \ Design Review |  | 2025-06-02: 6/2-6/20
| ENV52 | MMIS Dev | 2025-07-21: 6/23-7/25; 2025-09-01: P1
| ENV57 | MMIS SIT | 2025-07-21: 7/21-8/15; 2025-09-01: P1
| ENV53 | Regression | 2025-08-18: 8/18-8/29; 2025-09-08: P1(9/10-9/12)
| ENV04 | UAT | 2025-09-01: 9/1-9/26; 2025-09-15: P1(9/15-9/26)
| ENV05 | Prod | 2025-09-29: 2025-09-28
| SysDoc |  | 2025-09-15: Check out to QA - R14.2 & R14.3; 2025-09-29: Check in Doc \ NTT Data Review; 2025-10-13: Review \ Feedback \ Meetings \ Formatting Changes
14.4 | Scope Freeze \ Req Approval \ Design Review |  | 2025-07-07: 7/7-7/25
| ENV52 | MMIS Dev | 2025-08-25: 7/28-8/29; 2025-10-06: P1
| ENV57 | MMIS SIT | 2025-08-25: 8/25-9/19; 2025-10-06: P1
| ENV53 | Regression | 2025-09-22: 9/22-10/3; 2025-10-13: P1(10/15-10/17)
| ENV04 | UAT | 2025-10-06: 10/6-10/31; 2025-10-20: P1(10/20-10/31)
| ENV05 | Prod | 2025-11-03: 2025-11-02
14.5 | Scope Freeze \ Req Approval \ Design Review |  | 2025-08-11: 8/11-8/29
| ENV52 | MMIS Dev | 2025-09-29: 9/1-10/3; 2025-11-10: P1
| ENV57 | MMIS SIT | 2025-09-29: 9/29-10/24; 2025-11-10: P1
| ENV53 | Regression | 2025-10-27: 10/27-11/7; 2025-11-17: P1(11/19-11/21)
| ENV04 | UAT | 2025-11-10: 11/10-12/5; 2025-11-24: P1(11/24-12/5)
| ENV05 | Prod | 2025-12-08: 2025-12-07
| SysDoc |  | 2025-11-24: Check out to QA - R14.4 & R14.5; 2025-12-08: Check in Doc \ NTT Data Review; 2025-12-22: Review \ Feedback \ Meetings \ Formatting Changes
14.6 | Scope Freeze \ Req Approval \ Design Review |  | 2025-09-15: 9/15-10/3
| ENV52 | MMIS Dev | 2025-11-03: 10/6-11/7; 2025-12-15: P1
| ENV57 | MMIS SIT | 2025-11-03: 11/3-11/28; 2025-12-15: P1
| ENV53 | Regression | 2025-12-01: 12/1-12/12; 2025-12-22: P1(12/24-12/26)
| ENV04 | UAT | 2025-12-15: 12/15-1/9; 2025-12-29: P1(12/29-1/9)
| ENV05 | Prod | 2026-01-12: 2026-01-11
14.7 | Scope Freeze \ Req Approval \ Design Review |  | 2025-10-20: 10/20-11/7
| ENV52 | MMIS Dev | 2025-12-08: 11/10-12/12; 2026-01-19: P1
| ENV57 | MMIS SIT | 2025-12-08: 12/8-1/2; 2026-01-19: P1
| ENV53 | Regression | 2026-01-05: 1/5-1/15; 2026-01-26: P1(1/28-1/30)
| ENV04 | UAT | 2026-01-19: 1/19-2/13; 2026-02-02: P1(2/2-2/13)
| ENV05 | Prod | 2026-02-16: 2026-02-15
| SysDoc |  | 2026-02-02: Check out to QA - R14.6 & R14.7; 2026-02-16: Check in Doc \ NTT Data Review; 2026-03-02: Review \ Feedback \ Meetings \ Formatting Changes

## 20240125
Release | ENV | Phase | 2023-05-01 |  |  |  |  | 2023-06-01 |  |  |  | 2023-07-01 |  |  |  |  | 2023-08-01 |  |  |  | 2023-09-01 |  |  |  | 2023-10-01 |  |  |  |  | 2023-11-01 |  |  |  | 2023-12-01 |  |  |  | 2024-01-01 |  |  |  |  | 2024-02-01 |  |  |  | 2024-03-01 |  |  |  | 2024-04-01 |  |  |  |  | 2024-05-01 |  |  |  | 2024-06-01 |  |  |  |  | 2024-07-01 |  |  |  | 2024-08-01 |  |  |  |  | 2024-09-01 |  |  |  | 2024-10-01 |  |  |  |  | 2024-11-01 |  |  |  | 2024-12-01 |  |  |  |  | 2025-01-01 |  |  |  | 2025-02-01 |  |  |  |  | 2024-05-01
 | time axis 2023-05-01 to 2025-04-07
12.2 | Scope Freeze \ Req Approval \ Design Review |  | 2023-05-22: 5/22-6/9
| ENV52 | MMIS Dev | 2023-07-10: 6/12-7/14; 2023-08-21: P1
| ENV57 | MMIS SIT | 2023-07-10: 7/10-8/4; 2023-08-21: P1
| ENV53 | Regression | 2023-08-07: 8/7-8/19; 2023-08-28: P1(8/30-9/1)
| ENV04 | UAT | 2023-08-21: 8/21-9/15; 2023-09-04: P1(9/4-9/15)
| ENV05 | Prod | 2023-09-18: 2023-09-17
12.3 | Scope Freeze \ Req Approval \ Design Review |  | 2023-06-26: 6/26-7/14
| ENV52 | MMIS Dev | 2023-08-14: 7/17-8/18; 2023-09-25: P1
| ENV57 | MMIS SIT | 2023-08-14: 8/14-9/8; 2023-09-25: P1
| ENV53 | Regression | 2023-09-11: 9/11-9/22; 2023-10-02: P1(10/4-10/6)
| ENV04 | UAT | 2023-09-25: 9/25-10/20; 2023-10-09: P1(10/9-10/20)
| ENV05 | Prod | 2023-10-23: 2023-10-22
| SysDoc |  | 2023-10-09: Check out to QA - R12.2 & R12.3; 2023-10-23: Check in Doc \ NTT Data Review; 2023-11-06: Review \ Feedback \ Meetings \ Formatting Changes
12.4 | Scope Freeze \ Req Approval \ Design Review |  | 2023-07-31: 7/31-8/18
| ENV52 | MMIS Dev | 2023-09-18: 8/21-9/22; 2023-10-30: P1
| ENV57 | MMIS SIT | 2023-09-18: 9/18-10/13; 2023-10-30: P1
| ENV53 | Regression | 2023-10-16: 10/16-10/27; 2023-11-06: P1(11/8-11/10)
| ENV04 | UAT | 2023-10-30: 10/30-11/24; 2023-11-13: P1(11/13-11/24)
| ENV05 | Prod | 2023-11-27: 2023-11-26
12.5 | Scope Freeze \ Req Approval \ Design Review |  | 2023-09-04: 9/4-9/22
| ENV52 | MMIS Dev | 2023-10-23: 9/25-10/27; 2023-12-04: P1
| ENV57 | MMIS SIT | 2023-10-23: 10/23-11/17; 2023-12-04: P1
| ENV53 | Regression | 2023-11-20: 11/20-12/1; 2023-12-11: P1(12/13-12/15)
| ENV04 | UAT | 2023-12-04: 12/4-1/5; 2023-12-11: P1(12/18-1/5)
| ENV05 | Prod | 2024-01-08: 2024-01-07
| SysDoc |  | 2023-12-25: Check out to QA - R12.4 & R12.5; 2024-01-08: Check in Doc \ NTT Data Review; 2024-01-22: Review \ Feedback \ Meetings \ Formatting Changes
12.6 | Scope Freeze \ Req Approval \ Design Review |  | 2023-10-09: 10/9-11/3
| ENV52 | MMIS Dev | 2023-12-04: 11/6-12/8; 2024-01-15: P1
| ENV57 | MMIS SIT | 2023-12-04: 12/4-12/29; 2024-01-15: P1
| ENV53 | Regression | 2024-01-01: 1/1-1/12; 2024-01-22: P1(1/24-1/26)
| ENV04 | UAT | 2024-01-15: 1/15-2/11; 2024-01-29: P1(1/29-2/11)
| ENV05 | Prod | 2024-02-12: 2024-02-11
12.6.1 | ENV52 | MMIS Dev | 2024-01-22: 1/25-2/2
| ENV57 | MMIS SIT | 2024-01-29: 1/30 - 2/7
| ENV53 | Regression | 2024-02-05: 2/8-2/9
| ENV04 | UAT | 2024-02-12: 2/12-2/23
| ENV05 | Prod | 2024-02-26: 2024-02-25
12.7 | Scope Freeze \ Req Approval \ Design Review |  | 2023-11-20: 11/20-12/8
| ENV52 | MMIS Dev | 2024-01-08: 12/11-1/12; 2024-03-04: P1
| ENV57 | MMIS SIT | 2024-01-08: 1/8-2/16; 2024-03-04: P1
| ENV53 | Regression | 2024-02-19: 2/19-3/1; 2024-03-04: P1(3/7-3/8)
| ENV04 | UAT | 2024-03-04: 3/4-3/22; 2024-03-11: P1(3/11-3/22)
| ENV05 | Prod | 2024-03-25: 2024-03-24
| SysDoc |  | 2024-03-11: Check out to QA - R12.6 & R12.7; 2024-03-25: Check in Doc \ NTT Data Review; 2024-04-08: Review \ Feedback \ Meetings \ Formatting Changes
12.8 | Scope Freeze \ Req Approval \ Design Review |  | 2023-12-25: 12/25-1/12
| ENV52 | MMIS Dev | 2024-02-12: 1/15-2/16; 2024-04-01: P1
| ENV57 | MMIS SIT | 2024-02-19: 2/19-3/15; 2024-04-01: P1
| ENV53 | Regression | 2024-03-18: 3/18-3/29
| ENV04 | UAT | 2024-04-01: 4/1-4/19; 2024-04-08: P1(4/8-4/19)
| ENV05 | Prod | 2024-04-22: 2024-04-21
12.9 | Scope Freeze \ Req Approval \ Design Review |  | 2024-01-29: 1/29-2/17
| ENV52 | MMIS Dev | 2024-03-18: 2/19-3/22; 2024-04-29: P1
| ENV57 | MMIS SIT | 2024-03-18: 3/18-4/12; 2024-04-29: P1
| ENV53 | Regression | 2024-04-15: 4/15-4/26; 2024-05-06: P1(5/8-5/10)
| ENV04 | UAT | 2024-04-29: 4/29-5/24; 2024-05-13: P1(5/13-5/24)
| ENV05 | Prod | 2024-05-27: 2024-05-26
| SysDoc |  | 2024-05-13: Check out to QA - R12.8 & R12.9; 2024-05-27: Check in Doc \ NTT Data Review; 2024-06-10: Review \ Feedback \ Meetings \ Formatting Changes
13 | Scope Freeze \ Req Approval \ Design Review |  | 2024-03-04: 3/4-3/22
| ENV52 | MMIS Dev | 2024-04-22: 3/25-4/26; 2024-06-03: P1
| ENV57 | MMIS SIT | 2024-04-22: 4/22-5/17; 2024-06-03: P1
| ENV53 | Regression | 2024-05-20: 5/20-5/31; 2024-06-10: P1(6/12-6/14)
| ENV04 | UAT | 2024-06-03: 6/3-6/28; 2024-06-17: P1(6/17-6/28)
| ENV05 | Prod | 2024-07-01: 2024-06-30
13.1 | Scope Freeze \ Req Approval \ Design Review |  | 2024-04-08: 4/8-4/26
| ENV52 | MMIS Dev | 2024-05-27: 4/29-5/31; 2024-07-08: P1
| ENV57 | MMIS SIT | 2024-05-27: 5/27-6/21; 2024-07-08: P1
| ENV53 | Regression | 2024-06-24: 6/24-7/5; 2024-07-15: P1(7/17-7/19)
| ENV04 | UAT | 2024-07-08: 7/8-8/2; 2024-07-22: P1(7/22-8/2)
| ENV05 | Prod | 2024-08-05: 2024-08-04
| SysDoc |  | 2024-07-22: Check out to QA - R13.0 & R13.1; 2024-08-05: Check in Doc \ NTT Data Review; 2024-08-19: Review \ Feedback \ Meetings \ Formatting Changes
13.2 | Scope Freeze \ Req Approval \ Design Review |  | 2024-05-13: 5/13-5/31
| ENV52 | MMIS Dev | 2024-07-01: 6/3-7/5; 2024-08-12: P1
| ENV57 | MMIS SIT | 2024-07-01: 7/1-7/26; 2024-08-12: P1
| ENV53 | Regression | 2024-07-29: 7/29-8/9; 2024-08-19: P1(8/21-8/23)
| ENV04 | UAT | 2024-08-12: 8/12-9/6; 2024-08-26: P1(8/26-9/6)
| ENV05 | Prod | 2024-09-09: 2024-09-08
13.3 | Scope Freeze \ Req Approval \ Design Review |  | 2024-06-17: 6/17-7/5
| ENV52 | MMIS Dev | 2024-08-05: 7/8-8/9; 2024-09-16: P1
| ENV57 | MMIS SIT | 2024-08-05: 8/5-8/30; 2024-09-16: P1
| ENV53 | Regression | 2024-09-02: 9/2-9/13; 2024-09-23: P1(9/25-9/27)
| ENV04 | UAT | 2024-09-16: 9/16-10/11; 2024-09-30: P1(9/30-10/11)
| ENV05 | Prod | 2024-10-14: 2024-10-13
| SysDoc |  | 2024-09-30: Check out to QA - R13.2 & R13.3; 2024-10-14: Check in Doc \ NTT Data Review; 2024-10-28: Review \ Feedback \ Meetings \ Formatting Changes
13.4 | Scope Freeze \ Req Approval \ Design Review |  | 2024-07-22: 7/22-8/9
| ENV52 | MMIS Dev | 2024-09-09: 8/12-9/13; 2024-10-21: P1
| ENV57 | MMIS SIT | 2024-09-09: 9/9-10/4; 2024-10-21: P1
| ENV53 | Regression | 2024-10-07: 10/7-10/18; 2024-10-28: P1(10/30-11/1)
| ENV04 | UAT | 2024-10-21: 10/21-11/15; 2024-11-04: P1(11/4-11/15)
| ENV05 | Prod | 2024-11-18: 2024-11-17
13.5 | Scope Freeze \ Req Approval \ Design Review |  | 2024-08-26: 8/26-9/13
| ENV52 | MMIS Dev | 2024-10-14: 9/16-10/18; 2024-11-25: P1
| ENV57 | MMIS SIT | 2024-10-14: 10/14-11/8; 2024-11-25: P1
| ENV53 | Regression | 2024-11-11: 11/11-11/22; 2024-12-02: P1(12/4-12/6)
| ENV04 | UAT | 2024-11-25: 11/25-12/20; 2024-12-09: P1(12/9-12/20)
| ENV05 | Prod | 2024-12-23: 2024-12-22
| SysDoc |  | 2024-12-09: Check out to QA - R13.4 & R13.5; 2024-12-23: Check in Doc \ NTT Data Review; 2025-01-06: Review \ Feedback \ Meetings \ Formatting Changes
13.6 | Scope Freeze \ Req Approval \ Design Review |  | 2024-09-30: 9/30-10/18
| ENV52 | MMIS Dev | 2024-11-18: 10/21-11/22; 2024-12-30: P1
| ENV57 | MMIS SIT | 2024-11-18: 11/18-12/13; 2024-12-30: P1
| ENV53 | Regression | 2024-12-16: 12/16-12/27; 2025-01-06: P1(1/8-1/10)
| ENV04 | UAT | 2024-12-30: 12/30-1/24; 2025-01-13: P1(1/13-1/24)
| ENV05 | Prod | 2025-01-27: 2025-01-26
13.7 | Scope Freeze \ Req Approval \ Design Review |  | 2024-11-04: 11/4-11/22
| ENV52 | MMIS Dev | 2024-12-23: 11/25-12/27; 2025-02-03: P1
| ENV57 | MMIS SIT | 2024-12-23: 12/23-1/17; 2025-02-03: P1
| ENV53 | Regression | 2025-01-20: 1/20-1/31; 2025-02-10: P1(2/12-2/14)
| ENV04 | UAT | 2025-02-03: 2/3-2/28; 2025-02-17: P1(2/17-2/28)
| ENV05 | Prod | 2025-03-03: 2025-03-02
| SysDoc |  | 2025-02-17: Check out to QA - R13.6 & R13.7; 2025-03-03: Check in Doc \ NTT Data Review; 2025-03-17: Review \ Feedback \ Meetings \ Formatting Changes

## 20231108
Release | ENV | Phase | 2023-05-01 |  |  |  |  | 2023-06-01 |  |  |  | 2023-07-01 |  |  |  |  | 2023-08-01 |  |  |  | 2023-09-01 |  |  |  | 2023-10-01 |  |  |  |  | 2023-11-01 |  |  |  | 2023-12-01 |  |  |  | 2024-01-01 |  |  |  |  | 2024-02-01 |  |  |  | 2024-03-01 |  |  |  | 2024-04-01 |  |  |  |  | 2024-05-01 |  |  |  | 2024-06-01 |  |  |  |  | 2024-07-01 |  |  |  | 2024-08-01 |  |  |  |  | 2024-09-01 |  |  |  | 2024-10-01 |  |  |  |  | 2024-11-01 |  |  |  | 2024-12-01 |  |  |  |  | 2025-01-01 |  |  |  | 2025-02-01 |  |  |  |  | 2024-05-01
 | time axis 2023-05-01 to 2025-04-07
12.2 | Scope Freeze \ Req Approval \ Design Review |  | 2023-05-22: 5/22-6/9
| ENV52 | MMIS Dev | 2023-07-10: 6/12-7/14; 2023-08-21: P1
| ENV57 | MMIS SIT | 2023-07-10: 7/10-8/4; 2023-08-21: P1
| ENV53 | Regression | 2023-08-07: 8/7-8/19; 2023-08-28: P1(8/30-9/1)
| ENV04 | UAT | 2023-08-21: 8/21-9/15; 2023-09-04: P1(9/4-9/15)
| ENV05 | Prod | 2023-09-18: 2023-09-17
12.3 | Scope Freeze \ Req Approval \ Design Review |  | 2023-06-26: 6/26-7/14
| ENV52 | MMIS Dev | 2023-08-14: 7/17-8/18; 2023-09-25: P1
| ENV57 | MMIS SIT | 2023-08-14: 8/14-9/8; 2023-09-25: P1
| ENV53 | Regression | 2023-09-11: 9/11-9/22; 2023-10-02: P1(10/4-10/6)
| ENV04 | UAT | 2023-09-25: 9/25-10/20; 2023-10-09: P1(10/9-10/20)
| ENV05 | Prod | 2023-10-23: 2023-10-22
| SysDoc |  | 2023-10-09: Check out to QA - R12.2 & R12.3; 2023-10-23: Check in Doc \ NTT Data Review; 2023-11-06: Review \ Feedback \ Meetings \ Formatting Changes
12.4 | Scope Freeze \ Req Approval \ Design Review |  | 2023-07-31: 7/31-8/18
| ENV52 | MMIS Dev | 2023-09-18: 8/21-9/22; 2023-10-30: P1
| ENV57 | MMIS SIT | 2023-09-18: 9/18-10/13; 2023-10-30: P1
| ENV53 | Regression | 2023-10-16: 10/16-10/27; 2023-11-06: P1(11/8-11/10)
| ENV04 | UAT | 2023-10-30: 10/30-11/24; 2023-11-13: P1(11/13-11/24)
| ENV05 | Prod | 2023-11-27: 2023-11-26
12.5 | Scope Freeze \ Req Approval \ Design Review |  | 2023-09-04: 9/4-9/22
| ENV52 | MMIS Dev | 2023-10-23: 9/25-10/27; 2023-12-04: P1
| ENV57 | MMIS SIT | 2023-10-23: 10/23-11/17; 2023-12-04: P1
| ENV53 | Regression | 2023-11-20: 11/20-12/1; 2023-12-11: P1(12/13-12/15)
| ENV04 | UAT | 2023-12-04: 12/4-1/5; 2023-12-11: P1(12/18-1/5)
| ENV05 | Prod | 2024-01-08: 2024-01-07
| SysDoc |  | 2023-12-25: Check out to QA - R12.4 & R12.5; 2024-01-08: Check in Doc \ NTT Data Review; 2024-01-22: Review \ Feedback \ Meetings \ Formatting Changes
12.6 | Scope Freeze \ Req Approval \ Design Review |  | 2023-10-09: 10/9-11/3
| ENV52 | MMIS Dev | 2023-12-04: 11/6-12/8; 2024-01-15: P1
| ENV57 | MMIS SIT | 2023-12-04: 12/4-12/29; 2024-01-15: P1
| ENV53 | Regression | 2024-01-01: 1/1-1/12; 2024-01-22: P1(1/24-1/26)
| ENV04 | UAT | 2024-01-15: 1/15-2/11; 2024-01-29: P1(1/29-2/11)
| ENV05 | Prod | 2024-02-12: 2024-02-11
12.7 | Scope Freeze \ Req Approval \ Design Review |  | 2023-11-20: 11/20-12/8
| ENV52 | MMIS Dev | 2024-01-08: 12/11-1/12; 2024-02-19: P1
| ENV57 | MMIS SIT | 2024-01-08: 1/8-2/2; 2024-02-19: P1
| ENV53 | Regression | 2024-02-05: 1/29-2/16; 2024-02-26: P1(2/28-3/1)
| ENV04 | UAT | 2024-02-19: 2/19-3/15; 2024-03-04: P1(3/4-3/15)
| ENV05 | Prod | 2024-03-18: 2024-03-17
| SysDoc |  | 2024-02-19: Check out to QA - R12.6 & R12.7; 2024-03-04: Check in Doc \ NTT Data Review; 2024-03-18: Review \ Feedback \ Meetings \ Formatting Changes
12.8 | Scope Freeze \ Req Approval \ Design Review |  | 2023-12-25: 12/25-1/12
| ENV52 | MMIS Dev | 2024-02-12: 1/15-2/16; 2024-03-25: P1
| ENV57 | MMIS SIT | 2024-02-12: 2/12-3/8; 2024-03-25: P1
| ENV53 | Regression | 2024-03-11: 3/11-3/22; 2024-04-01: P1(4/3-4/5)
| ENV04 | UAT | 2024-03-25: 3/25-4/19; 2024-04-08: P1(4/8-4/19)
| ENV05 | Prod | 2024-04-22: 2024-04-21
12.9 | Scope Freeze \ Req Approval \ Design Review |  | 2024-01-29: 1/29-2/17
| ENV52 | MMIS Dev | 2024-03-18: 2/19-3/22; 2024-04-29: P1
| ENV57 | MMIS SIT | 2024-03-18: 3/18-4/12; 2024-04-29: P1
| ENV53 | Regression | 2024-04-15: 4/15-4/26; 2024-05-06: P1(5/8-5/10)
| ENV04 | UAT | 2024-04-29: 4/29-5/24; 2024-05-13: P1(5/13-5/24)
| ENV05 | Prod | 2024-05-27: 2024-05-26
| SysDoc |  | 2024-05-13: Check out to QA - R12.8 & R12.9; 2024-05-27: Check in Doc \ NTT Data Review; 2024-06-10: Review \ Feedback \ Meetings \ Formatting Changes
13 | Scope Freeze \ Req Approval \ Design Review |  | 2024-03-04: 3/4-3/22
| ENV52 | MMIS Dev | 2024-04-22: 3/25-4/26; 2024-06-03: P1
| ENV57 | MMIS SIT | 2024-04-22: 4/22-5/17; 2024-06-03: P1
| ENV53 | Regression | 2024-05-20: 5/20-5/31; 2024-06-10: P1(6/12-6/14)
| ENV04 | UAT | 2024-06-03: 6/3-6/28; 2024-06-17: P1(6/17-6/28)
| ENV05 | Prod | 2024-07-01: 2024-06-30
13.1 | Scope Freeze \ Req Approval \ Design Review |  | 2024-04-08: 4/8-4/26
| ENV52 | MMIS Dev | 2024-05-27: 4/29-5/31; 2024-07-08: P1
| ENV57 | MMIS SIT | 2024-05-27: 5/27-6/21; 2024-07-08: P1
| ENV53 | Regression | 2024-06-24: 6/24-7/5; 2024-07-15: P1(7/17-7/19)
| ENV04 | UAT | 2024-07-08: 7/8-8/2; 2024-07-22: P1(7/22-8/2)
| ENV05 | Prod | 2024-08-05: 2024-08-04
| SysDoc |  | 2024-07-22: Check out to QA - R13.0 & R13.1; 2024-08-05: Check in Doc \ NTT Data Review; 2024-08-19: Review \ Feedback \ Meetings \ Formatting Changes
13.2 | Scope Freeze \ Req Approval \ Design Review |  | 2024-05-13: 5/13-5/31
| ENV52 | MMIS Dev | 2024-07-01: 6/3-7/5; 2024-08-12: P1
| ENV57 | MMIS SIT | 2024-07-01: 7/1-7/26; 2024-08-12: P1
| ENV53 | Regression | 2024-07-29: 7/29-8/9; 2024-08-19: P1(8/21-8/23)
| ENV04 | UAT | 2024-08-12: 8/12-9/6; 2024-08-26: P1(8/26-9/6)
| ENV05 | Prod | 2024-09-09: 2024-09-08
13.3 | Scope Freeze \ Req Approval \ Design Review |  | 2024-06-17: 6/17-7/5
| ENV52 | MMIS Dev | 2024-08-05: 7/8-8/9; 2024-09-16: P1
| ENV57 | MMIS SIT | 2024-08-05: 8/5-8/30; 2024-09-16: P1
| ENV53 | Regression | 2024-09-02: 9/2-9/13; 2024-09-23: P1(9/25-9/27)
| ENV04 | UAT | 2024-09-16: 9/16-10/11; 2024-09-30: P1(9/30-10/11)
| ENV05 | Prod | 2024-10-14: 2024-10-13
| SysDoc |  | 2024-09-30: Check out to QA - R13.2 & R13.3; 2024-10-14: Check in Doc \ NTT Data Review; 2024-10-28: Review \ Feedback \ Meetings \ Formatting Changes
13.4 | Scope Freeze \ Req Approval \ Design Review |  | 2024-07-22: 7/22-8/9
| ENV52 | MMIS Dev | 2024-09-09: 8/12-9/13; 2024-10-21: P1
| ENV57 | MMIS SIT | 2024-09-09: 9/9-10/4; 2024-10-21: P1
| ENV53 | Regression | 2024-10-07: 10/7-10/18; 2024-10-28: P1(10/30-11/1)
| ENV04 | UAT | 2024-10-21: 10/21-11/15; 2024-11-04: P1(11/4-11/15)
| ENV05 | Prod | 2024-11-18: 2024-11-17
13.5 | Scope Freeze \ Req Approval \ Design Review |  | 2024-08-26: 8/26-9/13
| ENV52 | MMIS Dev | 2024-10-14: 9/16-10/18; 2024-11-25: P1
| ENV57 | MMIS SIT | 2024-10-14: 10/14-11/8; 2024-11-25: P1
| ENV53 | Regression | 2024-11-11: 11/11-11/22; 2024-12-02: P1(12/4-12/6)
| ENV04 | UAT | 2024-11-25: 11/25-12/20; 2024-12-09: P1(12/9-12/20)
| ENV05 | Prod | 2024-12-23: 2024-12-22
| SysDoc |  | 2024-12-09: Check out to QA - R13.4 & R13.5; 2024-12-23: Check in Doc \ NTT Data Review; 2025-01-06: Review \ Feedback \ Meetings \ Formatting Changes
13.6 | Scope Freeze \ Req Approval \ Design Review |  | 2024-09-30: 9/30-10/18
| ENV52 | MMIS Dev | 2024-11-18: 10/21-11/22; 2024-12-30: P1
| ENV57 | MMIS SIT | 2024-11-18: 11/18-12/13; 2024-12-30: P1
| ENV53 | Regression | 2024-12-16: 12/16-12/27; 2025-01-06: P1(1/8-1/10)
| ENV04 | UAT | 2024-12-30: 12/30-1/24; 2025-01-13: P1(1/13-1/24)
| ENV05 | Prod | 2025-01-27: 2025-01-26
13.7 | Scope Freeze \ Req Approval \ Design Review |  | 2024-11-04: 11/4-11/22
| ENV52 | MMIS Dev | 2024-12-23: 11/25-12/27; 2025-02-03: P1
| ENV57 | MMIS SIT | 2024-12-23: 12/23-1/17; 2025-02-03: P1
| ENV53 | Regression | 2025-01-20: 1/20-1/31; 2025-02-10: P1(2/12-2/14)
| ENV04 | UAT | 2025-02-03: 2/3-2/28; 2025-02-17: P1(2/17-2/28)
| ENV05 | Prod | 2025-03-03: 2025-03-02
| SysDoc |  | 2025-02-17: Check out to QA - R13.6 & R13.7; 2025-03-03: Check in Doc \ NTT Data Review; 2025-03-17: Review \ Feedback \ Meetings \ Formatting Changes

## 20230320
Release | ENV | Phase | 2019-07-01 |  |  |  |  | 2019-08-01 |  |  |  | 2022-05-01 |  |  |  |  | 2022-06-01 |  |  |  | 2022-07-01 |  |  |  | 2022-08-01 |  |  |  |  | 2022-09-01 |  |  |  | 2022-10-01 |  |  |  | 2022-11-01 |  |  |  |  | 2022-12-01 |  |  |  | 2023-01-01 |  |  |  |  | 2023-02-01 |  |  |  | 2023-03-01 |  |  |  | 2023-04-01 |  |  |  | 2023-05-01 |  |  |  |  | 2023-06-01 |  |  |  | 2023-07-01 |  |  |  |  | 2023-08-01 |  |  |  | 2023-09-01 |  |  |  | 2023-10-01 |  |  |  |  | 2023-11-01 |  |  |  | 2023-12-01 |  |  |  | 2024-01-01 |  |  |  |  | 2024-02-01 |  |  |  | 2024-03-01 |  |  |  | 2024-04-01
 | time axis 2019-07-01 to 2024-04-29
8.6 | Scope Freeze \ Req Approval \ Design Review |  | 2019-07-15: 7/15-8/2
| ENV52 | MMIS Dev | bar: 2019-08-05 to 2019-08-26
| ENV57 | MMIS SIT
| ENV53 | Regression
| ENV04 | UAT
| ENV05 | Prod
8.7 | Scope Freeze \ Req Approval \ Design Review |  | 2019-08-19: 8/19-9/6
| ENV52 | MMIS Dev
| ENV57 | MMIS SIT
| ENV53 | Regression
| ENV04 | UAT
| ENV05 | Prod
SysDoc
11.2 | Scope Freeze \ Req Approval \ Design Review |  | 2022-05-02: 5/2-5/20
| ENV52 | MMIS Dev | 2022-06-20: 5/23-6/24; 2022-08-01: P1
| ENV57 | MMIS SIT | 2022-06-20: 6/20-7/15; 2022-08-01: P1
| ENV53 | Regression | 2022-07-18: 7/18-7/29; 2022-08-08: P1(8/10-8/12)
| ENV04 | UAT | 2022-08-01: 8/4-8/26; 2022-08-15: P1(8/15-8/26)
| ENV05 | Prod | 2022-08-29: 2022-08-28
11.3 | Scope Freeze \ Req Approval \ Design Review |  | 2022-06-06: 6/6-6/24
| ENV52 | MMIS Dev | 2022-07-25: 6/27-7/29; 2022-09-05: P1
| ENV57 | MMIS SIT | 2022-07-25: 7/25-8/19; 2022-09-05: P1
| ENV53 | Regression | 2022-08-22: 8/22-9/2; 2022-09-12: P1(9/14-9/16)
| ENV04 | UAT | 2022-09-05: 9/5-9/30; 2022-09-19: P1(9/19-9/30)
| ENV05 | Prod | 2022-10-03: 2022-10-02
| SysDoc |  | 2022-09-19: Check out to QA - R11.2 & R11.3; 2022-10-03: Check in Doc \ NTT Data Review; 2022-10-17: Review \ Feedback \ Meetings \ Formatting Changes
11.4 | Scope Freeze \ Req Approval \ Design Review |  | 2022-07-11: 7/11-7/29
| ENV52 | MMIS Dev | 2022-08-29: 8/1-9/2; 2022-10-10: P1
| ENV57 | MMIS SIT | 2022-08-29: 8/29-9/23; 2022-10-10: P1
| ENV53 | Regression | 2022-09-26: 9/26-10/7; 2022-10-17: P1(10/19-10/21)
| ENV04 | UAT | 2022-10-10: 10/10-11/4; 2022-10-24: P1(10/24-11/4)
| ENV05 | Prod | 2022-11-07: 2022-11-06
11.5 | Scope Freeze \ Req Approval \ Design Review |  | 2022-08-15: 8/15-9/2
| ENV52 | MMIS Dev | 2022-10-03: 9/5-10/7; 2022-11-14: P1
| ENV57 | MMIS SIT | 2022-10-03: 10/3-10/28; 2022-11-14: P1
| ENV53 | Regression | 2022-10-31: 10/31-11/11; 2022-11-21: P1(11/23-11/25)
| ENV04 | UAT | 2022-11-14: 11/14-12/9; 2022-11-28: P1(11/28-12/9)
| ENV05 | Prod | 2022-12-12: 2022-12-11
| SysDoc |  | 2022-11-28: Check out to QA - R11.4 & R11.5; 2022-12-12: Check in Doc \ NTT Data Review; 2022-12-26: Review \ Feedback \ Meetings \ Formatting Changes
11.6/ TSU | Scope Freeze \ Req Approval \ Design Review |  | 2022-09-19: 9/19-10/7
| ENV52 | MMIS Dev | 2022-11-07: 10/10-11/11; 2022-12-26: P1; 2023-01-09: P2
| ENV57 | MMIS SIT | 2022-11-07: 11/7-12/2; 2022-12-26: P1; 2023-01-09: P2
| ENV53 | Regression | 2022-12-05: 12/5-12/23; 2023-01-02: P1(1/4-1/6); 2023-01-16: P2(1/18-1/20)
| TSU(ENV05) | Prod Pre-Cutover | 2022-12-26: 12/30-2/3; 2023-01-09: P1(1/9-2/3); 2023-01-23: P2(1/23-2/3)
| ENV04 | UAT | 2023-01-09: 1/9-2/10; 2023-01-23: P1(1/23-2/10)
| ENV05 | Prod | 2023-02-13: 2023-02-13
11.7 | Scope Freeze \ Req Approval \ Design Review |  | 2022-11-28: 11/28-12/16
| ENV54 | MMIS Dev | 2023-01-16: 12/19-1/20; 2023-02-27: P1; 2023-03-06: P2
| ENV58 | MMIS SIT | 2023-01-16: 1/16-2/10; 2023-02-27: P1; 2023-03-06: P2
| ENV53 | Regression | 2023-02-13: 2/13-2/24; 2023-03-06: P1(3/8-3/10)
| ENV04 | UAT | 2023-02-27: 2/27-3/24; 2023-03-06: P1(3/6-3/24); 2023-03-13: P2(3/13-3/24); 2023-03-27: P3(3/29-4/7)
| ENV05 | Prod | 2023-03-27: 2023-03-26; 2023-04-10: 2023-04-09
| SysDoc |  | 2023-03-13: Check out to QA - R11.6 & R11.7; 2023-03-27: Check in Doc \ NTT Data Review; 2023-04-10: Review \ Feedback \ Meetings \ Formatting Changes
11.8 | Scope Freeze \ Req Approval \ Design Review |  | 2023-01-02: 1/2-1/20
| ENV54 | MMIS Dev | 2023-02-20: 1/23-2/24; 2023-04-10: P1
| ENV57 | MMIS SIT | 2023-02-20: 2/20-3/17; 2023-04-10: P1
| ENV53 | Regression | 2023-03-20: 3/20-4/7; 2023-04-10: P1(4/12-4/14)
| ENV04 | UAT | 2023-04-10: 4/12-4/28; 2023-04-17: P1(4/17-4/28)
| ENV05 | Prod | 2023-05-01: 2023-04-30
11.9 | Scope Freeze \ Req Approval \ Design Review |  | 2023-02-06: 2/6-2/24
| ENV52 | MMIS Dev | 2023-03-27: 2/27-3/31; 2023-05-08: P1
| ENV57 | MMIS SIT | 2023-03-27: 3/27-4/21; 2023-05-08: P1
| ENV53 | Regression | 2023-04-24: 4/24-5/5; 2023-05-15: P1(5/17-5/19)
| ENV04 | UAT | 2023-05-08: 5/8-6/2; 2023-05-22: P1(5/22-6/2)
| ENV05 | Prod | 2023-06-05: 2023-06-04
| SysDoc |  | 2023-05-22: Check out to QA - R11.8 & R11.9; 2023-06-05: Check in Doc \ NTT Data Review; 2023-06-19: Review \ Feedback \ Meetings \ Formatting Changes
12 | Scope Freeze \ Req Approval \ Design Review |  | 2023-03-13: 3/13-3/31
| ENV52 | MMIS Dev | 2023-05-01: 4/3-5/5; 2023-06-12: P1
| ENV57 | MMIS SIT | 2023-05-01: 5/1-5/26; 2023-06-12: P1
| ENV53 | Regression | 2023-05-29: 5/29-6/9; 2023-06-19: P1(6/21-6/23)
| ENV04 | UAT | 2023-06-12: 6/12-7/7; 2023-06-26: P1(6/26-7/7)
| ENV05 | Prod | 2023-07-10: 2023-07-09
12.1 | Scope Freeze \ Req Approval \ Design Review |  | 2023-04-17: 4/17-5/5
| ENV52 | MMIS Dev | 2023-06-05: 5/8-6/9; 2023-07-17: P1
| ENV57 | MMIS SIT | 2023-06-05: 6/5-6/30; 2023-07-17: P1
| ENV53 | Regression | 2023-07-03: 7/3-7/14; 2023-07-24: P1(7/26-7/28)
| ENV04 | UAT | 2023-07-17: 7/17-8/11; 2023-07-31: P1(7/31-8/11)
| ENV05 | Prod | 2023-08-14: 2023-08-13
| SysDoc |  | 2023-07-31: Check out to QA - R12.0 & R12.1; 2023-08-14: Check in Doc \ NTT Data Review; 2023-08-28: Review \ Feedback \ Meetings \ Formatting Changes
12.2 | Scope Freeze \ Req Approval \ Design Review |  | 2023-05-22: 5/22-6/9
| ENV52 | MMIS Dev | 2023-07-10: 6/12-7/14; 2023-08-21: P1
| ENV57 | MMIS SIT | 2023-07-10: 7/10-8/4; 2023-08-21: P1
| ENV53 | Regression | 2023-08-07: 8/7-8/19; 2023-08-28: P1(8/30-9/1)
| ENV04 | UAT | 2023-08-21: 8/21-9/15; 2023-09-04: P1(9/4-9/15)
| ENV05 | Prod | 2023-09-18: 2023-09-17
12.3 | Scope Freeze \ Req Approval \ Design Review |  | 2023-06-26: 6/26-7/14
| ENV52 | MMIS Dev | 2023-08-14: 7/17-8/18; 2023-09-25: P1
| ENV57 | MMIS SIT | 2023-08-14: 8/14-9/8; 2023-09-25: P1
| ENV53 | Regression | 2023-09-11: 9/11-9/22; 2023-10-02: P1(10/4-10/6)
| ENV04 | UAT | 2023-09-25: 9/25-10/20; 2023-10-09: P1(10/9-10/20)
| ENV05 | Prod | 2023-10-23: 2023-10-22
| SysDoc |  | 2023-10-09: Check out to QA - R12.2 & R12.3; 2023-10-23: Check in Doc \ NTT Data Review; 2023-11-06: Review \ Feedback \ Meetings \ Formatting Changes
12.4 | Scope Freeze \ Req Approval \ Design Review |  | 2023-07-31: 7/31-8/18
| ENV52 | MMIS Dev | 2023-09-18: 8/21-9/22; 2023-10-30: P1
| ENV57 | MMIS SIT | 2023-09-18: 9/18-10/13; 2023-10-30: P1
| ENV53 | Regression | 2023-10-16: 10/16-10/27; 2023-11-06: P1(11/8-11/10)
| ENV04 | UAT | 2023-10-30: 10/30-11/24; 2023-11-13: P1(11/13-11/24)
| ENV05 | Prod | 2023-11-27: 2023-11-26
12.5 | Scope Freeze \ Req Approval \ Design Review |  | 2023-09-04: 9/4-9/22
| ENV52 | MMIS Dev | 2023-10-23: 9/25-10/27; 2023-12-04: P1
| ENV57 | MMIS SIT | 2023-10-23: 10/23-11/17; 2023-12-04: P1
| ENV53 | Regression | 2023-11-20: 11/20-12/1; 2023-12-11: P1(12/13-12/15)
| ENV04 | UAT | 2023-12-04: 12/4-12/22; 2023-12-11: P1(12/18-12/22)
| ENV05 | Prod | 2023-12-25: 2023-12-24
| SysDoc |  | 2023-12-11: Check out to QA - R12.4 & R12.5; 2023-12-25: Check in Doc \ NTT Data Review; 2024-01-08: Review \ Feedback \ Meetings \ Formatting Changes
12.6 | Scope Freeze \ Req Approval \ Design Review |  | 2023-10-09: 10/9-10/27
| ENV52 | MMIS Dev | 2023-11-27: 10/30-12/1; 2024-01-08: P1
| ENV57 | MMIS SIT | 2023-11-27: 11/27-12/22; 2024-01-08: P1
| ENV53 | Regression | 2023-12-25: 12/25-1/5; 2024-01-15: P1(1/17-1/19)
| ENV04 | UAT | 2024-01-08: 1/8-2/2; 2024-01-22: P1(1/22-2/2)
| ENV05 | Prod | 2024-02-05: 2024-02-04
12.7 | Scope Freeze \ Req Approval \ Design Review |  | 2023-11-13: 11/13-12/1
| ENV52 | MMIS Dev | 2024-01-01: 12/4-1/5; 2024-02-12: P1
| ENV57 | MMIS SIT | 2024-01-01: 1/1-1/26; 2024-02-12: P1
| ENV53 | Regression | 2024-01-29: 1/29-2/9; 2024-02-19: P1(2/21-2/23)
| ENV04 | UAT | 2024-02-12: 2/12-3/8; 2024-02-26: P1(2/26-3/8)
| ENV05 | Prod | 2024-03-11: 2024-03-10
| SysDoc |  | 2024-02-26: Check out to QA - R12.6 & R12.7; 2024-03-11: Check in Doc \ NTT Data Review; 2024-03-25: Review \ Feedback \ Meetings \ Formatting Changes

## 20221108
Release | ENV | Phase | 2019-07-01 |  |  |  |  | 2019-08-01 |  |  |  | 2022-05-01 |  |  |  |  | 2022-06-01 |  |  |  | 2022-07-01 |  |  |  | 2022-08-01 |  |  |  |  | 2022-09-01 |  |  |  | 2022-10-01 |  |  |  | 2022-11-01 |  |  |  |  | 2022-12-01 |  |  |  | 2023-01-01 |  |  |  |  | 2023-02-01 |  |  |  | 2023-03-01 |  |  |  | 2023-04-01 |  |  |  | 2023-05-01 |  |  |  |  | 2023-06-01 |  |  |  | 2023-07-01 |  |  |  |  | 2023-08-01 |  |  |  | 2023-09-01 |  |  |  | 2023-10-01 |  |  |  |  | 2023-11-01 |  |  |  | 2023-12-01 |  |  |  | 2024-01-01 |  |  |  |  | 2024-02-01 |  |  |  | 2024-03-01 |  |  |  | 2024-04-01
 | time axis 2019-07-01 to 2024-04-29
8.6 | Scope Freeze \ Req Approval \ Design Review |  | 2019-07-15: 7/15-8/2
| ENV52 | MMIS Dev | bar: 2019-08-05 to 2019-08-26
| ENV57 | MMIS SIT
| ENV53 | Regression
| ENV04 | UAT
| ENV05 | Prod
8.7 | Scope Freeze \ Req Approval \ Design Review |  | 2019-08-19: 8/19-9/6
| ENV52 | MMIS Dev
| ENV57 | MMIS SIT
| ENV53 | Regression
| ENV04 | UAT
| ENV05 | Prod
SysDoc
11.2 | Scope Freeze \ Req Approval \ Design Review |  | 2022-05-02: 5/2-5/20
| ENV52 | MMIS Dev | 2022-06-20: 5/23-6/24; 2022-08-01: P1
| ENV57 | MMIS SIT | 2022-06-20: 6/20-7/15; 2022-08-01: P1
| ENV53 | Regression | 2022-07-18: 7/18-7/29; 2022-08-08: P1(8/10-8/12)
| ENV04 | UAT | 2022-08-01: 8/4-8/26; 2022-08-15: P1(8/15-8/26)
| ENV05 | Prod | 2022-08-29: 2022-08-28
11.3 | Scope Freeze \ Req Approval \ Design Review |  | 2022-06-06: 6/6-6/24
| ENV52 | MMIS Dev | 2022-07-25: 6/27-7/29; 2022-09-05: P1
| ENV57 | MMIS SIT | 2022-07-25: 7/25-8/19; 2022-09-05: P1
| ENV53 | Regression | 2022-08-22: 8/22-9/2; 2022-09-12: P1(9/14-9/16)
| ENV04 | UAT | 2022-09-05: 9/5-9/30; 2022-09-19: P1(9/19-9/30)
| ENV05 | Prod | 2022-10-03: 2022-10-02
| SysDoc |  | 2022-09-19: Check out to QA - R11.2 & R11.3; 2022-10-03: Check in Doc \ NTT Data Review; 2022-10-17: Review \ Feedback \ Meetings \ Formatting Changes
11.4 | Scope Freeze \ Req Approval \ Design Review |  | 2022-07-11: 7/11-7/29
| ENV52 | MMIS Dev | 2022-08-29: 8/1-9/2; 2022-10-10: P1
| ENV57 | MMIS SIT | 2022-08-29: 8/29-9/23; 2022-10-10: P1
| ENV53 | Regression | 2022-09-26: 9/26-10/7; 2022-10-17: P1(10/19-10/21)
| ENV04 | UAT | 2022-10-10: 10/10-11/4; 2022-10-24: P1(10/24-11/4)
| ENV05 | Prod | 2022-11-07: 2022-11-06
11.5 | Scope Freeze \ Req Approval \ Design Review |  | 2022-08-15: 8/15-9/2
| ENV52 | MMIS Dev | 2022-10-03: 9/5-10/7; 2022-11-14: P1
| ENV57 | MMIS SIT | 2022-10-03: 10/3-10/28; 2022-11-14: P1
| ENV53 | Regression | 2022-10-31: 10/31-11/11; 2022-11-21: P1(11/23-11/25)
| ENV04 | UAT | 2022-11-14: 11/14-12/9; 2022-11-28: P1(11/28-12/9)
| ENV05 | Prod | 2022-12-12: 2022-12-11
| SysDoc |  | 2022-11-28: Check out to QA - R11.4 & R11.5; 2022-12-12: Check in Doc \ NTT Data Review; 2022-12-26: Review \ Feedback \ Meetings \ Formatting Changes
11.6/ TSU | Scope Freeze \ Req Approval \ Design Review |  | 2022-09-19: 9/19-10/7
| ENV52 | MMIS Dev | 2022-11-07: 10/10-11/11; 2022-12-26: P1; 2023-01-09: P2
| ENV57 | MMIS SIT | 2022-11-07: 11/7-12/2; 2022-12-26: P1; 2023-01-09: P2
| ENV53 | Regression | 2022-12-05: 12/5-12/23; 2023-01-02: P1(1/4-1/6); 2023-01-16: P2(1/18-1/20)
| TSU(ENV05) | Prod Pre-Cutover | 2022-12-26: 12/30-2/3; 2023-01-09: P1(1/9-2/3); 2023-01-23: P2(1/23-2/3)
| ENV04 | UAT | 2023-01-09: 1/9-2/10; 2023-01-23: P1(1/23-2/10)
| ENV05 | Prod | 2023-02-13: 2023-02-13
11.7 | Scope Freeze \ Req Approval \ Design Review |  | 2022-11-28: 11/28-12/16
| ENV54 | MMIS Dev | 2023-01-16: 12/19-1/20; 2023-02-27: P1
| ENV58 | MMIS SIT | 2023-01-16: 1/16-2/10; 2023-02-27: P1
| ENV53 | Regression | 2023-02-13: 2/13-2/24; 2023-03-06: P1(3/8-3/10)
| ENV04 | UAT | 2023-02-27: 2/27-3/24; 2023-03-13: P1(3/13-3/24)
| ENV05 | Prod | 2023-03-27: 2023-03-26
| SysDoc |  | 2023-03-13: Check out to QA - R11.6 & R11.7; 2023-03-27: Check in Doc \ NTT Data Review; 2023-04-10: Review \ Feedback \ Meetings \ Formatting Changes
11.8 | Scope Freeze \ Req Approval \ Design Review |  | 2023-01-02: 1/2-1/20
| ENV54 | MMIS Dev | 2023-02-20: 1/23-2/24; 2023-04-03: P1
| ENV57 | MMIS SIT | 2023-02-20: 2/20-3/17; 2023-04-03: P1
| ENV53 | Regression | 2023-03-20: 3/20-3/31; 2023-04-10: P1(4/12-4/14)
| ENV04 | UAT | 2023-04-03: 4/3-4/28; 2023-04-17: P1(4/17-4/28)
| ENV05 | Prod | 2023-05-01: 2023-04-30
11.9 | Scope Freeze \ Req Approval \ Design Review |  | 2023-02-06: 2/6-2/24
| ENV52 | MMIS Dev | 2023-03-27: 2/27-3/31; 2023-05-08: P1
| ENV57 | MMIS SIT | 2023-03-27: 3/27-4/21; 2023-05-08: P1
| ENV53 | Regression | 2023-04-24: 4/24-5/5; 2023-05-15: P1(5/17-5/19)
| ENV04 | UAT | 2023-05-08: 5/8-6/2; 2023-05-22: P1(5/22-6/2)
| ENV05 | Prod | 2023-06-05: 2023-06-04
| SysDoc |  | 2023-05-22: Check out to QA - R11.8 & R11.9; 2023-06-05: Check in Doc \ NTT Data Review; 2023-06-19: Review \ Feedback \ Meetings \ Formatting Changes
12 | Scope Freeze \ Req Approval \ Design Review |  | 2023-03-13: 3/13-3/31
| ENV52 | MMIS Dev | 2023-05-01: 4/3-5/5; 2023-06-12: P1
| ENV57 | MMIS SIT | 2023-05-01: 5/1-5/26; 2023-06-12: P1
| ENV53 | Regression | 2023-05-29: 5/29-6/9; 2023-06-19: P1(6/21-6/23)
| ENV04 | UAT | 2023-06-12: 6/12-7/7; 2023-06-26: P1(6/26-7/7)
| ENV05 | Prod | 2023-07-10: 2023-07-09
12.1 | Scope Freeze \ Req Approval \ Design Review |  | 2023-04-17: 4/17-5/5
| ENV52 | MMIS Dev | 2023-06-05: 5/8-6/9; 2023-07-17: P1
| ENV57 | MMIS SIT | 2023-06-05: 6/5-6/30; 2023-07-17: P1
| ENV53 | Regression | 2023-07-03: 7/3-7/14; 2023-07-24: P1(7/26-7/28)
| ENV04 | UAT | 2023-07-17: 7/17-8/11; 2023-07-31: P1(7/31-8/11)
| ENV05 | Prod | 2023-08-14: 2023-08-13
| SysDoc |  | 2023-07-31: Check out to QA - R12.0 & R12.1; 2023-08-14: Check in Doc \ NTT Data Review; 2023-08-28: Review \ Feedback \ Meetings \ Formatting Changes
12.2 | Scope Freeze \ Req Approval \ Design Review |  | 2023-05-22: 5/22-6/9
| ENV52 | MMIS Dev | 2023-07-10: 6/12-7/14; 2023-08-21: P1
| ENV57 | MMIS SIT | 2023-07-10: 7/10-8/4; 2023-08-21: P1
| ENV53 | Regression | 2023-08-07: 8/7-8/19; 2023-08-28: P1(8/30-9/1)
| ENV04 | UAT | 2023-08-21: 8/21-9/15; 2023-09-04: P1(9/4-9/15)
| ENV05 | Prod | 2023-09-18: 2023-09-17
12.3 | Scope Freeze \ Req Approval \ Design Review |  | 2023-06-26: 6/26-7/14
| ENV52 | MMIS Dev | 2023-08-14: 7/17-8/18; 2023-09-25: P1
| ENV57 | MMIS SIT | 2023-08-14: 8/14-9/8; 2023-09-25: P1
| ENV53 | Regression | 2023-09-11: 9/11-9/22; 2023-10-02: P1(10/4-10/6)
| ENV04 | UAT | 2023-09-25: 9/25-10/20; 2023-10-09: P1(10/9-10/20)
| ENV05 | Prod | 2023-10-23: 2023-10-22
| SysDoc |  | 2023-10-09: Check out to QA - R12.2 & R12.3; 2023-10-23: Check in Doc \ NTT Data Review; 2023-11-06: Review \ Feedback \ Meetings \ Formatting Changes
12.4 | Scope Freeze \ Req Approval \ Design Review |  | 2023-07-31: 7/31-8/18
| ENV52 | MMIS Dev | 2023-09-18: 8/21-9/22; 2023-10-30: P1
| ENV57 | MMIS SIT | 2023-09-18: 9/18-10/13; 2023-10-30: P1
| ENV53 | Regression | 2023-10-16: 10/16-10/27; 2023-11-06: P1(11/8-11/10)
| ENV04 | UAT | 2023-10-30: 10/30-11/24; 2023-11-13: P1(11/13-11/24)
| ENV05 | Prod | 2023-11-27: 2023-11-26
12.5 | Scope Freeze \ Req Approval \ Design Review |  | 2023-09-04: 9/4-9/22
| ENV52 | MMIS Dev | 2023-10-23: 9/25-10/27; 2023-12-04: P1
| ENV57 | MMIS SIT | 2023-10-23: 10/23-11/17; 2023-12-04: P1
| ENV53 | Regression | 2023-11-20: 11/20-12/1; 2023-12-11: P1(12/13-12/15)
| ENV04 | UAT | 2023-12-04: 12/4-12/22; 2023-12-11: P1(12/18-12/22)
| ENV05 | Prod | 2023-12-25: 2023-12-24
| SysDoc |  | 2023-12-11: Check out to QA - R12.4 & R12.5; 2023-12-25: Check in Doc \ NTT Data Review; 2024-01-08: Review \ Feedback \ Meetings \ Formatting Changes
12.6 | Scope Freeze \ Req Approval \ Design Review |  | 2023-10-09: 10/9-10/27
| ENV52 | MMIS Dev | 2023-11-27: 10/30-12/1; 2024-01-08: P1
| ENV57 | MMIS SIT | 2023-11-27: 11/27-12/22; 2024-01-08: P1
| ENV53 | Regression | 2023-12-25: 12/25-1/5; 2024-01-15: P1(1/17-1/19)
| ENV04 | UAT | 2024-01-08: 1/8-2/2; 2024-01-22: P1(1/22-2/2)
| ENV05 | Prod | 2024-02-05: 2024-02-04
12.7 | Scope Freeze \ Req Approval \ Design Review |  | 2023-11-13: 11/13-12/1
| ENV52 | MMIS Dev | 2024-01-01: 12/4-1/5; 2024-02-12: P1
| ENV57 | MMIS SIT | 2024-01-01: 1/1-1/26; 2024-02-12: P1
| ENV53 | Regression | 2024-01-29: 1/29-2/9; 2024-02-19: P1(2/21-2/23)
| ENV04 | UAT | 2024-02-12: 2/12-3/8; 2024-02-26: P1(2/26-3/8)
| ENV05 | Prod | 2024-03-11: 2024-03-10
| SysDoc |  | 2024-02-26: Check out to QA - R12.6 & R12.7; 2024-03-11: Check in Doc \ NTT Data Review; 2024-03-25: Review \ Feedback \ Meetings \ Formatting Changes

## 20220908
Release | ENV | Phase | 2019-07-01 |  |  |  |  | 2019-08-01 |  |  |  | 2022-05-01 |  |  |  |  | 2022-06-01 |  |  |  | 2022-07-01 |  |  |  | 2022-08-01 |  |  |  |  | 2022-09-01 |  |  |  | 2022-10-01 |  |  |  | 2022-11-01 |  |  |  |  | 2022-12-01 |  |  |  | 2023-01-01 |  |  |  |  | 2023-02-01 |  |  |  | 2023-03-01 |  |  |  | 2023-04-01 |  |  |  | 2023-05-01 |  |  |  |  | 2023-06-01 |  |  |  | 2023-07-01 |  |  |  |  | 2023-08-01 |  |  |  | 2023-09-01 |  |  |  | 2023-10-01 |  |  |  |  | 2023-11-01 |  |  |  | 2023-12-01 |  |  |  | 2024-01-01 |  |  |  |  | 2024-02-01 |  |  |  | 2024-03-01 |  |  |  | 2024-04-01
 | time axis 2019-07-01 to 2024-04-29
8.6 | Scope Freeze \ Req Approval \ Design Review |  | 2019-07-15: 7/15-8/2
| ENV52 | MMIS Dev | bar: 2019-08-05 to 2019-08-26
| ENV57 | MMIS SIT
| ENV53 | Regression
| ENV04 | UAT
| ENV05 | Prod
8.7 | Scope Freeze \ Req Approval \ Design Review |  | 2019-08-19: 8/19-9/6
| ENV52 | MMIS Dev
| ENV57 | MMIS SIT
| ENV53 | Regression
| ENV04 | UAT
| ENV05 | Prod
SysDoc
11.2 | Scope Freeze \ Req Approval \ Design Review |  | 2022-05-02: 5/2-5/20
| ENV52 | MMIS Dev | 2022-06-20: 5/23-6/24; 2022-08-01: P1
| ENV57 | MMIS SIT | 2022-06-20: 6/20-7/15; 2022-08-01: P1
| ENV53 | Regression | 2022-07-18: 7/18-7/29; 2022-08-08: P1(8/10-8/12)
| ENV04 | UAT | 2022-08-01: 8/4-8/26; 2022-08-15: P1(8/15-8/26)
| ENV05 | Prod | 2022-08-29: 2022-08-28
11.3 | Scope Freeze \ Req Approval \ Design Review |  | 2022-06-06: 6/6-6/24
| ENV52 | MMIS Dev | 2022-07-25: 6/27-7/29; 2022-09-05: P1
| ENV57 | MMIS SIT | 2022-07-25: 7/25-8/19; 2022-09-05: P1
| ENV53 | Regression | 2022-08-22: 8/22-9/2; 2022-09-12: P1(9/14-9/16)
| ENV04 | UAT | 2022-09-05: 9/5-9/30; 2022-09-19: P1(9/19-9/30)
| ENV05 | Prod | 2022-10-03: 2022-10-02
| SysDoc |  | 2022-09-19: Check out to QA - R11.2 & R11.3; 2022-10-03: Check in Doc \ NTT Data Review; 2022-10-17: Review \ Feedback \ Meetings \ Formatting Changes
11.4 | Scope Freeze \ Req Approval \ Design Review |  | 2022-07-11: 7/11-7/29
| ENV52 | MMIS Dev | 2022-08-29: 8/1-9/2; 2022-10-10: P1
| ENV57 | MMIS SIT | 2022-08-29: 8/29-9/23; 2022-10-10: P1
| ENV53 | Regression | 2022-09-26: 9/26-10/7; 2022-10-17: P1(10/19-10/21)
| ENV04 | UAT | 2022-10-10: 10/10-11/4; 2022-10-24: P1(10/24-11/4)
| ENV05 | Prod | 2022-11-07: 2022-11-06
11.5 | Scope Freeze \ Req Approval \ Design Review |  | 2022-08-15: 8/15-9/2
| ENV52 | MMIS Dev | 2022-10-03: 9/5-10/7; 2022-11-14: P1
| ENV57 | MMIS SIT | 2022-10-03: 10/3-10/28; 2022-11-14: P1
| ENV53 | Regression | 2022-10-31: 10/31-11/11; 2022-11-21: P1(11/23-11/25)
| ENV04 | UAT | 2022-11-14: 11/14-12/9; 2022-11-28: P1(11/28-12/9)
| ENV05 | Prod | 2022-12-12: 2022-12-11
| SysDoc |  | 2022-11-28: Check out to QA - R11.4 & R11.5; 2022-12-12: Check in Doc \ NTT Data Review; 2022-12-26: Review \ Feedback \ Meetings \ Formatting Changes
11.6/ TSU | Scope Freeze \ Req Approval \ Design Review |  | 2022-09-19: 9/19-10/7
| ENV52 | MMIS Dev | 2022-11-07: 10/10-11/11; 2022-12-19: P1; 2023-01-02: P2; 2023-01-16: P3
| ENV57 | MMIS SIT | 2022-11-07: 11/7-12/2; 2022-12-19: P1; 2023-01-02: P2; 2023-01-16: P3
| ENV53 | Regression | 2022-12-05: 12/5-12/16; 2022-12-26: P1(12/28-12/30); 2023-01-09: P2(1/11-1/13); 2023-01-23: P3(1/25-1/27)
| ENV04 | UAT | 2022-12-19: 12/19-2/10; 2023-01-02: P1(1/2-2/10); 2023-01-16: P2(1/16-2/10); 2023-01-30: P3(1/30-2/10)
| ENV05 | Prod | 2023-02-13: 2023-02-13
11.7 | Scope Freeze \ Req Approval \ Design Review |  | 2022-11-28: 11/28-12/16
| ENV54 | MMIS Dev | 2023-01-16: 12/19-1/20; 2023-02-27: P1
| ENV58 | MMIS SIT | 2023-01-16: 1/16-2/10; 2023-02-27: P1
| ENV53 | Regression | 2023-02-13: 2/13-2/24; 2023-03-06: P1(3/8-3/10)
| ENV04 | UAT | 2023-02-27: 2/27-3/24; 2023-03-13: P1(3/13-3/24)
| ENV05 | Prod | 2023-03-27: 2023-03-26
| SysDoc |  | 2023-03-13: Check out to QA - R11.6 & R11.7; 2023-03-27: Check in Doc \ NTT Data Review; 2023-04-10: Review \ Feedback \ Meetings \ Formatting Changes
11.8 | Scope Freeze \ Req Approval \ Design Review |  | 2023-01-02: 1/2-1/20
| ENV54 | MMIS Dev | 2023-02-20: 1/23-2/24; 2023-04-03: P1
| ENV57 | MMIS SIT | 2023-02-20: 2/20-3/17; 2023-04-03: P1
| ENV53 | Regression | 2023-03-20: 3/20-3/31; 2023-04-10: P1(4/12-4/14)
| ENV04 | UAT | 2023-04-03: 4/3-4/28; 2023-04-17: P1(4/17-4/28)
| ENV05 | Prod | 2023-05-01: 2023-04-30
11.9 | Scope Freeze \ Req Approval \ Design Review |  | 2023-02-06: 2/6-2/24
| ENV52 | MMIS Dev | 2023-03-27: 2/27-3/31; 2023-05-08: P1
| ENV57 | MMIS SIT | 2023-03-27: 3/27-4/21; 2023-05-08: P1
| ENV53 | Regression | 2023-04-24: 4/24-5/5; 2023-05-15: P1(5/17-5/19)
| ENV04 | UAT | 2023-05-08: 5/8-6/2; 2023-05-22: P1(5/22-6/2)
| ENV05 | Prod | 2023-06-05: 2023-06-04
| SysDoc |  | 2023-05-22: Check out to QA - R11.8 & R11.9; 2023-06-05: Check in Doc \ NTT Data Review; 2023-06-19: Review \ Feedback \ Meetings \ Formatting Changes
12 | Scope Freeze \ Req Approval \ Design Review |  | 2023-03-13: 3/13-3/31
| ENV52 | MMIS Dev | 2023-05-01: 4/3-5/5; 2023-06-12: P1
| ENV57 | MMIS SIT | 2023-05-01: 5/1-5/26; 2023-06-12: P1
| ENV53 | Regression | 2023-05-29: 5/29-6/9; 2023-06-19: P1(6/21-6/23)
| ENV04 | UAT | 2023-06-12: 6/12-7/7; 2023-06-26: P1(6/26-7/7)
| ENV05 | Prod | 2023-07-10: 2023-07-09
12.1 | Scope Freeze \ Req Approval \ Design Review |  | 2023-04-17: 4/17-5/5
| ENV52 | MMIS Dev | 2023-06-05: 5/8-6/9; 2023-07-17: P1
| ENV57 | MMIS SIT | 2023-06-05: 6/5-6/30; 2023-07-17: P1
| ENV53 | Regression | 2023-07-03: 7/3-7/14; 2023-07-24: P1(7/26-7/28)
| ENV04 | UAT | 2023-07-17: 7/17-8/11; 2023-07-31: P1(7/31-8/11)
| ENV05 | Prod | 2023-08-14: 2023-08-13
| SysDoc |  | 2023-07-31: Check out to QA - R12.0 & R12.1; 2023-08-14: Check in Doc \ NTT Data Review; 2023-08-28: Review \ Feedback \ Meetings \ Formatting Changes
12.2 | Scope Freeze \ Req Approval \ Design Review |  | 2023-05-22: 5/22-6/9
| ENV52 | MMIS Dev | 2023-07-10: 6/12-7/14; 2023-08-21: P1
| ENV57 | MMIS SIT | 2023-07-10: 7/10-8/4; 2023-08-21: P1
| ENV53 | Regression | 2023-08-07: 8/7-8/19; 2023-08-28: P1(8/30-9/1)
| ENV04 | UAT | 2023-08-21: 8/21-9/15; 2023-09-04: P1(9/4-9/15)
| ENV05 | Prod | 2023-09-18: 2023-09-17
12.3 | Scope Freeze \ Req Approval \ Design Review |  | 2023-06-26: 6/26-7/14
| ENV52 | MMIS Dev | 2023-08-14: 7/17-8/18; 2023-09-25: P1
| ENV57 | MMIS SIT | 2023-08-14: 8/14-9/8; 2023-09-25: P1
| ENV53 | Regression | 2023-09-11: 9/11-9/22; 2023-10-02: P1(10/4-10/6)
| ENV04 | UAT | 2023-09-25: 9/25-10/20; 2023-10-09: P1(10/9-10/20)
| ENV05 | Prod | 2023-10-23: 2023-10-22
| SysDoc |  | 2023-10-09: Check out to QA - R12.2 & R12.3; 2023-10-23: Check in Doc \ NTT Data Review; 2023-11-06: Review \ Feedback \ Meetings \ Formatting Changes
12.4 | Scope Freeze \ Req Approval \ Design Review |  | 2023-07-31: 7/31-8/18
| ENV52 | MMIS Dev | 2023-09-18: 8/21-9/22; 2023-10-30: P1
| ENV57 | MMIS SIT | 2023-09-18: 9/18-10/13; 2023-10-30: P1
| ENV53 | Regression | 2023-10-16: 10/16-10/27; 2023-11-06: P1(11/8-11/10)
| ENV04 | UAT | 2023-10-30: 10/30-11/24; 2023-11-13: P1(11/13-11/24)
| ENV05 | Prod | 2023-11-27: 2023-11-26
12.5 | Scope Freeze \ Req Approval \ Design Review |  | 2023-09-04: 9/4-9/22
| ENV52 | MMIS Dev | 2023-10-23: 9/25-10/27; 2023-12-04: P1
| ENV57 | MMIS SIT | 2023-10-23: 10/23-11/17; 2023-12-04: P1
| ENV53 | Regression | 2023-11-20: 11/20-12/1; 2023-12-11: P1(12/13-12/15)
| ENV04 | UAT | 2023-12-04: 12/4-12/22; 2023-12-11: P1(12/18-12/22)
| ENV05 | Prod | 2023-12-25: 2023-12-24
| SysDoc |  | 2023-12-11: Check out to QA - R12.4 & R12.5; 2023-12-25: Check in Doc \ NTT Data Review; 2024-01-08: Review \ Feedback \ Meetings \ Formatting Changes
12.6 | Scope Freeze \ Req Approval \ Design Review |  | 2023-10-09: 10/9-10/27
| ENV52 | MMIS Dev | 2023-11-27: 10/30-12/1; 2024-01-08: P1
| ENV57 | MMIS SIT | 2023-11-27: 11/27-12/22; 2024-01-08: P1
| ENV53 | Regression | 2023-12-25: 12/25-1/5; 2024-01-15: P1(1/17-1/19)
| ENV04 | UAT | 2024-01-08: 1/8-2/2; 2024-01-22: P1(1/22-2/2)
| ENV05 | Prod | 2024-02-05: 2024-02-04
12.7 | Scope Freeze \ Req Approval \ Design Review |  | 2023-11-13: 11/13-12/1
| ENV52 | MMIS Dev | 2024-01-01: 12/4-1/5; 2024-02-12: P1
| ENV57 | MMIS SIT | 2024-01-01: 1/1-1/26; 2024-02-12: P1
| ENV53 | Regression | 2024-01-29: 1/29-2/9; 2024-02-19: P1(2/21-2/23)
| ENV04 | UAT | 2024-02-12: 2/12-3/8; 2024-02-26: P1(2/26-3/8)
| ENV05 | Prod | 2024-03-11: 2024-03-10
| SysDoc |  | 2024-02-26: Check out to QA - R12.6 & R12.7; 2024-03-11: Check in Doc \ NTT Data Review; 2024-03-25: Review \ Feedback \ Meetings \ Formatting Changes

## 20220509
Release | ENV | Phase | 2019-07-01 |  |  |  |  | 2019-08-01 |  |  |  | 2021-10-01 |  |  |  | 2021-11-01 |  |  |  |  | 2021-12-01 |  |  |  | 2022-01-01 |  |  |  |  | 2022-02-01 |  |  |  | 2022-03-01 |  |  |  | 2022-04-01 |  |  |  | 2022-05-01 |  |  |  |  | 2022-06-01 |  |  |  | 2022-07-01 |  |  |  | 2022-08-01 |  |  |  |  | 2022-09-01 |  |  |  | 2022-10-01 |  |  |  | 2022-11-01 |  |  |  |  | 2022-12-01 |  |  |  | 2023-01-01 |  |  |  |  | 2023-02-01 |  |  |  | 2023-03-01 |  |  |  | 2023-04-01 |  |  |  | 2023-05-01 |  |  |  |  | 2023-06-01 |  |  |  | 2023-07-01 |  |  |  |  | 2023-08-01 |  |  |  | 2023-09-01 |  |  |  | 2023-10-01 |  |  |  |  | 2023-11-01 |  |  |  | 2023-12-01 |  |  |  | 2024-01-01 |  |  |  |  | 2024-02-01 |  |  |  | 2024-03-01
 | time axis 2019-07-01 to 2024-03-25
8.6 | Scope Freeze \ Req Approval \ Design Review |  | 2019-07-15: 7/15-8/2
| ENV52 | MMIS Dev | bar: 2019-08-05 to 2019-08-26
| ENV57 | MMIS SIT
| ENV53 | Regression
| ENV04 | UAT
| ENV05 | Prod
8.7 | Scope Freeze \ Req Approval \ Design Review |  | 2019-08-19: 8/19-9/6
| ENV52 | MMIS Dev
| ENV57 | MMIS SIT
| ENV53 | Regression
| ENV04 | UAT
| ENV05 | Prod
SysDoc
10.6 | Scope Freeze \ Req Approval \ Design Review |  | 2021-10-04: 10/4-10/22
| ENV52 | MMIS Dev | 2021-11-22: 10/25-11/26; 2022-01-03: P1
| ENV57 | MMIS SIT | 2021-11-22: 11/22-12/17; 2022-01-03: P1
| ENV53 | Regression | 2021-12-20: 12/20-12/31; 2022-01-10: P1(1/12-1/14)
| ENV04 | UAT | 2022-01-03: 1/3-1/28; 2022-01-17: 1/17-1/28
| ENV05 | Prod | 2022-01-31: 2022-01-30
10.7 | Scope Freeze \ Req Approval \ Design Review |  | 2021-11-08: 11/8-11/26
| ENV52 | MMIS Dev | 2021-12-27: 11/29-12/31; 2022-02-07: P1
| ENV57 | MMIS SIT | 2021-12-27: 12/27-1/21; 2022-02-07: P1
| ENV53 | Regression | 2022-01-24: 1/24-2/4; 2022-02-14: P1(2/16-2/18)
| ENV04 | UAT | 2022-02-07: 2/7-3/4; 2022-03-07: 3/7(P1); 2022-03-14: 3/13(P2); 2022-03-21: 3/23(P3); 2022-03-28: 4/6(P4) & 4/7(P5); 2022-04-11: 4/7-4/15
| ENV05 | Prod | 2022-04-18: 2022-04-17
| SysDoc |  | 2022-04-04: Check out to QA - R10.6 & R10.7; 2022-04-18: Check in Doc \ NTT Data Review; 2022-05-02: Review \ Feedback \ Meetings \ Formatting Changes
10.8 | Scope Freeze \ Req Approval \ Design Review |  | 2021-12-13: 12/13-12/31
| ENV52 | MMIS Dev | 2022-01-31: 1/3-2/4
| ENV57 | MMIS SIT | 2022-01-31: 1/31-3/4
10.8 & 10.9 | Scope Freeze \ Req Approval \ Design Review |  | 2022-01-17: 1/17-2/4
| ENV52 | MMIS Dev | 2022-03-07: 2/7-3/11; 2022-04-18: P1
| ENV57 | MMIS SIT | 2022-03-07: 3/7-4/8; 2022-04-18: P1
| ENV53 | Regression | 2022-04-11: 4/11-4/22; 2022-04-25: P1(4/27-4/29)
| ENV04 | UAT | 2022-04-25: 4/25-5/13; 2022-05-02: P1(5/2-5/13)
| ENV05 | Prod | 2022-05-16: 2022-05-15
| SysDoc |  | 2022-05-16: Check out to QA - R10.8 & R10.9; 2022-05-30: Check in Doc \ NTTData Review; 2022-06-13: Review \ Feedback \ Meetings \ Formatting Changes
11 | Scope Freeze \ Req Approval \ Design Review |  | 2022-02-21: 2/21-3/11
| ENV52 | MMIS Dev | 2022-04-11: 3/14-4/15; 2022-05-23: P1
| ENV57 | MMIS SIT | 2022-04-11: 4/11-5/6; 2022-05-23: P1
| ENV53 | Regression | 2022-05-09: 5/9-5/20; 2022-05-30: P1(6/1-6/3)
| ENV04 | UAT | 2022-05-23: 5/23-6/17; 2022-06-06: P1(6/6-6/17)
| ENV05 | Prod | 2022-06-20: 2022-06-19
11.1 | Scope Freeze \ Req Approval \ Design Review |  | 2022-03-28: 3/28-4/15
| ENV52 | MMIS Dev | 2022-05-16: 4/18-5/20; 2022-06-27: P1
| ENV57 | MMIS SIT | 2022-05-16: 5/16-6/10; 2022-06-27: P1
| ENV53 | Regression | 2022-06-13: 6/13-6/24; 2022-07-04: P1(7/6-7/8)
| ENV04 | UAT | 2022-06-27: 6/27-7/22; 2022-07-11: P1(7/11-7/22)
| ENV05 | Prod | 2022-07-25: 2022-07-24
| SysDoc |  | 2022-07-11: Check out to QA - R11.0 & R11.1; 2022-07-25: Check in Doc \ NTT Data Review; 2022-08-08: Review \ Feedback \ Meetings \ Formatting Changes
11.2 | Scope Freeze \ Req Approval \ Design Review |  | 2022-05-02: 5/2-5/20
| ENV52 | MMIS Dev | 2022-06-20: 5/23-6/24; 2022-08-01: P1
| ENV57 | MMIS SIT | 2022-06-20: 6/20-7/15; 2022-08-01: P1
| ENV53 | Regression | 2022-07-18: 7/18-7/29; 2022-08-08: P1(8/10-8/12)
| ENV04 | UAT | 2022-08-01: 8/1-8/26; 2022-08-15: P1(8/15-8/26)
| ENV05 | Prod | 2022-08-29: 2022-08-28
11.3 | Scope Freeze \ Req Approval \ Design Review |  | 2022-06-06: 6/6-6/24
| ENV52 | MMIS Dev | 2022-07-25: 6/27-7/29; 2022-09-05: P1
| ENV57 | MMIS SIT | 2022-07-25: 7/25-8/19; 2022-09-05: P1
| ENV53 | Regression | 2022-08-22: 8/22-9/2; 2022-09-12: P1(9/14-9/16)
| ENV04 | UAT | 2022-09-05: 9/5-9/30; 2022-09-19: P1(9/19-9/30)
| ENV05 | Prod | 2022-10-03: 2022-10-02
| SysDoc |  | 2022-09-19: Check out to QA - R11.2 & R11.3; 2022-10-03: Check in Doc \ NTT Data Review; 2022-10-17: Review \ Feedback \ Meetings \ Formatting Changes
11.4 | Scope Freeze \ Req Approval \ Design Review |  | 2022-07-11: 7/11-7/29
| ENV52 | MMIS Dev | 2022-08-29: 8/1-9/2; 2022-10-10: P1
| ENV57 | MMIS SIT | 2022-08-29: 8/29-9/23; 2022-10-10: P1
| ENV53 | Regression | 2022-09-26: 9/26-10/7; 2022-10-17: P1(10/19-10/21)
| ENV04 | UAT | 2022-10-10: 10/10-11/4; 2022-10-24: P1(10/24-11/4)
| ENV05 | Prod | 2022-11-07: 2022-11-06
11.5 | Scope Freeze \ Req Approval \ Design Review |  | 2022-08-15: 8/15-9/2
| ENV52 | MMIS Dev | 2022-10-03: 9/5-10/7; 2022-11-14: P1
| ENV57 | MMIS SIT | 2022-10-03: 10/3-10/28; 2022-11-14: P1
| ENV53 | Regression | 2022-10-31: 10/31-11/11; 2022-11-21: P1(11/23-11/25)
| ENV04 | UAT | 2022-11-14: 11/14-12/9; 2022-11-28: P1(11/28-12/9)
| ENV05 | Prod | 2022-12-12: 2022-12-11
| SysDoc |  | 2022-11-28: Check out to QA - R11.4 & R11.5; 2022-12-12: Check in Doc \ NTT Data Review; 2022-12-26: Review \ Feedback \ Meetings \ Formatting Changes
11.6 | Scope Freeze \ Req Approval \ Design Review |  | 2022-09-19: 9/19-10/7
| ENV52 | MMIS Dev | 2022-11-07: 10/10-11/11; 2022-12-19: P1
| ENV57 | MMIS SIT | 2022-11-07: 11/7-12/2; 2022-12-19: P1
| ENV53 | Regression | 2022-12-05: 12/5-12/16; 2022-12-26: P1(12/28-12/30)
| ENV04 | UAT | 2022-12-19: 12/19-1/13; 2023-01-02: P1(1/2-1/13)
| ENV05 | Prod | 2023-01-16: 2023-01-15
11.7 | Scope Freeze \ Req Approval \ Design Review |  | 2022-10-24: 10/24-11/11
| ENV52 | MMIS Dev | 2022-12-12: 11/14-12/16; 2023-01-23: P1
| ENV57 | MMIS SIT | 2022-12-12: 12/12-1/6; 2023-01-23: P1
| ENV53 | Regression | 2023-01-09: 1/9-1/20; 2023-01-30: P1(2/1-2/3)
| ENV04 | UAT | 2023-01-23: 1/23-2/17; 2023-02-06: P1(2/6-2/17)
| ENV05 | Prod | 2023-02-20: 2023-02-19
| SysDoc |  | 2023-02-06: Check out to QA - R11.6 & R11.7; 2023-02-20: Check in Doc \ NTT Data Review; 2023-03-06: Review \ Feedback \ Meetings \ Formatting Changes
11.8 | Scope Freeze \ Req Approval \ Design Review |  | 2022-11-28: 11/28-12/16
| ENV52 | MMIS Dev | 2023-01-16: 12/19-1/20; 2023-02-27: P1
| ENV57 | MMIS SIT | 2023-01-16: 1/16-2/10; 2023-02-27: P1
| ENV53 | Regression | 2023-02-13: 2/13-2/24; 2023-03-06: P1(3/8-3/10)
| ENV04 | UAT | 2023-02-27: 2/27-3/24; 2023-03-13: P1(3/13-3/24)
| ENV05 | Prod | 2023-03-27: 2023-03-26
11.9 | Scope Freeze \ Req Approval \ Design Review |  | 2023-01-02: 1/2-1/20
| ENV52 | MMIS Dev | 2023-02-20: 1/23-2/24; 2023-04-03: P1
| ENV57 | MMIS SIT | 2023-02-20: 2/20-3/17; 2023-04-03: P1
| ENV53 | Regression | 2023-03-20: 3/20-3/31; 2023-04-10: P1(4/12-4/14)
| ENV04 | UAT | 2023-04-03: 4/3-4/28; 2023-04-17: P1(4/17-4/28)
| ENV05 | Prod | 2023-05-01: 2023-04-30
| SysDoc |  | 2023-04-17: Check out to QA - R11.8 & R11.9; 2023-05-01: Check in Doc \ NTT Data Review; 2023-05-15: Review \ Feedback \ Meetings \ Formatting Changes
12 | Scope Freeze \ Req Approval \ Design Review |  | 2023-02-06: 2/6-2/24
| ENV52 | MMIS Dev | 2023-03-27: 2/27-3/31; 2023-05-08: P1
| ENV57 | MMIS SIT | 2023-03-27: 3/27-4/21; 2023-05-08: P1
| ENV53 | Regression | 2023-04-24: 4/24-5/5; 2023-05-15: P1(5/17-5/19)
| ENV04 | UAT | 2023-05-08: 5/8-6/2; 2023-05-22: P1(5/22-6/2)
| ENV05 | Prod | 2023-06-05: 2023-06-04
12.1 | Scope Freeze \ Req Approval \ Design Review |  | 2023-03-13: 3/13-3/31
| ENV52 | MMIS Dev | 2023-05-01: 4/3-5/5; 2023-06-12: P1
| ENV57 | MMIS SIT | 2023-05-01: 5/1-5/26; 2023-06-12: P1
| ENV53 | Regression | 2023-05-29: 5/29-6/9; 2023-06-19: P1(6/21-6/23)
| ENV04 | UAT | 2023-06-12: 6/12-7/7; 2023-06-26: P1(6/26-7/7)
| ENV05 | Prod | 2023-07-10: 2023-07-09
| SysDoc |  | 2023-06-26: Check out to QA - R12.0 & R12.1; 2023-07-10: Check in Doc \ NTT Data Review; 2023-07-24: Review \ Feedback \ Meetings \ Formatting Changes
12.2 | Scope Freeze \ Req Approval \ Design Review |  | 2023-04-17: 4/17-5/5
| ENV52 | MMIS Dev | 2023-06-05: 5/8-6/9; 2023-07-17: P1
| ENV57 | MMIS SIT | 2023-06-05: 6/5-6/30; 2023-07-17: P1
| ENV53 | Regression | 2023-07-03: 7/3-7/14; 2023-07-24: P1(7/26-7/28)
| ENV04 | UAT | 2023-07-17: 7/17-8/11; 2023-07-31: P1(7/31-8/11)
| ENV05 | Prod | 2023-08-14: 2023-08-13
12.3 | Scope Freeze \ Req Approval \ Design Review |  | 2023-05-22: 5/22-6/9
| ENV52 | MMIS Dev | 2023-07-10: 6/12-7/14; 2023-08-21: P1
| ENV57 | MMIS SIT | 2023-07-10: 7/10-8/4; 2023-08-21: P1
| ENV53 | Regression | 2023-08-07: 8/7-8/19; 2023-08-28: P1(8/30-9/1)
| ENV04 | UAT | 2023-08-21: 8/21-9/15; 2023-09-04: P1(9/4-9/15)
| ENV05 | Prod | 2023-09-18: 2023-09-17
| SysDoc |  | 2023-09-04: Check out to QA - R12.2 & R12.3; 2023-09-18: Check in Doc \ NTT Data Review; 2023-10-02: Review \ Feedback \ Meetings \ Formatting Changes
12.4 | Scope Freeze \ Req Approval \ Design Review |  | 2023-06-26: 6/26-7/14
| ENV52 | MMIS Dev | 2023-08-14: 7/17-8/18; 2023-09-25: P1
| ENV57 | MMIS SIT | 2023-08-14: 8/14-9/8; 2023-09-25: P1
| ENV53 | Regression | 2023-09-11: 9/11-9/22; 2023-10-02: P1(10/4-10/6)
| ENV04 | UAT | 2023-09-25: 9/25-10/20; 2023-10-09: P1(10/9-10/20)
| ENV05 | Prod | 2023-10-23: 2023-10-22
12.5 | Scope Freeze \ Req Approval \ Design Review |  | 2023-07-31: 7/31-8/18
| ENV52 | MMIS Dev | 2023-09-18: 8/21-9/22; 2023-10-30: P1
| ENV57 | MMIS SIT | 2023-09-18: 9/18-10/13; 2023-10-30: P1
| ENV53 | Regression | 2023-10-16: 10/16-10/27; 2023-11-06: P1(11/8-11/10)
| ENV04 | UAT | 2023-10-30: 10/30-11/24; 2023-11-13: P1(11/13-11/24)
| ENV05 | Prod | 2023-11-27: 2023-11-26
| SysDoc |  | 2023-11-13: Check out to QA - R12.4 & R12.5; 2023-11-27: Check in Doc \ NTT Data Review; 2023-12-11: Review \ Feedback \ Meetings \ Formatting Changes
12.6 | Scope Freeze \ Req Approval \ Design Review |  | 2023-09-04: 9/4-9/22
| ENV52 | MMIS Dev | 2023-10-23: 9/25-10/27; 2023-12-04: P1
| ENV57 | MMIS SIT | 2023-10-23: 10/23-11/17; 2023-12-04: P1
| ENV53 | Regression | 2023-11-20: 11/20-12/1; 2023-12-11: P1(12/13-12/15)
| ENV04 | UAT | 2023-12-04: 12/4-12/22; 2023-12-11: P1(12/18-12/22)
| ENV05 | Prod | 2023-12-25: 2023-12-24
12.7 | Scope Freeze \ Req Approval \ Design Review |  | 2023-10-09: 10/9-10/27
| ENV52 | MMIS Dev | 2023-11-27: 10/30-12/1; 2024-01-08: P1
| ENV57 | MMIS SIT | 2023-11-27: 11/27-12/22; 2024-01-08: P1
| ENV53 | Regression | 2023-12-25: 12/25-1/5; 2024-01-15: P1(1/17-1/19)
| ENV04 | UAT | 2024-01-08: 1/8-2/2; 2024-01-22: P1(1/22-2/2)
| ENV05 | Prod | 2024-02-05: 2024-02-04
| SysDoc |  | 2024-01-22: Check out to QA - R12.6 & R12.7; 2024-02-05: Check in Doc \ NTT Data Review; 2024-02-19: Review \ Feedback \ Meetings \ Formatting Changes
Note on AD21: Author: Data Refresh Activity is tentatively to happen after R10.6 between 01/31/2022 - 02/07/2022

## 20220310
Release | ENV | Phase | 2019-07-01 |  |  |  |  | 2019-08-01 |  |  |  | 2020-10-01 |  |  |  | 2020-11-01 |  |  |  |  | 2020-12-01 |  |  |  | 2021-01-01 |  |  |  | 2021-02-01 |  |  |  | 2021-03-01 |  |  |  |  | 2021-04-01 |  |  |  | 2021-05-01 |  |  |  |  | 2021-06-01 |  |  |  | 2021-07-01 |  |  |  | 2021-08-01 |  |  |  |  | 2021-09-01 |  |  |  | 2021-10-01 |  |  |  | 2021-11-01 |  |  |  |  | 2021-12-01 |  |  |  | 2022-01-01 |  |  |  |  | 2022-02-01 |  |  |  | 2022-03-01 |  |  |  | 2022-04-01 |  |  |  | 2022-05-01 |  |  |  |  | 2022-06-01 |  |  |  | 2022-07-01 |  |  |  | 2022-08-01 |  |  |  |  | 2022-09-01 |  |  |  | 2022-10-01 |  |  |  | 2022-11-01 |  |  |  |  | 2022-12-01 |  |  |  | 2023-01-01
|  |  | 2019-07-01 | 2019-07-08 | 2019-07-15 | 2019-07-22 | 2019-07-29 | 2019-08-05 | 2019-08-12 | 2019-08-19 | 2019-08-26 | 2020-10-05 | 2020-10-12 | 2020-10-19 | 2020-10-26 | 2020-11-02 | 2020-11-09 | 2020-11-16 | 2020-11-23 | 2020-11-30 | 2020-12-07 | 2020-12-14 | 2020-12-21 | 2020-12-28 | 2021-01-04 | 2021-01-11 | 2021-01-18 | 2021-01-25 | 2021-02-01 | 2021-02-08 | 2021-02-15 | 2021-02-22 | 2021-03-01 | 2021-03-08 | 2021-03-15 | 2021-03-22 | 2021-03-29 | 2021-04-05 | 2021-04-12 | 2021-04-19 | 2021-04-26 | 2021-05-03 | 2021-05-10 | 2021-05-17 | 2021-05-24 | 2021-05-31 | 2020-06-07 | 2020-06-14 | 2020-06-21 | 2020-06-28 | 2020-07-05 | 2021-07-12 | 2021-07-19 | 2021-07-26 | 2021-08-02 | 2021-08-09 | 2021-08-16 | 2021-08-23 | 2021-08-30 | 2021-09-06 | 2021-09-13 | 2021-09-20 | 2021-09-27 | 2021-10-04 | 2021-10-11 | 2021-10-18 | 2021-10-25 | 2021-11-01 | 2021-11-08 | 2021-11-15 | 2021-11-22 | 2021-11-29 | 2021-12-06 | 2021-12-13 | 2021-12-20 | 2021-12-27 | 2022-01-03 | 2022-01-10 | 2022-01-17 | 2022-01-24 | 2022-01-31 | 2022-02-07 | 2022-02-14 | 2022-02-21 | 2022-02-28 | 2022-03-07 | 2022-03-14 | 2022-03-21 | 2022-03-28 | 2022-04-04 | 2022-04-11 | 2022-04-18 | 2022-04-25 | 2022-05-02 | 2022-05-09 | 2022-05-16 | 2022-05-23 | 2022-05-30 | 2022-06-06 | 2022-06-13 | 2022-06-20 | 2022-06-27 | 2022-07-04 | 2022-07-11 | 2022-07-18 | 2022-07-25 | 2022-08-01 | 2022-08-08 | 2022-08-15 | 2022-08-22 | 2022-08-29 | 2022-09-05 | 2022-09-12 | 2022-09-19 | 2022-09-26 | 2022-10-03 | 2022-10-10 | 2022-10-17 | 2022-10-24 | 2022-10-31 | 2022-11-07 | 2022-11-14 | 2022-11-21 | 2022-11-28 | 2022-12-05 | 2022-12-12 | 2022-12-19 | 2022-12-26 | 2023-01-02 | 2023-01-09 | 2023-01-16 | 2023-01-23 | 2023-01-30
8.6 | Scope Freeze \ Req Approval \ Design Review |  |  |  | 7/15-8/2
| ENV52 | MMIS Dev
| ENV57 | MMIS SIT
| ENV53 | Regression
| ENV04 | UAT
| ENV05 | Prod
8.7 | Scope Freeze \ Req Approval \ Design Review | [8 empty] | 8/19-9/6
| ENV52 | MMIS Dev
| ENV57 | MMIS SIT
| ENV53 | Regression
| ENV04 | UAT
| ENV05 | Prod
SysDoc
9.6 | Scope Freeze \ Req Approval \ Design Review | [12 empty] | 10/19-11/6
| ENV52 | MMIS Dev | [18 empty] | 11/9-12/11 | [5 empty] | P1
| ENV57 | MMIS SIT | [18 empty] | 12/7-1/1 | [5 empty] | P1
| ENV53 | Regression | [22 empty] | 1/4-1/15 |  |  | P1(1/27-1/29)
| ENV04 | UAT | [24 empty] | 1/18-2/12 |  | 2/1-2/12
| ENV05 | Prod | [28 empty] | 2021-02-14
9.7 | Scope Freeze \ Req Approval \ Design Review | [17 empty] | 11/23-12/11
| ENV52 | MMIS Dev | [23 empty] | 12/14-1/15 | [5 empty] | P1
| ENV57 | MMIS SIT | [23 empty] | 1/11-2/5 | [5 empty] | P1
| ENV53 | Regression | [27 empty] | 2/8-2/19 |  |  | P1(3/3-3/5)
| ENV04 | UAT | [29 empty] | 2/22-3/19 |  | 3/8-3/19
| ENV05 | Prod | [33 empty] | 2021-03-21
| SysDoc | [32 empty] | Check out to QA - R9.6 & R9.7 |  | Check in Doc \ NTT Data Review |  | Review \ Feedback \ Meetings \ Formatting Changes
9.8 | Scope Freeze \ Req Approval \ Design Review | [22 empty] | 12/28-1/15
| ENV52 | MMIS Dev | [28 empty] | 1/18-2/19 | [5 empty] | P1
| ENV57 | MMIS SIT | [28 empty] | 2/15-3/12 | [5 empty] | P1
| ENV53 | Regression | [32 empty] | 3/15-3/26 |  |  | P1(4/7-4/9)
| ENV04 | UAT | [34 empty] | 3/29-4/23 |  | 4/12-4/23
| ENV05 | Prod | [38 empty] | 2021-04-25
9.9 | Scope Freeze \ Req Approval \ Design Review | [27 empty] | 2/1-2/19
| ENV52 | MMIS Dev | [33 empty] | 2/22-3/26 | [5 empty] | P1
| ENV57 | MMIS SIT | [33 empty] | 3/22-4/16 | [5 empty] | P1
| ENV53 | Regression | [37 empty] | 4/19-4/30 |  |  | P1(5/12-5/14)
| ENV04 | UAT | [39 empty] | 5/3-5/28 |  | 5/17-5/28
| ENV05 | Prod | [43 empty] | 2021-05-30
| SysDoc | [42 empty] | Check out to QA - R9.8 & R9.9 |  | Check in Doc \ NTT Data Review |  | Review \ Feedback \ Meetings \ Formatting Changes
10 | Scope Freeze \ Req Approval \ Design Review | [32 empty] | 3/8-3/26
| ENV52 | MMIS Dev | [38 empty] | 3/29-4/30 | [5 empty] | P1
| ENV57 | MMIS SIT | [38 empty] | 4/26-5/21 | [5 empty] | P1
| ENV53 | Regression | [42 empty] | 5/24-6/4 |  |  | P1(6/16-6/18)
| ENV04 | UAT | [44 empty] | 6/7-7/2 |  | 6/21-7/2
| ENV05 | Prod | [48 empty] | 2021-07-04
10.1 | Scope Freeze \ Req Approval \ Design Review | [37 empty] | 4/12-4/30
| ENV52 | MMIS Dev | [43 empty] | 5/3-6/4 | [5 empty] | P1
| ENV57 | MMIS SIT | [43 empty] | 5/31-6/25 | [5 empty] | P1
| ENV53 | Regression | [47 empty] | 6/28-7/9 |  |  | P1(7/21-7/23)
| ENV04 | UAT | [49 empty] | 7/12-8/6 |  | 7/26-8/6
| ENV05 | Prod | [53 empty] | 2021-08-08
| SysDoc | [52 empty] | Check out to QA - R10.0 & R10.1 |  | Check in Doc \ NTT Data Review |  | Review \ Feedback \ Meetings \ Formatting Changes
10.2 | Scope Freeze \ Req Approval \ Design Review | [42 empty] | 5/17-6/4
| ENV52 | MMIS Dev | [48 empty] | 6/7-7/9 | [5 empty] | P1
| ENV57 | MMIS SIT | [48 empty] | 7/5-7/30 | [5 empty] | P1
| ENV53 | Regression | [52 empty] | 8/2-8/13 |  |  | P1(8/25-8/27)
| ENV04 | UAT | [54 empty] | 8/16-9/10 |  | 8/30-9/10
| ENV05 | Prod | [58 empty] | 2021-09-12
10.3 | Scope Freeze \ Req Approval \ Design Review | [47 empty] | 6/21-7/9
| ENV52 | MMIS Dev | [53 empty] | 7/12-8/13 | [5 empty] | P1
| ENV57 | MMIS SIT | [53 empty] | 8/9-9/3 | [5 empty] | P1
| ENV53 | Regression | [57 empty] | 9/6-9/17 |  |  | P1(9/29-10/1)
| ENV04 | UAT | [59 empty] | 9/20-10/15 |  | 10/4-10/15
| ENV05 | Prod | [63 empty] | 2021-10-17
| SysDoc | [62 empty] | Check out to QA - R10.2 & R10.3 |  | Check in Doc \ NTT Data Review |  | Review \ Feedback \ Meetings \ Formatting Changes
10.4 | Scope Freeze \ Req Approval \ Design Review | [52 empty] | 7/26-8/13
| ENV52 | MMIS Dev | [58 empty] | 8/16-9/17 | [5 empty] | P1
| ENV57 | MMIS SIT | [58 empty] | 9/13-10/8 | [5 empty] | P1
| ENV53 | Regression | [62 empty] | 10/11-10/22 |  |  | P1(11/3-11/5)
| ENV04 | UAT | [64 empty] | 10/25-11/19 |  | 11/8-11/19
| ENV05 | Prod | [68 empty] | 2021-11-21
10.5 | Scope Freeze \ Req Approval \ Design Review | [57 empty] | 8/30-9/17
| ENV52 | MMIS Dev | [63 empty] | 9/20-10/22 | [5 empty] | P1
| ENV57 | MMIS SIT | [63 empty] | 10/18-11/12 | [5 empty] | P1
| ENV53 | Regression | [67 empty] | 11/15-11/26 |  |  | P1(12/8-12/10)
| ENV04 | UAT | [69 empty] | 11/29-12/24 |  | 12/13-12/17
| ENV05 | Prod | [72 empty] | 2021-12-19
| SysDoc | [71 empty] | Check out to QA - R10.4 & R10.5 |  | Check in Doc \ NTT Data Review |  | Review \ Feedback \ Meetings \ Formatting Changes
10.6 | Scope Freeze \ Req Approval \ Design Review | [62 empty] | 10/4-10/22
| ENV52 | MMIS Dev | [68 empty] | 10/25-11/26 | [5 empty] | P1
| ENV57 | MMIS SIT | [68 empty] | 11/22-12/17 | [5 empty] | P1
| ENV53 | Regression | [72 empty] | 12/20-12/31 |  |  | P1(1/12-1/14)
| ENV04 | UAT | [74 empty] | 1/3-1/28 |  | 1/17-1/28
| ENV05 | Prod | [78 empty] | 2022-01-30
10.7 | Scope Freeze \ Req Approval \ Design Review | [67 empty] | 11/8-11/26
| ENV52 | MMIS Dev | [73 empty] | 11/29-12/31 | [5 empty] | P1
| ENV57 | MMIS SIT | [73 empty] | 12/27-1/21 | [5 empty] | P1
| ENV53 | Regression | [77 empty] | 1/24-2/4 |  |  | P1(2/16-2/18)
| ENV04 | UAT | [79 empty] | 2/7-3/4 |  |  |  | 3/7(P1) | 3/13(P2) | 3/23(P3) | 3/24-4/8
| ENV05 | Prod | [88 empty] | 2022-04-10
| SysDoc | [87 empty] | Check out to QA - R10.6 & R10.7 |  | Check in Doc \ NTT Data Review |  | Review \ Feedback \ Meetings \ Formatting Changes
10.8 | Scope Freeze \ Req Approval \ Design Review | [72 empty] | 12/13-12/31
| ENV52 | MMIS Dev | [78 empty] | 1/3-2/4
| ENV57 | MMIS SIT | [78 empty] | 1/31-3/11
10.8 & 10.9 | Scope Freeze \ Req Approval \ Design Review | [77 empty] | 1/17-2/4
| ENV52 | MMIS Dev | [83 empty] | 2/7-3/11 | [5 empty] | P1
| ENV57 | MMIS SIT | [83 empty] | 3/7-4/1 | [5 empty] | P1
| ENV53 | Regression | [86 empty] | 3/28-4/15 |  |  |  | P1(4/27-4/29)
| ENV04 | UAT | [89 empty] | 4/18-5/13 |  | 5/2-5/13
| ENV05 | Prod | [93 empty] | 2022-05-15
| SysDoc | [94 empty] | Check out to QA - R10.8 & R10.9 |  | Check in Doc \ NTTData Review |  | Review \ Feedback \ Meetings \ Formatting Changes
11 | Scope Freeze \ Req Approval \ Design Review | [82 empty] | 2/21-3/11
| ENV52 | MMIS Dev | [88 empty] | 3/14-4/15 | [5 empty] | P1
| ENV57 | MMIS SIT | [88 empty] | 4/11-5/6 | [5 empty] | P1
| ENV53 | Regression | [92 empty] | 5/9-5/20 |  |  | P1(6/1-6/3)
| ENV04 | UAT | [94 empty] | 5/23-6/17 |  | 6/6-6/17
| ENV05 | Prod | [98 empty] | 2022-06-19
11.1 | Scope Freeze \ Req Approval \ Design Review | [87 empty] | 3/28-4/15
| ENV52 | MMIS Dev | [93 empty] | 4/18-5/20 | [5 empty] | P1
| ENV57 | MMIS SIT | [93 empty] | 5/16-6/10 | [5 empty] | P1
| ENV53 | Regression | [97 empty] | 6/13-6/24 |  |  | P1(7/6-7/8)
| ENV04 | UAT | [99 empty] | 6/27-7/22 |  | 7/11-7/22
| ENV05 | Prod | [103 empty] | 2022-07-24
| SysDoc | [102 empty] | Check out to QA - R11.0 & R11.1 |  | Check in Doc \ NTT Data Review |  | Review \ Feedback \ Meetings \ Formatting Changes
11.2 | Scope Freeze \ Req Approval \ Design Review | [92 empty] | 5/2-5/20
| ENV52 | MMIS Dev | [98 empty] | 5/23-6/24 | [5 empty] | P1
| ENV57 | MMIS SIT | [98 empty] | 6/20-7/15 | [5 empty] | P1
| ENV53 | Regression | [102 empty] | 7/18-7/29 |  |  | P1(8/10-8/12)
| ENV04 | UAT | [104 empty] | 8/1-8/26 |  | 8/15-8/26
| ENV05 | Prod | [108 empty] | 2022-08-28
11.3 | Scope Freeze \ Req Approval \ Design Review | [97 empty] | 6/6-6/24
| ENV52 | MMIS Dev | [103 empty] | 6/27-7/29 | [5 empty] | P1
| ENV57 | MMIS SIT | [103 empty] | 7/25-8/19 | [5 empty] | P1
| ENV53 | Regression | [107 empty] | 8/22-9/2 |  |  | P1(9/14-9/16)
| ENV04 | UAT | [109 empty] | 9/5-9/30 |  | 9/19-9/30
| ENV05 | Prod | [113 empty] | 2022-10-02
| SysDoc | [112 empty] | Check out to QA - R11.2 & R11.3 |  | Check in Doc \ NTT Data Review |  | Review \ Feedback \ Meetings \ Formatting Changes
11.4 | Scope Freeze \ Req Approval \ Design Review | [102 empty] | 7/11-7/29
| ENV52 | MMIS Dev | [108 empty] | 8/1-9/2 | [5 empty] | P1
| ENV57 | MMIS SIT | [108 empty] | 8/29-9/23 | [5 empty] | P1
| ENV53 | Regression | [112 empty] | 9/26-10/7 |  |  | P1(10/19-10/21)
| ENV04 | UAT | [114 empty] | 10/10-11/4 |  | 10/24-11/4
| ENV05 | Prod | [118 empty] | 2022-11-06
11.5 | Scope Freeze \ Req Approval \ Design Review | [107 empty] | 8/15-9/2
| ENV52 | MMIS Dev | [113 empty] | 9/5-10/7 | [5 empty] | P1
| ENV57 | MMIS SIT | [113 empty] | 10/3-10/28 | [5 empty] | P1
| ENV53 | Regression | [117 empty] | 10/31-11/11 |  |  | P1(11/23-11/25)
| ENV04 | UAT | [119 empty] | 11/14-12/9 |  | 11/28-12/9
| ENV05 | Prod | [123 empty] | 2022-12-11
| SysDoc | [122 empty] | Check out to QA - R11.4 & R11.5 |  | Check in Doc \ NTT Data Review |  | Review \ Feedback \ Meetings \ Formatting Changes
Note on CD86: Author: Data Refresh Activity is tentatively to happen after R10.6 between 01/31/2022 - 02/07/2022

## 20210219
Release | ENV | Phase | 2019-07-01 |  |  |  |  | 2019-08-01 |  |  |  | 2020-10-01 |  |  |  | 2020-11-01 |  |  |  |  | 2020-12-01 |  |  |  | 2021-01-01 |  |  |  | 2021-02-01 |  |  |  | 2021-03-01 |  |  |  |  | 2021-04-01 |  |  |  | 2021-05-01 |  |  |  |  | 2021-06-01 |  |  |  | 2021-07-01 |  |  |  | 2021-08-01 |  |  |  |  | 2021-09-01 |  |  |  | 2021-10-01 |  |  |  | 2021-11-01 |  |  |  |  | 2021-12-01 |  |  |  | 2022-01-01 |  |  |  |  | 2022-02-01 |  |  |  | 2022-03-01 |  |  |  | 2022-04-01 |  |  |  | 2022-05-01 |  |  |  |  | 2022-06-01 |  |  |  | 2022-07-01 |  |  |  | 2022-08-01 |  |  |  |  | 2022-09-01 |  |  |  | 2022-10-01 |  |  |  | 2022-11-01 |  |  |  |  | 2022-12-01 |  |  |  | 2023-01-01
|  |  | 2019-07-01 | 2019-07-08 | 2019-07-15 | 2019-07-22 | 2019-07-29 | 2019-08-05 | 2019-08-12 | 2019-08-19 | 2019-08-26 | 2020-10-05 | 2020-10-12 | 2020-10-19 | 2020-10-26 | 2020-11-02 | 2020-11-09 | 2020-11-16 | 2020-11-23 | 2020-11-30 | 2020-12-07 | 2020-12-14 | 2020-12-21 | 2020-12-28 | 2021-01-04 | 2021-01-11 | 2021-01-18 | 2021-01-25 | 2021-02-01 | 2021-02-08 | 2021-02-15 | 2021-02-22 | 2021-03-01 | 2021-03-08 | 2021-03-15 | 2021-03-22 | 2021-03-29 | 2021-04-05 | 2021-04-12 | 2021-04-19 | 2021-04-26 | 2021-05-03 | 2021-05-10 | 2021-05-17 | 2021-05-24 | 2021-05-31 | 2020-06-07 | 2020-06-14 | 2020-06-21 | 2020-06-28 | 2020-07-05 | 2021-07-12 | 2021-07-19 | 2021-07-26 | 2021-08-02 | 2021-08-09 | 2021-08-16 | 2021-08-23 | 2021-08-30 | 2021-09-06 | 2021-09-13 | 2021-09-20 | 2021-09-27 | 2021-10-04 | 2021-10-11 | 2021-10-18 | 2021-10-25 | 2021-11-01 | 2021-11-08 | 2021-11-15 | 2021-11-22 | 2021-11-29 | 2021-12-06 | 2021-12-13 | 2021-12-20 | 2021-12-27 | 2022-01-03 | 2022-01-10 | 2022-01-17 | 2022-01-24 | 2022-01-31 | 2022-02-07 | 2022-02-14 | 2022-02-21 | 2022-02-28 | 2022-03-07 | 2022-03-14 | 2022-03-21 | 2022-03-28 | 2022-04-04 | 2022-04-11 | 2022-04-18 | 2022-04-25 | 2022-05-02 | 2022-05-09 | 2022-05-16 | 2022-05-23 | 2022-05-30 | 2022-06-06 | 2022-06-13 | 2022-06-20 | 2022-06-27 | 2022-07-04 | 2022-07-11 | 2022-07-18 | 2022-07-25 | 2022-08-01 | 2022-08-08 | 2022-08-15 | 2022-08-22 | 2022-08-29 | 2022-09-05 | 2022-09-12 | 2022-09-19 | 2022-09-26 | 2022-10-03 | 2022-10-10 | 2022-10-17 | 2022-10-24 | 2022-10-31 | 2022-11-07 | 2022-11-14 | 2022-11-21 | 2022-11-28 | 2022-12-05 | 2022-12-12 | 2022-12-19 | 2022-12-26 | 2023-01-02 | 2023-01-09 | 2023-01-16 | 2023-01-23 | 2023-01-30
8.6 | Scope Freeze \ Req Approval \ Design Review |  |  |  | 7/15-8/2
| ENV52 | MMIS Dev
| ENV57 | MMIS SIT
| ENV53 | Regression
| ENV04 | UAT
| ENV05 | Prod
8.7 | Scope Freeze \ Req Approval \ Design Review | [8 empty] | 8/19-9/6
| ENV52 | MMIS Dev
| ENV57 | MMIS SIT
| ENV53 | Regression
| ENV04 | UAT
| ENV05 | Prod
SysDoc
9.6 | Scope Freeze \ Req Approval \ Design Review | [12 empty] | 10/19-11/6
| ENV52 | MMIS Dev | [18 empty] | 11/9-12/11 | [5 empty] | P1
| ENV57 | MMIS SIT | [18 empty] | 12/7-1/1 | [5 empty] | P1
| ENV53 | Regression | [22 empty] | 1/4-1/15 |  |  | P1(1/27-1/29)
| ENV04 | UAT | [24 empty] | 1/18-2/12 |  | 2/1-2/12
| ENV05 | Prod | [28 empty] | 2021-02-14
9.7 | Scope Freeze \ Req Approval \ Design Review | [17 empty] | 11/23-12/11
| ENV52 | MMIS Dev | [23 empty] | 12/14-1/15 | [5 empty] | P1
| ENV57 | MMIS SIT | [23 empty] | 1/11-2/5 | [5 empty] | P1
| ENV53 | Regression | [27 empty] | 2/8-2/19 |  |  | P1(3/3-3/5)
| ENV04 | UAT | [29 empty] | 2/22-3/19 |  | 3/8-3/19
| ENV05 | Prod | [33 empty] | 2021-03-21
| SysDoc | [32 empty] | Check out to QA - R9.6 & R9.7 |  | Check in Doc \ Cognosante Review |  | Review \ Feedback \ Meetings \ Formatting Changes
9.8 | Scope Freeze \ Req Approval \ Design Review | [22 empty] | 12/28-1/15
| ENV52 | MMIS Dev | [28 empty] | 1/18-2/19 | [5 empty] | P1
| ENV57 | MMIS SIT | [28 empty] | 2/15-3/12 | [5 empty] | P1
| ENV53 | Regression | [32 empty] | 3/15-3/26 |  |  | P1(4/7-4/9)
| ENV04 | UAT | [34 empty] | 3/29-4/23 |  | 4/12-4/23
| ENV05 | Prod | [38 empty] | 2021-04-25
9.9 | Scope Freeze \ Req Approval \ Design Review | [27 empty] | 2/1-2/19
| ENV52 | MMIS Dev | [33 empty] | 2/22-3/26 | [5 empty] | P1
| ENV57 | MMIS SIT | [33 empty] | 3/22-4/16 | [5 empty] | P1
| ENV53 | Regression | [37 empty] | 4/19-4/30 |  |  | P1(5/12-5/14)
| ENV04 | UAT | [39 empty] | 5/3-5/28 |  | 5/17-5/28
| ENV05 | Prod | [43 empty] | 2021-05-30
| SysDoc | [42 empty] | Check out to QA - R9.8 & R9.9 |  | Check in Doc \ Cognosante Review |  | Review \ Feedback \ Meetings \ Formatting Changes
10 | Scope Freeze \ Req Approval \ Design Review | [32 empty] | 3/8-3/26
| ENV52 | MMIS Dev | [38 empty] | 3/29-4/30 | [5 empty] | P1
| ENV57 | MMIS SIT | [38 empty] | 4/26-5/21 | [5 empty] | P1
| ENV53 | Regression | [42 empty] | 5/24-6/4 |  |  | P1(6/16-6/18)
| ENV04 | UAT | [44 empty] | 6/7-7/2 |  | 6/21-7/2
| ENV05 | Prod | [48 empty] | 2021-07-04
10.1 | Scope Freeze \ Req Approval \ Design Review | [37 empty] | 4/12-4/30
| ENV52 | MMIS Dev | [43 empty] | 5/3-6/4 | [5 empty] | P1
| ENV57 | MMIS SIT | [43 empty] | 5/31-6/25 | [5 empty] | P1
| ENV53 | Regression | [47 empty] | 6/28-7/9 |  |  | P1(7/21-7/23)
| ENV04 | UAT | [49 empty] | 7/12-8/6 |  | 7/26-8/6
| ENV05 | Prod | [53 empty] | 2021-08-08
| SysDoc | [52 empty] | Check out to QA - R10.0 & R10.1 |  | Check in Doc \ Cognosante Review |  | Review \ Feedback \ Meetings \ Formatting Changes
10.2 | Scope Freeze \ Req Approval \ Design Review | [42 empty] | 5/17-6/4
| ENV52 | MMIS Dev | [48 empty] | 6/7-7/9 | [5 empty] | P1
| ENV57 | MMIS SIT | [48 empty] | 7/5-7/30 | [5 empty] | P1
| ENV53 | Regression | [52 empty] | 8/2-8/13 |  |  | P1(8/25-8/27)
| ENV04 | UAT | [54 empty] | 8/16-9/10 |  | 8/30-9/10
| ENV05 | Prod | [58 empty] | 2021-09-12
10.3 | Scope Freeze \ Req Approval \ Design Review | [47 empty] | 6/21-7/9
| ENV52 | MMIS Dev | [53 empty] | 7/12-8/13 | [5 empty] | P1
| ENV57 | MMIS SIT | [53 empty] | 8/9-9/3 | [5 empty] | P1
| ENV53 | Regression | [57 empty] | 9/6-9/17 |  |  | P1(9/29-10/1)
| ENV04 | UAT | [59 empty] | 9/20-10/15 |  | 10/4-10/15
| ENV05 | Prod | [63 empty] | 2021-10-17
| SysDoc | [62 empty] | Check out to QA - R10.2 & R10.3 |  | Check in Doc \ Cognosante Review |  | Review \ Feedback \ Meetings \ Formatting Changes
10.4 | Scope Freeze \ Req Approval \ Design Review | [52 empty] | 7/26-8/13
| ENV52 | MMIS Dev | [58 empty] | 8/16-9/17 | [5 empty] | P1
| ENV57 | MMIS SIT | [58 empty] | 9/13-10/8 | [5 empty] | P1
| ENV53 | Regression | [62 empty] | 10/11-10/22 |  |  | P1(11/3-11/5)
| ENV04 | UAT | [64 empty] | 10/25-11/19 |  | 11/8-11/19
| ENV05 | Prod | [68 empty] | 2021-11-21
10.5 | Scope Freeze \ Req Approval \ Design Review | [57 empty] | 8/30-9/17
| ENV52 | MMIS Dev | [63 empty] | 9/20-10/22 | [5 empty] | P1
| ENV57 | MMIS SIT | [63 empty] | 10/18-11/12 | [5 empty] | P1
| ENV53 | Regression | [67 empty] | 11/15-11/26 |  |  | P1(12/8-12/10)
| ENV04 | UAT | [69 empty] | 11/29-12/24 |  | 12/13-12/17
| ENV05 | Prod | [72 empty] | 2021-12-19
| SysDoc | [71 empty] | Check out to QA - R10.4 & R10.5 |  | Check in Doc \ Cognosante Review |  | Review \ Feedback \ Meetings \ Formatting Changes
10.6 | Scope Freeze \ Req Approval \ Design Review | [62 empty] | 10/4-10/22
| ENV52 | MMIS Dev | [68 empty] | 10/25-11/26 | [5 empty] | P1
| ENV57 | MMIS SIT | [68 empty] | 11/22-12/17 | [5 empty] | P1
| ENV53 | Regression | [72 empty] | 12/20-12/31 |  |  | P1(1/12-1/14)
| ENV04 | UAT | [74 empty] | 1/3-1/28 |  | 1/17-1/28
| ENV05 | Prod | [78 empty] | 2022-01-30
10.7 | Scope Freeze \ Req Approval \ Design Review | [67 empty] | 11/8-11/26
| ENV52 | MMIS Dev | [73 empty] | 11/29-12/31 | [5 empty] | P1
| ENV57 | MMIS SIT | [73 empty] | 12/27-1/21 | [5 empty] | P1
| ENV53 | Regression | [77 empty] | 1/24-2/4 |  |  | P1(2/16-2/18)
| ENV04 | UAT | [79 empty] | 2/7-3/4 |  | 2/21-3/4
| ENV05 | Prod | [83 empty] | 2022-03-06
| SysDoc | [82 empty] | Check out to QA - R10.6 & R10.7 |  | Check in Doc \ Cognosante Review |  | Review \ Feedback \ Meetings \ Formatting Changes
10.8 | Scope Freeze \ Req Approval \ Design Review | [72 empty] | 12/13-12/31
| ENV52 | MMIS Dev | [78 empty] | 1/3-2/4 | [5 empty] | P1
| ENV57 | MMIS SIT | [78 empty] | 1/31-2/25 | [5 empty] | P1
| ENV53 | Regression | [82 empty] | 2/28-3/11 |  |  | P1(3/23-3/25)
| ENV04 | UAT | [84 empty] | 3/14-4/8 |  | 3/28-4/8
| ENV05 | Prod | [88 empty] | 2022-04-10
10.9 | Scope Freeze \ Req Approval \ Design Review | [77 empty] | 1/17-2/4
| ENV52 | MMIS Dev | [83 empty] | 2/7-3/11 | [5 empty] | P1
| ENV57 | MMIS SIT | [83 empty] | 3/7-4/1 | [5 empty] | P1
| ENV53 | Regression | [87 empty] | 4/4-4/15 |  |  | P1(4/27-4/29)
| ENV04 | UAT | [89 empty] | 4/18-5/13 |  | 5/2-5/13
| ENV05 | Prod | [93 empty] | 2022-05-15
| SysDoc | [92 empty] | Check out to QA - R10.8 & R10.9 |  | Check in Doc \ Cognosante Review |  | Review \ Feedback \ Meetings \ Formatting Changes
11 | Scope Freeze \ Req Approval \ Design Review | [82 empty] | 2/21-3/11
| ENV52 | MMIS Dev | [88 empty] | 3/14-4/15 | [5 empty] | P1
| ENV57 | MMIS SIT | [88 empty] | 4/11-5/6 | [5 empty] | P1
| ENV53 | Regression | [92 empty] | 5/9-5/20 |  |  | P1(6/1-6/3)
| ENV04 | UAT | [94 empty] | 5/23-6/17 |  | 6/6-6/17
| ENV05 | Prod | [98 empty] | 2022-06-19
11.1 | Scope Freeze \ Req Approval \ Design Review | [87 empty] | 3/28-4/15
| ENV52 | MMIS Dev | [93 empty] | 4/18-5/20 | [5 empty] | P1
| ENV57 | MMIS SIT | [93 empty] | 5/16-6/10 | [5 empty] | P1
| ENV53 | Regression | [97 empty] | 6/13-6/24 |  |  | P1(7/6-7/8)
| ENV04 | UAT | [99 empty] | 6/27-7/22 |  | 7/11-7/22
| ENV05 | Prod | [103 empty] | 2022-07-24
| SysDoc | [102 empty] | Check out to QA - R11.0 & R11.1 |  | Check in Doc \ Cognosante Review |  | Review \ Feedback \ Meetings \ Formatting Changes
11.2 | Scope Freeze \ Req Approval \ Design Review | [92 empty] | 5/2-5/20
| ENV52 | MMIS Dev | [98 empty] | 5/23-6/24 | [5 empty] | P1
| ENV57 | MMIS SIT | [98 empty] | 6/20-7/15 | [5 empty] | P1
| ENV53 | Regression | [102 empty] | 7/18-7/29 |  |  | P1(8/10-8/12)
| ENV04 | UAT | [104 empty] | 8/1-8/26 |  | 8/15-8/26
| ENV05 | Prod | [108 empty] | 2022-08-28
11.3 | Scope Freeze \ Req Approval \ Design Review | [97 empty] | 6/6-6/24
| ENV52 | MMIS Dev | [103 empty] | 6/27-7/29 | [5 empty] | P1
| ENV57 | MMIS SIT | [103 empty] | 7/25-8/19 | [5 empty] | P1
| ENV53 | Regression | [107 empty] | 8/22-9/2 |  |  | P1(9/14-9/16)
| ENV04 | UAT | [109 empty] | 9/5-9/30 |  | 9/19-9/30
| ENV05 | Prod | [113 empty] | 2022-10-02
| SysDoc | [112 empty] | Check out to QA - R11.2 & R11.3 |  | Check in Doc \ Cognosante Review |  | Review \ Feedback \ Meetings \ Formatting Changes
11.4 | Scope Freeze \ Req Approval \ Design Review | [102 empty] | 7/11-7/29
| ENV52 | MMIS Dev | [108 empty] | 8/1-9/2 | [5 empty] | P1
| ENV57 | MMIS SIT | [108 empty] | 8/29-9/23 | [5 empty] | P1
| ENV53 | Regression | [112 empty] | 9/26-10/7 |  |  | P1(10/19-10/21)
| ENV04 | UAT | [114 empty] | 10/10-11/4 |  | 10/24-11/4
| ENV05 | Prod | [118 empty] | 2022-11-06
11.5 | Scope Freeze \ Req Approval \ Design Review | [107 empty] | 8/15-9/2
| ENV52 | MMIS Dev | [113 empty] | 9/5-10/7 | [5 empty] | P1
| ENV57 | MMIS SIT | [113 empty] | 10/3-10/28 | [5 empty] | P1
| ENV53 | Regression | [117 empty] | 10/31-11/11 |  |  | P1(11/23-11/25)
| ENV04 | UAT | [119 empty] | 11/14-12/9 |  | 11/28-12/9
| ENV05 | Prod | [123 empty] | 2022-12-11
| SysDoc | [122 empty] | Check out to QA - R11.4 & R11.5 |  | Check in Doc \ Cognosante Review |  | Review \ Feedback \ Meetings \ Formatting Changes
Note on CD86: Author: Data Refresh Activity is tentatively to happen after R10.6 between 01/31/2022 - 02/07/2022

## 20200803
Release | ENV | Phase | 2019-07-01 |  |  |  |  | 2019-08-01 |  |  |  | 2019-09-01 |  |  |  |  | 2019-10-01 |  |  |  | 2019-11-01 |  |  |  | 2019-12-01 |  |  |  |  | 2020-01-01 |  |  |  | 2020-02-01 |  |  |  | 2020-03-01 |  |  |  |  | 2020-04-01 |  |  |  | 2020-05-01 |  |  |  | 2020-06-01 |  |  |  |  | 2020-07-01 |  |  |  | 2020-08-01 |  |  |  |  | 2020-09-01 |  |  |  | 2020-10-01 |  |  |  | 2020-11-01 |  |  |  |  | 2020-12-01 |  |  |  | 2021-01-01 |  |  |  | 2021-02-01 |  |  |  | 2021-03-01 |  |  |  |  | 2021-04-01 |  |  |  | 2021-05-01 |  |  |  |  | 2021-06-01 |  |  |  | 2021-07-01
|  |  | 2019-07-01 | 2019-07-08 | 2019-07-15 | 2019-07-22 | 2019-07-29 | 2019-08-05 | 2019-08-12 | 2019-08-19 | 2019-08-26 | 2019-09-02 | 2019-09-09 | 2019-09-16 | 2019-09-23 | 2019-09-30 | 2019-10-07 | 2019-10-14 | 2019-10-21 | 2019-10-28 | 2019-11-04 | 2019-11-11 | 2019-11-18 | 2019-11-25 | 2019-12-02 | 2019-12-09 | 2019-12-16 | 2019-12-23 | 2019-12-30 | 2020-01-06 | 2020-01-13 | 2020-01-20 | 2020-01-27 | 2020-02-03 | 2020-02-10 | 2020-02-17 | 2020-02-24 | 2020-03-02 | 2020-03-09 | 2020-03-16 | 2020-03-23 | 2020-03-30 | 2020-04-06 | 2020-04-13 | 2020-04-20 | 2020-04-27 | 2020-05-04 | 2020-05-11 | 2020-05-18 | 2020-05-25 | 2020-06-01 | 2020-06-08 | 2020-06-15 | 2020-06-22 | 2020-06-29 | 2020-07-06 | 2020-07-13 | 2020-07-20 | 2020-07-27 | 2020-08-03 | 2020-08-10 | 2020-08-17 | 2020-08-24 | 2020-08-31 | 2020-09-07 | 2020-09-14 | 2020-09-21 | 2020-09-28 | 2020-10-05 | 2020-10-12 | 2020-10-19 | 2020-10-26 | 2020-11-02 | 2020-11-09 | 2020-11-16 | 2020-11-23 | 2020-11-30 | 2020-12-07 | 2020-12-14 | 2020-12-21 | 2020-12-28 | 2021-01-04 | 2021-01-11 | 2021-01-18 | 2021-01-25 | 2021-02-01 | 2021-02-08 | 2021-02-15 | 2021-02-22 | 2021-03-01 | 2021-03-08 | 2021-03-15 | 2021-03-22 | 2021-03-29 | 2021-04-05 | 2021-04-12 | 2021-04-19 | 2021-04-26 | 2021-05-03 | 2021-05-10 | 2021-05-17 | 2021-05-24 | 2021-05-31 | 2020-06-07 | 2020-06-14 | 2020-06-21 | 2020-06-28 | 2020-07-05 | 2021-07-12 | 2021-07-19 | 2021-07-26
8.6 | Scope Freeze \ Req Approval \ Design Review |  |  |  | 7/15-8/2
| ENV52 | MMIS Dev | [9 empty] | 8/5-9/6 | [5 empty] | P1
| ENV57 | MMIS SIT | [9 empty] | 9/2-9/27 | [5 empty] | P1
| ENV53 | Regression | [13 empty] | 9/30-10/11 |  |  | P1 (10/23-10/25)
| ENV04 | UAT | [15 empty] | 10/14-11/8 |  | P1(10/28-11/8)
| ENV05 | Prod | [19 empty] | 2019-11-10
8.7 | Scope Freeze \ Req Approval \ Design Review | [8 empty] | 8/19-9/6
| ENV52 | MMIS Dev | [14 empty] | 9/9-10/11 | [6 empty] | P1
| ENV57 | MMIS SIT | [14 empty] | 10/7-11/1 | [6 empty] | P1
| ENV53 | Regression | [18 empty] | 11/4-11/15 |  |  |  | P1 (12/4-12/6)
| ENV04 | UAT | [20 empty] | 11/22-12/27 |  |  | P1(12/9-12/27)
| ENV05 | Prod | [26 empty] | 2019-12-29
| SysDoc | [23 empty] | Check out to QA - R8.6 & R8.7 |  | Check in Doc \ Cognosante Review |  | Review \ Feedback \ Meetings \ Formatting Changes
8.8 | Scope Freeze \ Req Approval \ Design Review | [13 empty] | 9/23-10/11
| ENV52 | MMIS Dev | [20 empty] | 10/14-11/22 | [12 empty] | P1
| ENV57 | MMIS SIT | [20 empty] | 11/18-12/20 | [12 empty] | P1
| ENV53 | Regression | [25 empty] | 12/23-1/3 | [8 empty] | P1 (2/26-2/29)
| ENV04 | UAT | [31 empty] | 2/6-2/21 |  |  |  | P1(3/2-3/13)
| ENV05 | Prod | [37 empty] | 2020-03-15
8.9 | Scope Freeze \ Req Approval \ Design Review | [19 empty] | 11/4-11/22
| ENV52 | MMIS Dev | [26 empty] | 11/25-1/3
| ENV57 | MMIS SIT | [26 empty] | 12/30-1/24
| ENV53 | Regression
| ENV04 | UAT
| ENV05 | Prod
SysDoc
8.9 & 9.0 | Scope Freeze \ Req Approval \ Design Review | [25 empty] | 12/16-1/3
| ENV52 | MMIS Dev | [32 empty] | 1/6-2/14 | [9 empty] | P1
| ENV57 | MMIS SIT | [32 empty] | 2/10-3/13 | [9 empty] | P1
| ENV53 | Regression | [36 empty] | 3/9-4/3 | [6 empty] | P1 (4/29-5/1)
| ENV04 | UAT | [40 empty] | 4/6-5/8 |  |  |  |  | P1(5/11-6/19)
| ENV05 | Prod | [58 empty] | 2020-08-09
9.1 | Scope Freeze \ Req Approval \ Design Review | [32 empty] | 2/3-2/21
| ENV52 | MMIS Dev | [42 empty] | 2/17-4/24 | [9 empty] | P1
| ENV57 | MMIS SIT | [39 empty] | 3/30-5/15 | [12 empty] | P1
| ENV53 | Regression | [46 empty] | 5/18-6/19 | [6 empty] | P1 (7/8-7/10)
| ENV04 | UAT | [51 empty] | 6/22-7/10 |  |  | P1(7/13-8/21)
| ENV05 | Prod | [60 empty] | 2020-08-23
| SysDoc | [58 empty] | Check out to QA - R8.8, R8.9, R9.0 & R9.1 |  |  | Check in Doc \ Cognosante Review |  | Review \ Feedback \ Meetings \ Formatting Changes
9.2 | Scope Freeze \ Req Approval \ Design Review | [43 empty] | 4/20-5/8
| ENV52 | MMIS Dev | [50 empty] | 4/27-6/19 | [10 empty] | P1
| ENV57 | MMIS SIT | [50 empty] | 6/15-7/10 | [10 empty] | P1
| ENV53 | Regression | [54 empty] | 7/13-7/24 | [7 empty] | P1 (9/9-9/11)
| ENV04 | UAT | [61 empty] | 8/31-9/11 |  | P1(9/14-9/25)
| ENV05 | Prod | [65 empty] | 2020-09-27
9.3 | Scope Freeze \ Req Approval \ Design Review | [49 empty] | 6/1-6/19
| ENV52 | MMIS Dev | [59 empty] | 6/22-8/21 | [6 empty] | P1
| ENV57 | MMIS SIT | [56 empty] | 7/27-9/18 | [9 empty] | P1
| ENV53 | Regression | [64 empty] | 9/21-10/2 |  |  | P1 (10/14-10/16)
| ENV04 | UAT | [66 empty] | 10/5-10/16 |  | P1(10/19-10/30)
| ENV05 | Prod | [70 empty] | 2020-11-01
| SysDoc | [69 empty] | Check out to QA - R9.2 & R9.3 |  | Check in Doc \ Cognosante Review |  | Review \ Feedback \ Meetings \ Formatting Changes
9.4 | Scope Freeze \ Req Approval \ Design Review | [58 empty] | 08/3-8/21
| ENV52 | MMIS Dev | [65 empty] | 8/24-10/2 | [5 empty] | P1
| ENV57 | MMIS SIT | [65 empty] | 9/28-10/23 | [5 empty] | P1
| ENV53 | Regression | [69 empty] | 10/26-11/6 |  |  | P1(11/18-11/20)
| ENV04 | UAT | [71 empty] | 11/9-11/20 |  | P1(11/23-12/4)
| ENV05 | Prod | [75 empty] | 2020-12-06
9.5 | Scope Freeze \ Req Approval \ Design Review | [64 empty] | 9/14-10/2
| ENV52 | MMIS Dev | [70 empty] | 10/5-11/6 | [5 empty] | P1
| ENV57 | MMIS SIT | [70 empty] | 11/2-11/27 | [5 empty] | P1
| ENV53 | Regression | [74 empty] | 11/30-12/11 |  |  | P1(12/23-12/25)
| ENV04 | UAT | [76 empty] | 12/14-12/25 |  | P1(12/28-1/8)
| ENV05 | Prod | [80 empty] | 2021-01-10
| SysDoc | [79 empty] | Check out to QA - R9.4 & R9.5 |  | Check in Doc \ Cognosante Review |  | Review \ Feedback \ Meetings \ Formatting Changes
9.6 | Scope Freeze \ Req Approval \ Design Review | [69 empty] | 10/19-11/6
| ENV52 | MMIS Dev | [75 empty] | 11/9-12/11 | [5 empty] | P1
| ENV57 | MMIS SIT | [75 empty] | 12/7-1/1 | [5 empty] | P1
| ENV53 | Regression | [79 empty] | 1/4-1/15 |  |  | P1(1/27-1/29)
| ENV04 | UAT | [81 empty] | 1/18-1/29 |  | 2/1-2/12
| ENV05 | Prod | [85 empty] | 2021-02-14
9.7 | Scope Freeze \ Req Approval \ Design Review | [74 empty] | 11/23-12/11
| ENV52 | MMIS Dev | [80 empty] | 12/14-1/15 | [5 empty] | P1
| ENV57 | MMIS SIT | [80 empty] | 1/11-2/5 | [5 empty] | P1
| ENV53 | Regression | [84 empty] | 2/8-2/19 |  |  | P1(3/3-3/5)
| ENV04 | UAT | [86 empty] | 2/22-3/5 |  | 3/8-3/19
| ENV05 | Prod | [90 empty] | 2021-03-21
| SysDoc | [89 empty] | Check out to QA - R9.6 & R9.7 |  | Check in Doc \ Cognosante Review |  | Review \ Feedback \ Meetings \ Formatting Changes
9.8 | Scope Freeze \ Req Approval \ Design Review | [79 empty] | 12/28-1/15
| ENV52 | MMIS Dev | [85 empty] | 1/18-2/19 | [5 empty] | P1
| ENV57 | MMIS SIT | [85 empty] | 2/15-3/12 | [5 empty] | P1
| ENV53 | Regression | [89 empty] | 3/15-3/26 |  |  | P1(4/7-4/9)
| ENV04 | UAT | [91 empty] | 3/29-4/9 |  | 4/12-4/23
| ENV05 | Prod | [95 empty] | 2021-04-25
9.9 | Scope Freeze \ Req Approval \ Design Review | [84 empty] | 2/1-2/19
| ENV52 | MMIS Dev | [90 empty] | 2/22-3/26 | [5 empty] | P1
| ENV57 | MMIS SIT | [90 empty] | 3/22-4/16 | [5 empty] | P1
| ENV53 | Regression | [94 empty] | 4/19-4/30 |  |  | P1(5/12-5/14)
| ENV04 | UAT | [96 empty] | 5/3-5/14 |  | 5/17-5/28
| ENV05 | Prod | [100 empty] | 2021-05-30
| SysDoc | [99 empty] | Check out to QA - R9.8 & R9.9 |  | Check in Doc \ Cognosante Review |  | Review \ Feedback \ Meetings \ Formatting Changes
10 | Scope Freeze \ Req Approval \ Design Review | [89 empty] | 3/8-3/26
| ENV52 | MMIS Dev | [95 empty] | 3/29-4/30 | [5 empty] | P1
| ENV57 | MMIS SIT | [95 empty] | 4/26-5/21 | [5 empty] | P1
| ENV53 | Regression | [99 empty] | 5/24-6/4 |  |  | P1(6/16-6/18)
| ENV04 | UAT | [101 empty] | 6/7-6/18 |  | 6/21-7/2
| ENV05 | Prod | [105 empty] | 2021-07-04

## 20200611
Release | ENV | Phase | 2019-07-01 |  |  |  |  | 2019-08-01 |  |  |  | 2019-09-01 |  |  |  |  | 2019-10-01 |  |  |  | 2019-11-01 |  |  |  | 2019-12-01 |  |  |  |  | 2020-01-01 |  |  |  | 2020-02-01 |  |  |  | 2020-03-01 |  |  |  |  | 2020-04-01 |  |  |  | 2020-05-01 |  |  |  | 2020-06-01 |  |  |  |  | 2020-07-01 |  |  |  | 2020-08-01 |  |  |  |  | 2020-09-01 |  |  |  | 2020-10-01 |  |  |  | 2020-11-01 |  |  |  |  | 2020-12-01 |  |  |  | 2021-01-01 |  |  |  | 2021-02-01 |  |  |  | 2021-03-01 |  |  |  |  | 2021-04-01 |  |  |  | 2021-05-01
 | time axis 2019-07-01 to 2021-05-31
8.6 | Scope Freeze \ Req Approval \ Design Review |  | 2019-07-15: 7/15-8/2
| ENV52 | MMIS Dev | 2019-09-02: 8/5-9/6; 2019-10-14: P1
| ENV57 | MMIS SIT | 2019-09-02: 9/2-9/27; 2019-10-14: P1
| ENV53 | Regression | 2019-09-30: 9/30-10/11; 2019-10-21: P1 (10/23-10/25)
| ENV04 | UAT | 2019-10-14: 10/14-11/8; 2019-10-28: P1(10/28-11/8)
| ENV05 | Prod | 2019-11-11: 2019-11-10
8.7 | Scope Freeze \ Req Approval \ Design Review |  | 2019-08-19: 8/19-9/6
| ENV52 | MMIS Dev | 2019-10-07: 9/9-10/11; 2019-11-25: P1
| ENV57 | MMIS SIT | 2019-10-07: 10/7-11/1; 2019-11-25: P1
| ENV53 | Regression | 2019-11-04: 11/4-11/15; 2019-12-02: P1 (12/4-12/6)
| ENV04 | UAT | 2019-11-18: 11/22-12/27; 2019-12-09: P1(12/9-12/27)
| ENV05 | Prod | 2019-12-30: 2019-12-29
| SysDoc |  | 2019-12-02: Check out to QA - R8.6 & R8.7; 2019-12-16: Check in Doc \ Cognosante Review; 2019-12-30: Review \ Feedback \ Meetings \ Formatting Changes
8.8 | Scope Freeze \ Req Approval \ Design Review |  | 2019-09-23: 9/23-10/11
| ENV52 | MMIS Dev | 2019-11-18: 10/14-11/22; 2020-02-17: P1
| ENV57 | MMIS SIT | 2019-11-18: 11/18-12/20; 2020-02-17: P1
| ENV53 | Regression | 2019-12-23: 12/23-1/3; 2020-02-24: P1 (2/26-2/29)
| ENV04 | UAT | 2020-02-03: 2/6-2/21; 2020-03-02: P1(3/2-3/13)
| ENV05 | Prod | 2020-03-16: 2020-03-15
8.9 | Scope Freeze \ Req Approval \ Design Review |  | 2019-11-04: 11/4-11/22
| ENV52 | MMIS Dev | 2019-12-30: 11/25-1/3
| ENV57 | MMIS SIT | 2019-12-30: 12/30-1/24
| ENV53 | Regression
| ENV04 | UAT
| ENV05 | Prod
SysDoc
8.9 & 9.0 | Scope Freeze \ Req Approval \ Design Review |  | 2019-12-16: 12/16-1/3
| ENV52 | MMIS Dev | 2020-02-10: 1/6-2/14; 2020-04-20: P1
| ENV57 | MMIS SIT | 2020-02-10: 2/10-3/13; 2020-04-20: P1
| ENV53 | Regression | 2020-03-09: 3/9-4/3; 2020-04-27: P1 (4/29-5/1)
| ENV04 | UAT | 2020-04-06: 4/6-5/8; 2020-05-11: P1(5/11-6/19)
| ENV05 | Prod | 2020-07-06: 2020-07-06
9.1 | Scope Freeze \ Req Approval \ Design Review |  | 2020-02-03: 2/3-2/21
| ENV52 | MMIS Dev | 2020-04-20: 2/17-4/24; 2020-06-22: P1
| ENV57 | MMIS SIT | 2020-03-30: 3/30-5/29; 2020-06-22: P1
| ENV53 | Regression | 2020-05-18: 5/18-6/19; 2020-06-29: P1 (7/1-7/3)
| ENV04 | UAT | 2020-06-22: 6/22-7/3; 2020-07-06: P1(7/6-7/17)
| ENV05 | Prod | 2020-07-20: 2020-07-19
| SysDoc |  | 2020-07-06: Check out to QA - R8.8, R8.9, R9.0 & R9.1; 2020-07-20: Check in Doc \ Cognosante Review; 2020-08-03: Review \ Feedback \ Meetings \ Formatting Changes
9.2 | Scope Freeze \ Req Approval \ Design Review |  | 2020-04-20: 4/20-5/8
| ENV52 | MMIS Dev | 2020-06-15: 4/27-6/19; 2020-07-27: P1
| ENV57 | MMIS SIT | 2020-06-15: 6/15-7/10; 2020-07-27: P1
| ENV53 | Regression | 2020-07-13: 7/13-7/24; 2020-08-03: P1 (8/5-8/7)
| ENV04 | UAT | 2020-07-27: 7/27-8/7; 2020-08-10: P1(8/10-8/21)
| ENV05 | Prod | 2020-08-24: 2020-08-23
9.3 | Scope Freeze \ Req Approval \ Design Review |  | 2020-06-01: 6/1-6/19
| ENV52 | MMIS Dev | 2020-07-20: 6/22-7/24; 2020-08-31: P1
| ENV57 | MMIS SIT | 2020-07-20: 7/20-8/14; 2020-08-31: P1
| ENV53 | Regression | 2020-08-17: 8/17-8/28; 2020-09-07: P1 (9/9-9/11)
| ENV04 | UAT | 2020-08-31: 8/31-9/11; 2020-09-14: P1(9/14-9/25)
| ENV05 | Prod | 2020-09-28: 2020-09-27
| SysDoc |  | 2020-09-14: Check out to QA - R9.2 & R9.3; 2020-09-28: Check in Doc \ Cognosante Review; 2020-10-12: Review \ Feedback \ Meetings \ Formatting Changes
9.4 | Scope Freeze \ Req Approval \ Design Review |  | 2020-07-06: 7/6-7/24
| ENV52 | MMIS Dev | 2020-08-24: 7/27-8/28; 2020-10-05: P1
| ENV57 | MMIS SIT | 2020-08-24: 8/24-9/19; 2020-10-05: P1
| ENV53 | Regression | 2020-09-21: 9/21-10/2; 2020-10-12: P1(10/14-10/16)
| ENV04 | UAT | 2020-10-05: 10/5-10/16; 2020-10-19: P1(10/19-10/30)
| ENV05 | Prod | 2020-11-02: 2020-11-01
9.5 | Scope Freeze \ Req Approval \ Design Review |  | 2020-08-10: 8/10-8/28
| ENV52 | MMIS Dev | 2020-09-28: 8/31-10/2; 2020-11-09: P1
| ENV57 | MMIS SIT | 2020-09-28: 9/28-10/23; 2020-11-09: P1
| ENV53 | Regression | 2020-10-26: 10/26-11/6; 2020-11-16: P1(11/18-11/20)
| ENV04 | UAT | 2020-11-09: 11/9-11/20; 2020-11-23: P1(11/23-12/4)
| ENV05 | Prod | 2020-12-07: 2020-12-06
| SysDoc |  | 2020-11-23: Check out to QA - R9.4 & R9.5; 2020-12-07: Check in Doc \ Cognosante Review; 2020-12-21: Review \ Feedback \ Meetings \ Formatting Changes
9.6 | Scope Freeze \ Req Approval \ Design Review |  | 2020-09-14: 9/14-10/2
| ENV52 | MMIS Dev | 2020-11-02: 10/5-11/6; 2020-12-14: P1
| ENV57 | MMIS SIT | 2020-11-02: 11/2-11/27; 2020-12-14: P1
| ENV53 | Regression | 2020-11-30: 11/30-12/11; 2020-12-21: P1(12/23-12/25)
| ENV04 | UAT | 2020-12-14: 12/14-12/25; 2020-12-28: P1(12/28-1/8)
| ENV05 | Prod | 2021-01-11: 2021-01-10
9.7 | Scope Freeze \ Req Approval \ Design Review |  | 2020-10-19: 10/19-11/6
| ENV52 | MMIS Dev | 2020-12-07: 11/9-12/11; 2021-01-18: P1
| ENV57 | MMIS SIT | 2020-12-07: 12/7-1/1; 2021-01-18: P1
| ENV53 | Regression | 2021-01-04: 1/4-1/15; 2021-01-25: P1(1/27-1/29)
| ENV04 | UAT | 2021-01-18: 1/18-1/29; 2021-02-01: P1(2/1-2/12)
| ENV05 | Prod | 2021-02-15: 2021-02-14
| SysDoc |  | 2021-02-01: Check out to QA - R9.6 & R9.7; 2021-02-15: Check in Doc \ Cognosante Review; 2021-03-01: Review \ Feedback \ Meetings \ Formatting Changes
9.8 | Scope Freeze \ Req Approval \ Design Review |  | 2020-11-23: 11/23-12/11
| ENV52 | MMIS Dev | 2021-01-11: 12/14-1/15; 2021-02-22: P1
| ENV57 | MMIS SIT | 2021-01-11: 1/11-2/5; 2021-02-22: P1
| ENV53 | Regression | 2021-02-08: 2/8-2/19; 2021-03-01: P1(3/3-3/5)
| ENV04 | UAT | 2021-02-22: 2/22-3/5; 2021-03-08: P1(3/8-3/19)
| ENV05 | Prod | 2021-03-22: 2021-03-21
9.9 | Scope Freeze \ Req Approval \ Design Review |  | 2020-12-28: 12/28-1/15
| ENV52 | MMIS Dev | 2021-02-15: 1/18-2/19; 2021-03-29: P1
| ENV57 | MMIS SIT | 2021-02-15: 2/15-3/12; 2021-03-29: P1
| ENV53 | Regression | 2021-03-15: 3/15-3/26; 2021-04-05: P1(4/7-4/9)
| ENV04 | UAT | 2021-03-29: 3/29-4/9; 2021-04-12: P1(4/12-4/23)
| ENV05 | Prod | 2021-04-26: 2021-04-25
| SysDoc |  | 2021-04-12: Check out to QA - R9.8 & R9.9; 2021-04-26: Check in Doc \ Cognosante Review; 2021-05-10: Review \ Feedback \ Meetings \ Formatting Changes
10 | Scope Freeze \ Req Approval \ Design Review |  | 2021-02-01: 2/1-2/19
| ENV52 | MMIS Dev | 2021-03-22: 2/22-3/26; 2021-05-03: P1
| ENV57 | MMIS SIT | 2021-03-22: 3/22-4/16; 2021-05-03: P!
| ENV53 | Regression | 2021-04-19: 4/19-4/30; 2021-05-10: P1(5/12-5/14)
| ENV04 | UAT | 2021-05-03: 5/3-5/14; 2021-05-17: P1(5/17-5/28)
| ENV05 | Prod | 2021-05-31: 2021-05-30

## 20200415
Release | ENV | Phase | 2019-07-01 |  |  |  |  | 2019-08-01 |  |  |  | 2019-09-01 |  |  |  |  | 2019-10-01 |  |  |  | 2019-11-01 |  |  |  | 2019-12-01 |  |  |  |  | 2020-01-01 |  |  |  | 2020-02-01 |  |  |  | 2020-03-01 |  |  |  |  | 2020-04-01 |  |  |  | 2020-05-01 |  |  |  | 2020-06-01 |  |  |  |  | 2020-07-01 |  |  |  | 2020-08-01 |  |  |  |  | 2020-09-01 |  |  |  | 2020-10-01 |  |  |  | 2020-11-01 |  |  |  |  | 2020-12-01 |  |  |  | 2021-01-01 |  |  |  | 2021-02-01 |  |  |  | 2021-03-01 |  |  |  |  | 2021-04-01 |  |  |  | 2021-05-01
 | time axis 2019-07-01 to 2021-05-31
8.6 | Scope Freeze \ Req Approval \ Design Review |  | 2019-07-15: 7/15-8/2
| ENV52 | MMIS Dev | 2019-09-02: 8/5-9/6; 2019-10-14: P1
| ENV57 | MMIS SIT | 2019-09-02: 9/2-9/27; 2019-10-14: P1
| ENV53 | Regression | 2019-09-30: 9/30-10/11; 2019-10-21: P1 (10/23-10/25)
| ENV04 | UAT | 2019-10-14: 10/14-11/8; 2019-10-28: P1(10/28-11/8)
| ENV05 | Prod | 2019-11-11: 2019-11-10
8.7 | Scope Freeze \ Req Approval \ Design Review |  | 2019-08-19: 8/19-9/6
| ENV52 | MMIS Dev | 2019-10-07: 9/9-10/11; 2019-11-25: P1
| ENV57 | MMIS SIT | 2019-10-07: 10/7-11/1; 2019-11-25: P1
| ENV53 | Regression | 2019-11-04: 11/4-11/15; 2019-12-02: P1 (12/4-12/6)
| ENV04 | UAT | 2019-11-18: 11/22-12/27; 2019-12-09: P1(12/9-12/27)
| ENV05 | Prod | 2019-12-30: 2019-12-29
| SysDoc |  | 2019-12-02: Check out to QA - R8.6 & R8.7; 2019-12-16: Check in Doc \ Cognosante Review; 2019-12-30: Review \ Feedback \ Meetings \ Formatting Changes
8.8 | Scope Freeze \ Req Approval \ Design Review |  | 2019-09-23: 9/23-10/11
| ENV52 | MMIS Dev | 2019-11-18: 10/14-11/22; 2020-02-17: P1
| ENV57 | MMIS SIT | 2019-11-18: 11/18-12/20; 2020-02-17: P1
| ENV53 | Regression | 2019-12-23: 12/23-1/3; 2020-02-24: P1 (2/26-2/29)
| ENV04 | UAT | 2020-02-03: 2/6-2/21; 2020-03-02: P1(3/2-3/13)
| ENV05 | Prod | 2020-03-16: 2020-03-15
8.9 | Scope Freeze \ Req Approval \ Design Review |  | 2019-11-04: 11/4-11/22
| ENV52 | MMIS Dev | 2019-12-30: 11/25-1/3
| ENV57 | MMIS SIT | 2019-12-30: 12/30-1/24
| ENV53 | Regression
| ENV04 | UAT
| ENV05 | Prod
SysDoc
8.9 & 9.0 | Scope Freeze \ Req Approval \ Design Review |  | 2019-12-16: 12/16-1/3
| ENV52 | MMIS Dev | 2020-02-10: 1/6-2/14; 2020-04-20: P1
| ENV57 | MMIS SIT | 2020-02-10: 2/10-3/13; 2020-04-20: P1
| ENV53 | Regression | 2020-03-09: 3/9-4/3; 2020-04-27: P1 (4/29-5/1)
| ENV04 | UAT | 2020-04-06: 4/6-5/8; 2020-05-11: P1(5/11-5/29)
| ENV05 | Prod | 2020-06-01: 2020-05-31
9.1 | Scope Freeze \ Req Approval \ Design Review |  | 2020-02-03: 2/3-2/21
| ENV52 | MMIS Dev | 2020-04-20: 2/17-4/24; 2020-06-08: P1
| ENV57 | MMIS SIT | 2020-03-30: 3/30-5/15; 2020-06-08: P1
| ENV53 | Regression | 2020-05-18: 5/18-6/4; 2020-06-15: P1 (6/17-6/19)
| ENV04 | UAT | 2020-06-08: 6/8-6/19; 2020-06-22: P1(6/22-7/3)
| ENV05 | Prod | 2020-07-06: 2020-07-05
| SysDoc |  | 2020-06-22: Check out to QA - R8.8, R8.9, R9.0 & R9.1; 2020-07-06: Check in Doc \ Cognosante Review; 2020-07-20: Review \ Feedback \ Meetings \ Formatting Changes
9.2 | Scope Freeze \ Req Approval \ Design Review |  | 2020-04-20: 4/20-5/8
| ENV52 | MMIS Dev | 2020-06-01: 4/27-6/5; 2020-07-13: P1
| ENV57 | MMIS SIT | 2020-06-01: 6/1-6/26; 2020-07-13: P1
| ENV53 | Regression | 2020-06-29: 6/29-7/10; 2020-07-20: P1 (7/22-7/24)
| ENV04 | UAT | 2020-07-13: 7/13-7/24; 2020-07-27: P1(7/27-8/7)
| ENV05 | Prod | 2020-08-10: 2020-08-09
9.3 | Scope Freeze \ Req Approval \ Design Review |  | 2020-05-18: 5/18-6/5
| ENV52 | MMIS Dev | 2020-07-06: 6/8-7/10; 2020-08-17: P1
| ENV57 | MMIS SIT | 2020-07-06: 7/6-7/31; 2020-08-17: P1
| ENV53 | Regression | 2020-08-03: 8/3-8/14; 2020-08-24: P1 (8/26-8/28)
| ENV04 | UAT | 2020-08-17: 8/17-8/28; 2020-08-31: P1(8/31-9/11)
| ENV05 | Prod | 2020-09-14: 2020-09-13
| SysDoc |  | 2020-08-31: Check out to QA - R9.2 & R9.3; 2020-09-14: Check in Doc \ Cognosante Review; 2020-09-28: Review \ Feedback \ Meetings \ Formatting Changes
9.4 | Scope Freeze \ Req Approval \ Design Review |  | 2020-06-22: 6/22-7/10
| ENV52 | MMIS Dev | 2020-08-10: 7/13-8/14; 2020-09-21: P1
| ENV57 | MMIS SIT | 2020-08-10: 8/10-9/4; 2020-09-21: P1
| ENV53 | Regression | 2020-09-07: 9/7-9/18; 2020-09-28: P1 (9/30-10/2)
| ENV04 | UAT | 2020-09-21: 9/21-10/2; 2020-10-05: P1(10/5-10/16)
| ENV05 | Prod | 2020-10-19: 2020-10-18
9.5 | Scope Freeze \ Req Approval \ Design Review |  | 2020-07-27: 7/27-8/14
| ENV52 | MMIS Dev | 2020-09-14: 8/17-9/18; 2020-10-26: P1
| ENV57 | MMIS SIT | 2020-09-14: 9/14-10/9; 2020-10-26: P1
| ENV53 | Regression | 2020-10-12: 10/12-10/23; 2020-11-02: P1 (11/4-11/6)
| ENV04 | UAT | 2020-10-26: 10/26-11/6; 2020-11-09: P1(11/9-11/20)
| ENV05 | Prod | 2020-11-23: 2020-11-22
| SysDoc |  | 2020-11-09: Check out to QA - R9.4 & R9.5; 2020-11-23: Check in Doc \ Cognosante Review; 2020-12-07: Review \ Feedback \ Meetings \ Formatting Changes
9.6 | Scope Freeze \ Req Approval \ Design Review |  | 2020-08-31: 8/31-9/18
| ENV52 | MMIS Dev | 2020-10-19: 9/21-10/23; 2020-11-30: P1
| ENV57 | MMIS SIT | 2020-10-19: 10/19-11/13; 2020-11-30: P1
| ENV53 | Regression | 2020-11-16: 11/16-11/27; 2020-12-07: P1 (12/9-12/11)
| ENV04 | UAT | 2020-11-30: 11/30-12/11; 2020-12-14: P1(12/14-12/25)
| ENV05 | Prod | 2020-12-28: 2020-12-27
9.7 | Scope Freeze \ Req Approval \ Design Review |  | 2020-10-05: 10/5-10/23
| ENV52 | MMIS Dev | 2020-11-23: 10/26-11/27; 2021-01-04: P1
| ENV57 | MMIS SIT | 2020-11-23: 11/23-12/18; 2021-01-04: P1
| ENV53 | Regression | 2020-12-21: 12/21-1/1; 2021-01-11: P1 (1/13-1/15)
| ENV04 | UAT | 2021-01-04: 1/4-1/15; 2021-01-18: P1(1/18-1/29)
| ENV05 | Prod | 2021-02-01: 2021-01-31
| SysDoc |  | 2021-01-18: Check out to QA - R9.6 & R9.7; 2021-02-01: Check in Doc \ Cognosante Review; 2021-02-15: Review \ Feedback \ Meetings \ Formatting Changes
9.8 | Scope Freeze \ Req Approval \ Design Review |  | 2020-11-09: 11/9-11/27
| ENV52 | MMIS Dev | 2020-12-28: 11/30-1/1; 2021-02-08: P1
| ENV57 | MMIS SIT | 2020-12-28: 12/28-1/22; 2021-02-08: P1
| ENV53 | Regression | 2021-01-25: 1/25-2/5; 2021-02-15: P1 (2/17-2/19)
| ENV04 | UAT | 2021-02-08: 2/8-2/19; 2021-02-22: P1(2/22-3/5)
| ENV05 | Prod | 2021-03-08: 2021-03-07
9.9 | Scope Freeze \ Req Approval \ Design Review |  | 2020-12-14: 12/14-1/1
| ENV52 | MMIS Dev | 2021-02-01: 1/4-2/5; 2021-03-15: P1
| ENV57 | MMIS SIT | 2021-02-01: 2/1-2/26; 2021-03-15: P1
| ENV53 | Regression | 2021-03-01: 3/1-3/12; 2021-03-22: P1 (3/24-3/26)
| ENV04 | UAT | 2021-03-15: 3/15-3/26; 2021-03-29: P1(3/29-4/9)
| ENV05 | Prod | 2021-04-12: 2021-04-11
| SysDoc |  | 2021-03-29: Check out to QA - R9.8 & R9.9; 2021-04-12: Check in Doc \ Cognosante Review; 2021-04-26: Review \ Feedback \ Meetings \ Formatting Changes
10 | Scope Freeze \ Req Approval \ Design Review |  | 2021-01-18: 1/18-2/5
| ENV52 | MMIS Dev | 2021-03-08: 2/8-3/12; 2021-04-19: P1
| ENV57 | MMIS SIT | 2021-03-08: 3/8-4/2; 2021-04-19: P1
| ENV53 | Regression | 2021-04-05: 4/5-4/16; 2021-04-26: P1 (4/28-4/30)
| ENV04 | UAT | 2021-04-19: 4/19-4/30; 2021-05-03: P1(5/3-5/14)
| ENV05 | Prod | 2021-05-17: 2020-05-16

## 20200212
Release | ENV | Phase | 2019-07-01 |  |  |  |  | 2019-08-01 |  |  |  | 2019-09-01 |  |  |  |  | 2019-10-01 |  |  |  | 2019-11-01 |  |  |  | 2019-12-01 |  |  |  |  | 2020-01-01 |  |  |  | 2020-02-01 |  |  |  | 2020-03-01 |  |  |  |  | 2020-04-01 |  |  |  | 2020-05-01 |  |  |  | 2020-06-01 |  |  |  |  | 2020-07-01 |  |  |  | 2020-08-01 |  |  |  |  | 2020-09-01 |  |  |  | 2020-10-01 |  |  |  | 2020-11-01 |  |  |  |  | 2020-12-01 |  |  |  | 2021-01-01 |  |  |  | 2021-02-01 |  |  |  | 2021-03-01 |  |  |  |  | 2021-04-01
 | time axis 2019-07-01 to 2021-04-26
8.6 | Scope Freeze \ Req Approval \ Design Review |  | 2019-07-15: 7/15-8/2
| ENV52 | MMIS Dev | 2019-09-02: 8/5-9/6; 2019-10-14: P1
| ENV57 | MMIS SIT | 2019-09-02: 9/2-9/27; 2019-10-14: P1
| ENV53 | Regression | 2019-09-30: 9/30-10/11; 2019-10-21: P1 (10/23-10/25)
| ENV04 | UAT | 2019-10-14: 10/14-11/8; 2019-10-28: P1(10/28-11/8)
| ENV05 | Prod | 2019-11-11: 2019-11-10
8.7 | Scope Freeze \ Req Approval \ Design Review |  | 2019-08-19: 8/19-9/6
| ENV52 | MMIS Dev | 2019-10-07: 9/9-10/11; 2019-11-25: P1
| ENV57 | MMIS SIT | 2019-10-07: 10/7-11/1; 2019-11-25: P1
| ENV53 | Regression | 2019-11-04: 11/4-11/15; 2019-12-02: P1 (12/4-12/6)
| ENV04 | UAT | 2019-11-18: 11/22-12/27; 2019-12-09: P1(12/9-12/27)
| ENV05 | Prod | 2019-12-30: 2019-12-29
| SysDoc |  | 2019-12-02: Check out to QA - R8.6 & R8.7; 2019-12-16: Check in Doc \ Cognosante Review; 2019-12-30: Review \ Feedback \ Meetings \ Formatting Changes
8.8 | Scope Freeze \ Req Approval \ Design Review |  | 2019-09-23: 9/23-10/11
| ENV52 | MMIS Dev | 2019-11-18: 10/14-11/22; 2020-02-10: P1
| ENV57 | MMIS SIT | 2019-11-18: 11/18-12/20; 2020-02-10: P1
| ENV53 | Regression | 2019-12-23: 12/23-1/3; 2020-02-17: P1 (2/19-2/21)
| ENV04 | UAT | 2020-02-03: 2/6-2/21; 2020-02-24: P1(2/24-3/27)
| ENV05 | Prod | 2020-03-30: 2020-03-29
8.9 | Scope Freeze \ Req Approval \ Design Review |  | 2019-11-04: 11/4-11/22
| ENV52 | MMIS Dev | 2019-12-30: 11/25-1/3
| ENV57 | MMIS SIT | 2019-12-30: 12/30-1/24
| ENV53 | Regression
| ENV04 | UAT
| ENV05 | Prod
SysDoc
8.9 & 9.0 | Scope Freeze \ Req Approval \ Design Review |  | 2019-12-16: 12/16-1/3
| ENV52 | MMIS Dev | 2020-02-10: 1/6-2/14; 2020-04-06: P1
| ENV57 | MMIS SIT | 2020-02-10: 2/10-3/13; 2020-04-06: P1
| ENV53 | Regression | 2020-03-09: 3/9-3/27; 2020-04-13: P1 (4/15-4/17)
| ENV04 | UAT | 2020-04-06: 4/6-4/17; 2020-04-20: P1(4/20-5/1)
| ENV05 | Prod | 2020-05-04: 2020-05-03
9.1 | Scope Freeze \ Req Approval \ Design Review |  | 2020-02-03: 2/3-2/21
| ENV52 | MMIS Dev | 2020-03-23: 2/17-3/27; 2020-05-04: P1
| ENV57 | MMIS SIT | 2020-03-23: 3/23-4/17; 2020-05-04: P1
| ENV53 | Regression | 2020-04-20: 4/20-5/1; 2020-05-11: P1 (5/13-5/15)
| ENV04 | UAT | 2020-05-04: 5/4-5/15; 2020-05-18: P1(5/18-5/29)
| ENV05 | Prod | 2020-06-01: 2020-05-31
| SysDoc |  | 2020-05-18: Check out to QA - R8.8, R8.9, R9.0 & R9.1; 2020-06-08: Check in Doc \ Cognosante Review; 2020-06-29: Review \ Feedback \ Meetings \ Formatting Changes
9.2 | Scope Freeze \ Req Approval \ Design Review |  | 2020-03-09: 3/9-3/27
| ENV52 | MMIS Dev | 2020-04-27: 3/30-5/1; 2020-06-01: P1
| ENV57 | MMIS SIT | 2020-04-27: 4/27-5/22; 2020-06-01: P1
| ENV53 | Regression | 2020-05-18: 5/18-5/28; 2020-06-08: P1 (6/10-6/12)
| ENV04 | UAT | 2020-06-01: 6/3-6/12; 2020-06-15: P1(6/15-6/26)
| ENV05 | Prod | 2020-06-29: 2020-06-28
9.3 | Scope Freeze \ Req Approval \ Design Review |  | 2020-04-13: 4/13-5/1
| ENV52 | MMIS Dev | 2020-06-01: 5/4-6/5; 2020-07-13: P1
| ENV57 | MMIS SIT | 2020-06-01: 6/1-6/26; 2020-07-13: P1
| ENV53 | Regression | 2020-06-29: 6/29-7/10; 2020-07-20: P1 (7/22-7/24)
| ENV04 | UAT | 2020-07-13: 7/13-7/24; 2020-07-27: P1(7/27-8/7)
| ENV05 | Prod | 2020-08-10: 2020-08-09
| SysDoc |  | 2020-07-27: Check out to QA - R9.2 & R9.3; 2020-08-10: Check in Doc \ Cognosante Review; 2020-08-24: Review \ Feedback \ Meetings \ Formatting Changes
9.4 | Scope Freeze \ Req Approval \ Design Review |  | 2020-05-18: 5/18-6/5
| ENV52 | MMIS Dev | 2020-07-06: 6/8-7/10; 2020-08-17: P1
| ENV57 | MMIS SIT | 2020-07-06: 7/6-7/31; 2020-08-17: P1
| ENV53 | Regression | 2020-08-03: 8/3-8/14; 2020-08-24: P1 (8/26-8/28)
| ENV04 | UAT | 2020-08-17: 8/17-8/28; 2020-08-31: P1(8/31-9/11)
| ENV05 | Prod | 2020-09-14: 2020-09-13
9.5 | Scope Freeze \ Req Approval \ Design Review |  | 2020-06-22: 6/22-7/10
| ENV52 | MMIS Dev | 2020-08-10: 7/13-8/14; 2020-09-21: P1
| ENV57 | MMIS SIT | 2020-08-10: 8/10-9/4; 2020-09-21: P1
| ENV53 | Regression | 2020-09-07: 9/7-9/18; 2020-09-28: P1 (9/30-10/2)
| ENV04 | UAT | 2020-09-21: 9/21-10/2; 2020-10-05: P1(10/5-10/16)
| ENV05 | Prod | 2020-10-19: 2020-10-18
| SysDoc |  | 2020-10-05: Check out to QA - R9.4 & R9.5; 2020-10-19: Check in Doc \ Cognosante Review; 2020-11-02: Review \ Feedback \ Meetings \ Formatting Changes
9.6 | Scope Freeze \ Req Approval \ Design Review |  | 2020-07-27: 7/27-8/14
| ENV52 | MMIS Dev | 2020-09-14: 8/17-9/18; 2020-10-26: P1
| ENV57 | MMIS SIT | 2020-09-14: 9/14-10/9; 2020-10-26: P1
| ENV53 | Regression | 2020-10-12: 10/12-10/23; 2020-11-02: P1 (11/4-11/6)
| ENV04 | UAT | 2020-10-26: 10/26-11/6; 2020-11-09: P1(11/9-11/20)
| ENV05 | Prod | 2020-11-23: 2020-11-22
9.7 | Scope Freeze \ Req Approval \ Design Review |  | 2020-08-31: 8/31-9/18
| ENV52 | MMIS Dev | 2020-10-19: 9/21-10/23; 2020-11-30: P1
| ENV57 | MMIS SIT | 2020-10-19: 10/19-11/13; 2020-11-30: P1
| ENV53 | Regression | 2020-11-16: 11/16-11/27; 2020-12-07: P1 (12/9-12/11)
| ENV04 | UAT | 2020-11-30: 11/30-12/11; 2020-12-14: P1(12/14-12/25)
| ENV05 | Prod | 2020-12-28: 2020-12-27
| SysDoc |  | 2020-12-14: Check out to QA - R9.6 & R9.7; 2020-12-28: Check in Doc \ Cognosante Review; 2021-01-11: Review \ Feedback \ Meetings \ Formatting Changes
9.8 | Scope Freeze \ Req Approval \ Design Review |  | 2020-10-05: 10/5-10/23
| ENV52 | MMIS Dev | 2020-11-23: 10/26-11/27; 2021-01-04: P1
| ENV57 | MMIS SIT | 2020-11-23: 11/23-12/18; 2021-01-04: P1
| ENV53 | Regression | 2020-12-21: 12/21-1/1; 2021-01-11: P1 (1/13-1/15)
| ENV04 | UAT | 2021-01-04: 1/4-1/15; 2021-01-18: P1(1/18-1/29)
| ENV05 | Prod | 2021-02-01: 2021-01-31
9.9 | Scope Freeze \ Req Approval \ Design Review |  | 2020-11-09: 11/9-11/27
| ENV52 | MMIS Dev | 2020-12-28: 11/30-1/1; 2021-02-08: P1
| ENV57 | MMIS SIT | 2020-12-28: 12/28-1/22; 2021-02-08: P1
| ENV53 | Regression | 2021-01-25: 1/25-2/5; 2021-02-15: P1 (2/17-2/19)
| ENV04 | UAT | 2021-02-08: 2/8-2/19; 2021-02-22: P1(2/22-3/5)
| ENV05 | Prod | 2021-03-08: 2021-03-07
| SysDoc |  | 2021-02-22: Check out to QA - R9.8 & R9.9; 2021-03-08: Check in Doc \ Cognosante Review; 2021-03-22: Review \ Feedback \ Meetings \ Formatting Changes
10 | Scope Freeze \ Req Approval \ Design Review |  | 2020-12-14: 12/14-1/1
| ENV52 | MMIS Dev | 2021-02-01: 1/4-2/5; 2021-03-15: P1
| ENV57 | MMIS SIT | 2021-02-01: 2/1-2/26; 2021-03-15: P1
| ENV53 | Regression | 2021-03-01: 3/1-3/12; 2021-03-22: P1 (3/24-3/26)
| ENV04 | UAT | 2021-03-15: 3/15-3/26; 2021-03-29: P1(3/29-4/9)
| ENV05 | Prod | 2021-04-12: 2021-04-11

## 20190805
Release | ENV | Phase | 2019-01-01 |  |  |  | 2019-02-01 |  |  |  | 2019-03-01 |  |  |  | 2019-04-01 |  |  |  |  | 2019-05-01 |  |  |  | 2019-06-01 |  |  |  | 2019-07-01 |  |  |  |  | 2019-08-01 |  |  |  | 2019-09-01 |  |  |  |  | 2019-10-01 |  |  |  | 2019-11-01 |  |  |  | 2019-12-01 |  |  |  |  | 2020-01-01 |  |  |  | 2020-02-01 |  |  |  | 2020-03-01 |  |  |  |  | 2020-04-01 |  |  |  | 2020-05-01 |  |  |  | 2020-06-01 |  |  |  |  | 2020-07-01 |  |  |  | 2020-08-01 |  |  |  |  | 2020-09-01 |  |  |  | 2020-10-01 |  |  |  | 2020-11-01 |  |  |  |  | 2020-12-01 |  |  |  | 2021-01-01 |  |  |  | 2021-02-01 |  |  |  | 2021-03-01
 | time axis 2019-01-07 to 2021-03-29
8.1 | Scope Freeze \ Req Approval \ Design Review |  | 2019-01-21: 1/21-2/8
| ENV52 | MMIS Dev | 2019-03-11: 2/11-3/15; 2019-04-22: P1
| ENV57 | MMIS SIT | 2019-03-11: 3/11-4/5; 2019-04-22: P1
| ENV53 | Regression | 2019-04-08: 4/8-4/19; 2019-04-29: P1 (5/1-5/3)
| ENV04 | UAT | 2019-04-22: 4/22-5/17; 2019-05-06: P1(5/6-5/17)
| ENV05 | Prod | 2019-05-20: 2019-05-19
| SysDoc |  | 2019-05-06: Check out to QA - R8.0 & R8.1; 2019-05-20: Check in Doc \ Cognosante Review; 2019-06-03: Review \ Feedback \ Meetings \ Formatting Changes
8.2 | Scope Freeze \ Req Approval \ Design Review |  | 2019-02-25: 2/25-3/15
| ENV52 | MMIS Dev | 2019-04-15: 3/18-4/19; 2019-05-27: P1
| ENV57 | MMIS SIT | 2019-04-15: 4/15-5/10; 2019-05-27: P1
| ENV53 | Regression | 2019-05-13: 5/13-5/24; 2019-06-03: P1 (6/5-6/7)
| ENV04 | UAT | 2019-05-27: 5/27-6/21; 2019-06-10: P1(6/10-6/21)
| ENV05 | Prod | 2019-06-24: 2019-06-23
8.3 | Scope Freeze \ Req Approval \ Design Review |  | 2019-04-01: 4/1-4/19
| ENV52 | MMIS Dev | 2019-05-20: 4/22-5/24; 2019-07-01: P1
| ENV57 | MMIS SIT | 2019-05-20: 5/20-6/14; 2019-07-01: P1
| ENV53 | Regression | 2019-06-17: 6/17-6/28; 2019-07-08: P1 (7/10-7/12)
| ENV04 | UAT | 2019-07-01: 7/1-7/26; 2019-07-15: P1(7/15-7/26)
| ENV05 | Prod | 2019-07-29: 2019-07-28
| SysDoc |  | 2019-07-15: Check out to QA - R8.2 & R8.3; 2019-07-29: Check in Doc \ Cognosante Review; 2019-08-12: Review \ Feedback \ Meetings \ Formatting Changes
8.4 | Scope Freeze \ Req Approval \ Design Review |  | 2019-05-06: 5/6-5/24
| ENV52 | MMIS Dev | 2019-06-24: 5/27-6/28; 2019-08-05: P1
| ENV57 | MMIS SIT | 2019-06-24: 6/24-7/19; 2019-08-05: P1
| ENV53 | Regression | 2019-07-22: 7/22-8/2; 2019-08-12: P1 (8/14-8/16)
| ENV04 | UAT | 2019-08-05: 8/5-8/30; 2019-08-19: P1(8/19-8/30)
| ENV05 | Prod | 2019-09-02: 2019-09-01
8.5 | Scope Freeze \ Req Approval \ Design Review |  | 2019-06-10: 6/10-6/28
| ENV52 | MMIS Dev | 2019-07-29: 7/1-8/2; 2019-09-09: P1
| ENV57 | MMIS SIT | 2019-07-29: 7/29-8/23; 2019-09-09: P1
| ENV53 | Regression | 2019-08-26: 8/26-9/6; 2019-09-16: P1 (9/18-9/20)
| ENV04 | UAT | 2019-09-09: 9/9-10/4; 2019-09-23: P1(9/23-10/4)
| ENV05 | Prod | 2019-10-07: 2019-10-06
| SysDoc |  | 2019-09-23: Check out to QA - R8.4 & R8.5; 2019-10-07: Check in Doc \ Cognosante Review; 2019-10-21: Review \ Feedback \ Meetings \ Formatting Changes
8.6 | Scope Freeze \ Req Approval \ Design Review |  | 2019-07-15: 7/15-8/2
| ENV52 | MMIS Dev | 2019-09-02: 8/5-9/6; 2019-10-14: P1
| ENV57 | MMIS SIT | 2019-09-02: 9/2-9/27; 2019-10-14: P1
| ENV53 | Regression | 2019-09-30: 9/30-10/11; 2019-10-21: P1 (10/23-10/25)
| ENV04 | UAT | 2019-10-14: 10/14-11/8; 2019-10-28: P1(10/28-11/8)
| ENV05 | Prod | 2019-11-11: 2019-11-10
8.7 | Scope Freeze \ Req Approval \ Design Review |  | 2019-08-19: 8/19-9/6
| ENV52 | MMIS Dev | 2019-10-07: 9/9-10/11; 2019-11-25: P1
| ENV57 | MMIS SIT | 2019-10-07: 10/7-11/1; 2019-11-25: P1
| ENV53 | Regression | 2019-11-04: 11/4-11/15; 2019-12-02: P1 (12/4-12/6)
| ENV04 | UAT | 2019-11-18: 11/22-12/27; 2019-12-09: P1(12/9-12/27)
| ENV05 | Prod | 2019-12-30: 2019-12-29
| SysDoc |  | 2019-12-02: Check out to QA - R8.6 & R8.7; 2019-12-16: Check in Doc \ Cognosante Review; 2019-12-30: Review \ Feedback \ Meetings \ Formatting Changes
8.8 | Scope Freeze \ Req Approval \ Design Review |  | 2019-09-23: 9/23-10/11
| ENV52 | MMIS Dev | 2019-11-18: 10/14-11/22; 2020-01-06: P1
| ENV57 | MMIS SIT | 2019-11-18: 11/18-12/20; 2020-01-06: P1
| ENV53 | Regression | 2019-12-23: 12/23-1/3; 2020-01-13: P1 (1/15-1/17)
| ENV04 | UAT | 2020-01-06: 1/6-1/31; 2020-01-20: P1(1/20-1/31)
| ENV05 | Prod | 2020-02-03: 2020-02-02
8.9 | Scope Freeze \ Req Approval \ Design Review |  | 2019-11-04: 11/4-11/22
| ENV52 | MMIS Dev | 2019-12-30: 11/25-1/3; 2020-02-10: P1
| ENV57 | MMIS SIT | 2019-12-30: 12/30-1/24; 2020-02-10: P1
| ENV53 | Regression | 2020-01-27: 1/27-2/7; 2020-02-17: P1 (2/19-2/21)
| ENV04 | UAT | 2020-02-10: 2/10-2/21; 2020-02-24: P1(2/24-3/6)
| ENV05 | Prod | 2020-03-09: 2020-03-08
| SysDoc |  | 2020-02-24: Check out to QA - R8.8 & R8.9; 2020-03-09: Check in Doc \ Cognosante Review; 2020-03-23: Review \ Feedback \ Meetings \ Formatting Changes
9 | Scope Freeze \ Req Approval \ Design Review |  | 2019-12-16: 12/16-1/3
| ENV52 | MMIS Dev | 2020-02-03: 1/6-2/7; 2020-03-16: P1
| ENV57 | MMIS SIT | 2020-02-03: 2/3-2/28; 2020-03-16: P1
| ENV53 | Regression | 2020-03-02: 3/2-3/13; 2020-03-23: P1 (3/25-3/27)
| ENV04 | UAT | 2020-03-16: 3/16-3/27; 2020-03-30: P1(3/30-4/10)
| ENV05 | Prod | 2020-04-13: 2020-04-12
9.1 | Scope Freeze \ Req Approval \ Design Review |  | 2020-01-20: 1/20-2/7
| ENV52 | MMIS Dev | 2020-03-09: 2/10-3/13; 2020-04-20: P1
| ENV57 | MMIS SIT | 2020-03-09: 3/9-4/3; 2020-04-20: P1
| ENV53 | Regression | 2020-04-06: 4/6-4/17; 2020-04-27: P1 (4/29-5/1)
| ENV04 | UAT | 2020-04-20: 4/20-5/1; 2020-05-04: P1(5/4-5/15)
| ENV05 | Prod | 2020-05-18: 2020-05-17
| SysDoc |  | 2020-05-04: Check out to QA - R9.0 & R9.1; 2020-05-18: Check in Doc \ Cognosante Review; 2020-06-01: Review \ Feedback \ Meetings \ Formatting Changes
9.2 | Scope Freeze \ Req Approval \ Design Review |  | 2020-02-24: 2/24-3/13
| ENV52 | MMIS Dev | 2020-04-13: 3/16-4/17; 2020-05-25: P1
| ENV57 | MMIS SIT | 2020-04-13: 4/13-5/8; 2020-05-25: P1
| ENV53 | Regression | 2020-05-11: 5/11-5/22; 2020-06-01: P1 (6/3-6/5)
| ENV04 | UAT | 2020-05-25: 5/25-6/5; 2020-06-08: P1(6/8-6/19)
| ENV05 | Prod | 2020-06-22: 2020-06-21
9.3 | Scope Freeze \ Req Approval \ Design Review |  | 2020-03-30: 3/30-4/17
| ENV52 | MMIS Dev | 2020-05-18: 4/20-5/22; 2020-06-29: P1
| ENV57 | MMIS SIT | 2020-05-18: 5/18-6/12; 2020-06-29: P1
| ENV53 | Regression | 2020-06-15: 6/15-6/26; 2020-07-06: P1 (7/8-7/10)
| ENV04 | UAT | 2020-06-29: 6/29-7/10; 2020-07-13: P1(7/13-7/24)
| ENV05 | Prod | 2020-07-27: 2020-07-26
| SysDoc |  | 2020-07-13: Check out to QA - R9.2 & R9.3; 2020-07-27: Check in Doc \ Cognosante Review; 2020-08-10: Review \ Feedback \ Meetings \ Formatting Changes
9.4 | Scope Freeze \ Req Approval \ Design Review |  | 2020-05-04: 5/4-5/22
| ENV52 | MMIS Dev | 2020-06-22: 5/25-6/26; 2020-08-03: P1
| ENV57 | MMIS SIT | 2020-06-22: 6/22-7/17; 2020-08-03: P1
| ENV53 | Regression | 2020-07-20: 7/20-7/31; 2020-08-10: P1 (8/12-8/14)
| ENV04 | UAT | 2020-08-03: 8/3-8/14; 2020-08-17: P1(8/17-8/28)
| ENV05 | Prod | 2020-08-31: 2020-08-30
9.5 | Scope Freeze \ Req Approval \ Design Review |  | 2020-06-08: 6/8-6/26
| ENV52 | MMIS Dev | 2020-07-27: 6/29-7/31; 2020-09-07: P1
| ENV57 | MMIS SIT | 2020-07-27: 7/27-8/21; 2020-09-07: P1
| ENV53 | Regression | 2020-08-24: 8/24-9/4; 2020-09-14: P1 (9/16-9/18)
| ENV04 | UAT | 2020-09-07: 9/7-9/18; 2020-09-21: P1(9/21-10/2)
| ENV05 | Prod | 2020-10-05: 2020-10-04
| SysDoc |  | 2020-09-21: Check out to QA - R9.4 & R9.5; 2020-10-05: Check in Doc \ Cognosante Review; 2020-10-19: Review \ Feedback \ Meetings \ Formatting Changes
9.6 | Scope Freeze \ Req Approval \ Design Review |  | 2020-07-13: 7/13-7/31
| ENV52 | MMIS Dev | 2020-08-31: 8/3-9/4; 2020-10-12: P1
| ENV57 | MMIS SIT | 2020-08-31: 8/31-9/25; 2020-10-12: P1
| ENV53 | Regression | 2020-09-28: 9/28-10/9; 2020-10-19: P1 (10/21-10/23)
| ENV04 | UAT | 2020-10-12: 10/12-10/23; 2020-10-26: P1(10/26-11/6)
| ENV05 | Prod | 2020-11-09: 2020-11-08
9.7 | Scope Freeze \ Req Approval \ Design Review |  | 2020-08-17: 8/17-9/4
| ENV52 | MMIS Dev | 2020-10-05: 9/7-10/9; 2020-11-16: P1
| ENV57 | MMIS SIT | 2020-10-05: 10/5-10/30; 2020-11-16: P1
| ENV53 | Regression | 2020-11-02: 11/2-11/13; 2020-11-23: P1 (11/25-11/27)
| ENV04 | UAT | 2020-11-16: 11/16-11/27; 2020-11-30: P1(11/30-12/11)
| ENV05 | Prod | 2020-12-14: 2020-12-13
| SysDoc |  | 2020-11-30: Check out to QA - R9.6 & R9.7; 2020-12-14: Check in Doc \ Cognosante Review; 2020-12-28: Review \ Feedback \ Meetings \ Formatting Changes
9.8 | Scope Freeze \ Req Approval \ Design Review |  | 2020-09-21: 9/21-10/9
| ENV52 | MMIS Dev | 2020-11-09: 10/12-11/13; 2020-12-21: P1
| ENV57 | MMIS SIT | 2020-11-09: 11/9-12/4; 2020-12-21: P1
| ENV53 | Regression | 2020-12-07: 12/7-12/18; 2020-12-28: P1 (12/30-1/1)
| ENV04 | UAT | 2020-12-21: 12/21-1/1; 2021-01-04: P1(1/4-1/15)
| ENV05 | Prod | 2021-01-18: 2021-01-17
9.9 | Scope Freeze \ Req Approval \ Design Review |  | 2020-10-26: 10/26-11/13
| ENV52 | MMIS Dev | 2020-12-14: 11/16-12/18; 2021-01-25: P1
| ENV57 | MMIS SIT | 2020-12-14: 12/14-1/8; 2021-01-25: P1
| ENV53 | Regression | 2021-01-11: 1/11-1/22; 2021-02-01: P1 (2/3-2/5)
| ENV04 | UAT | 2021-01-25: 1/25-2/5; 2021-02-08: P1(2/8-2/19)
| ENV05 | Prod | 2021-02-22: 2021-02-21
| SysDoc |  | 2021-02-08: Check out to QA - R9.8 & R9.9; 2021-02-22: Check in Doc \ Cognosante Review; 2021-03-08: Review \ Feedback \ Meetings \ Formatting Changes
10 | Scope Freeze \ Req Approval \ Design Review |  | 2020-11-30: 11/30-12/18
| ENV52 | MMIS Dev | 2021-01-18: 12/21-1/22; 2021-03-01: P1
| ENV57 | MMIS SIT | 2021-01-18: 1/18-2/12; 2021-03-01: P1
| ENV53 | Regression | 2021-02-15: 2/15-2/26; 2021-03-08: P1 (3/10-3/12)
| ENV04 | UAT | 2021-03-01: 3/1-3/12; 2021-03-15: P1(3/15-3/26)
| ENV05 | Prod | 2021-03-29: 2021-03-28

## 20190512
Release | ENV | Phase | 2019-01-01 |  |  |  | 2019-02-01 |  |  |  | 2019-03-01 |  |  |  | 2019-04-01 |  |  |  |  | 2019-05-01 |  |  |  | 2019-06-01 |  |  |  | 2019-07-01 |  |  |  |  | 2019-08-01 |  |  |  | 2019-09-01 |  |  |  |  | 2019-10-01 |  |  |  | 2019-11-01 |  |  |  | 2019-12-01 |  |  |  |  | 2020-01-01 |  |  |  | 2020-02-01 |  |  |  | 2020-03-01 |  |  |  |  | 2020-04-01 |  |  |  | 2020-05-01 |  |  |  | 2020-06-01 |  |  |  |  | 2020-07-01 |  |  |  | 2020-08-01 |  |  |  |  | 2020-09-01 |  |  |  | 2020-10-01 |  |  |  | 2020-11-01 |  |  |  |  | 2020-12-01 |  |  |  | 2021-01-01 |  |  |  | 2021-02-01 |  |  |  | 2021-03-01
 | time axis 2019-01-07 to 2021-03-29
8.1 | Scope Freeze \ Req Approval \ Design Review |  | 2019-01-21: 1/21-2/8
| ENV52 | MMIS Dev | 2019-03-11: 2/11-3/15; 2019-04-22: P1
| ENV57 | MMIS SIT | 2019-03-11: 3/11-4/5; 2019-04-22: P1
| ENV53 | Regression | 2019-04-08: 4/8-4/19; 2019-04-29: P1 (5/1-5/3)
| ENV04 | UAT | 2019-04-22: 4/22-5/17; 2019-05-06: P1(5/6-5/17)
| ENV05 | Prod | 2019-05-20: 2019-05-19
| SysDoc |  | 2019-05-06: Check out to QA - R8.0 & R8.1; 2019-05-20: Check in Doc \ Cognosante Review; 2019-06-03: Review \ Feedback \ Meetings \ Formatting Changes
8.2 | Scope Freeze \ Req Approval \ Design Review |  | 2019-02-25: 2/25-3/15
| ENV52 | MMIS Dev | 2019-04-15: 3/18-4/19; 2019-05-27: P1
| ENV57 | MMIS SIT | 2019-04-15: 4/15-5/10; 2019-05-27: P1
| ENV53 | Regression | 2019-05-13: 5/13-5/24; 2019-06-03: P1 (6/5-6/7)
| ENV04 | UAT | 2019-05-27: 5/27-6/21; 2019-06-10: P1(6/10-6/21)
| ENV05 | Prod | 2019-06-24: 2019-06-23
8.3 | Scope Freeze \ Req Approval \ Design Review |  | 2019-04-01: 4/1-4/19
| ENV52 | MMIS Dev | 2019-05-20: 4/22-5/24; 2019-07-01: P1
| ENV57 | MMIS SIT | 2019-05-20: 5/20-6/14; 2019-07-01: P1
| ENV53 | Regression | 2019-06-17: 6/17-6/28; 2019-07-08: P1 (7/10-7/12)
| ENV04 | UAT | 2019-07-01: 7/1-7/26; 2019-07-15: P1(7/15-7/26)
| ENV05 | Prod | 2019-07-29: 2019-07-28
| SysDoc |  | 2019-07-15: Check out to QA - R8.2 & R8.3; 2019-07-29: Check in Doc \ Cognosante Review; 2019-08-12: Review \ Feedback \ Meetings \ Formatting Changes
8.4 | Scope Freeze \ Req Approval \ Design Review |  | 2019-05-06: 5/6-5/24
| ENV52 | MMIS Dev | 2019-06-24: 5/27-6/28; 2019-08-05: P1
| ENV57 | MMIS SIT | 2019-06-24: 6/24-7/19; 2019-08-05: P1
| ENV53 | Regression | 2019-07-22: 7/22-8/2; 2019-08-12: P1 (8/14-8/16)
| ENV04 | UAT | 2019-08-05: 8/5-8/30; 2019-08-19: P1(8/19-8/30)
| ENV05 | Prod | 2019-09-02: 2019-09-01
8.5 | Scope Freeze \ Req Approval \ Design Review |  | 2019-06-10: 6/10-6/28
| ENV52 | MMIS Dev | 2019-07-29: 7/1-8/2; 2019-09-09: P1
| ENV57 | MMIS SIT | 2019-07-29: 7/29-8/23; 2019-09-09: P1
| ENV53 | Regression | 2019-08-26: 8/26-9/6; 2019-09-16: P1 (9/18-9/20)
| ENV04 | UAT | 2019-09-09: 9/9-10/4; 2019-09-23: P1(9/23-10/4)
| ENV05 | Prod | 2019-10-07: 2019-10-06
| SysDoc |  | 2019-09-23: Check out to QA - R8.4 & R8.5; 2019-10-07: Check in Doc \ Cognosante Review; 2019-10-21: Review \ Feedback \ Meetings \ Formatting Changes
8.6 | Scope Freeze \ Req Approval \ Design Review |  | 2019-07-15: 7/15-8/2
| ENV52 | MMIS Dev | 2019-09-02: 8/5-9/6; 2019-10-14: P1
| ENV57 | MMIS SIT | 2019-09-02: 9/2-9/27; 2019-10-14: P1
| ENV53 | Regression | 2019-09-30: 9/30-10/11; 2019-10-21: P1 (10/23-10/25)
| ENV04 | UAT | 2019-10-14: 10/14-11/8; 2019-10-28: P1(10/28-11/8)
| ENV05 | Prod | 2019-11-11: 2019-11-10
8.7 | Scope Freeze \ Req Approval \ Design Review |  | 2019-08-19: 8/19-9/6
| ENV52 | MMIS Dev | 2019-10-07: 9/9-10/11; 2019-11-18: P1
| ENV57 | MMIS SIT | 2019-10-07: 10/7-11/1; 2019-11-18: P1
| ENV53 | Regression | 2019-11-04: 11/4-11/15; 2019-11-25: P1 (11/27-11/29)
| ENV04 | UAT | 2019-11-18: 11/18-12/13; 2019-12-02: P1(12/2-12/13)
| ENV05 | Prod | 2019-12-16: 2019-12-15
| SysDoc |  | 2019-12-02: Check out to QA - R8.6 & R8.7; 2019-12-16: Check in Doc \ Cognosante Review; 2019-12-30: Review \ Feedback \ Meetings \ Formatting Changes
8.8 | Scope Freeze \ Req Approval \ Design Review |  | 2019-09-23: 9/23-10/11
| ENV52 | MMIS Dev | 2019-11-11: 10/14-11/15; 2019-12-23: P1
| ENV57 | MMIS SIT | 2019-11-11: 11/11-12/6; 2019-12-23: P1
| ENV53 | Regression | 2019-12-09: 12/9-12/20; 2019-12-30: P1 (1/1-1/3)
| ENV04 | UAT | 2019-12-23: 12/23-1/17; 2020-01-06: P1(1/6-1/17)
| ENV05 | Prod | 2020-01-20: 2020-01-19
8.9 | Scope Freeze \ Req Approval \ Design Review |  | 2019-10-28: 10/28-11/15
| ENV52 | MMIS Dev | 2019-12-16: 11/18-12/20; 2020-01-27: P1
| ENV57 | MMIS SIT | 2019-12-16: 12/16-1/10; 2020-01-27: P1
| ENV53 | Regression | 2020-01-13: 1/13-1/24; 2020-02-03: P1 (2/5-2/7)
| ENV04 | UAT | 2020-01-27: 1/27-2/21; 2020-02-10: P1(2/10-2/21)
| ENV05 | Prod | 2020-02-24: 2020-02-23
| SysDoc |  | 2020-02-10: Check out to QA - R8.8 & R8.9; 2020-02-24: Check in Doc \ Cognosante Review; 2020-03-09: Review \ Feedback \ Meetings \ Formatting Changes
9 | Scope Freeze \ Req Approval \ Design Review |  | 2019-12-02: 12/2-12/20
| ENV52 | MMIS Dev | 2020-01-20: 12/23-1/24; 2020-03-02: P1
| ENV57 | MMIS SIT | 2020-01-20: 1/20-2/14; 2020-03-02: P1
| ENV53 | Regression | 2020-02-17: 2/17-2/28; 2020-03-09: P1 (3/11-3/13)
| ENV04 | UAT | 2020-03-02: 3/2-3/27; 2020-03-16: P1(3/16-3/27)
| ENV05 | Prod | 2020-03-30: 2020-03-29
9.1 | Scope Freeze \ Req Approval \ Design Review |  | 2020-01-06: 1/6-1/24
| ENV52 | MMIS Dev | 2020-02-24: 1/27-2/28; 2020-04-06: P1
| ENV57 | MMIS SIT | 2020-02-24: 2/24-3/20; 2020-04-06: P1
| ENV53 | Regression | 2020-03-23: 3/23-4/3; 2020-04-13: P1 (4/15-4/17)
| ENV04 | UAT | 2020-04-06: 4/6-5/1; 2020-04-20: P1(4/20-5/1)
| ENV05 | Prod | 2020-05-04: 2020-05-03
| SysDoc |  | 2020-04-20: Check out to QA - R9.0 & R9.1; 2020-05-04: Check in Doc \ Cognosante Review; 2020-05-18: Review \ Feedback \ Meetings \ Formatting Changes
9.2 | Scope Freeze \ Req Approval \ Design Review |  | 2020-02-10: 2/10-2/28
| ENV52 | MMIS Dev | 2020-03-30: 3/2-4/3; 2020-05-11: P1
| ENV57 | MMIS SIT | 2020-03-30: 3/30-4/24; 2020-05-11: P1
| ENV53 | Regression | 2020-04-27: 4/27-5/8; 2020-05-18: P1 (5/20-5/22)
| ENV04 | UAT | 2020-05-11: 5/11-6/5; 2020-05-25: P1(5/25-6/5)
| ENV05 | Prod | 2020-06-08: 2020-06-07
9.3 | Scope Freeze \ Req Approval \ Design Review |  | 2020-03-16: 3/16-4/3
| ENV52 | MMIS Dev | 2020-05-04: 4/6-5/8; 2020-06-15: P1
| ENV57 | MMIS SIT | 2020-05-04: 5/4-5/29; 2020-06-15: P1
| ENV53 | Regression | 2020-06-01: 6/1-6/12; 2020-06-22: P1 (6/24-6/26)
| ENV04 | UAT | 2020-06-15: 6/15-7/10; 2020-06-29: P1(6/29-7/10)
| ENV05 | Prod | 2020-07-13: 2020-07-12
| SysDoc |  | 2020-06-29: Check out to QA - R9.2 & R9.3; 2020-07-13: Check in Doc \ Cognosante Review; 2020-07-27: Review \ Feedback \ Meetings \ Formatting Changes
9.4 | Scope Freeze \ Req Approval \ Design Review |  | 2020-04-20: 4/20-5/8
| ENV52 | MMIS Dev | 2020-06-08: 5/11-6/12; 2020-07-20: P1
| ENV57 | MMIS SIT | 2020-06-08: 6/8-7/3; 2020-07-20: P1
| ENV53 | Regression | 2020-07-06: 7/6-7/17; 2020-07-27: P1 (7/29-7/31)
| ENV04 | UAT | 2020-07-20: 7/20-8/14; 2020-08-03: P1(8/3-8/14)
| ENV05 | Prod | 2020-08-17: 2020-08-16
9.5 | Scope Freeze \ Req Approval \ Design Review |  | 2020-05-25: 5/25-6/12
| ENV52 | MMIS Dev | 2020-07-13: 6/15-7/17; 2020-08-24: P1
| ENV57 | MMIS SIT | 2020-07-13: 7/13-8/7; 2020-08-24: P1
| ENV53 | Regression | 2020-08-10: 8/10-8/21; 2020-08-31: P1 (9/2-9/4)
| ENV04 | UAT | 2020-08-24: 8/24-9/18; 2020-09-07: P1(9/7-9/18)
| ENV05 | Prod | 2020-09-21: 2020-09-20
| SysDoc |  | 2020-09-07: Check out to QA - R9.4 & R9.5; 2020-09-21: Check in Doc \ Cognosante Review; 2020-10-05: Review \ Feedback \ Meetings \ Formatting Changes
9.6 | Scope Freeze \ Req Approval \ Design Review |  | 2020-06-29: 6/29-7/17
| ENV52 | MMIS Dev | 2020-08-17: 7/20-8/21; 2020-09-28: P1
| ENV57 | MMIS SIT | 2020-08-17: 8/17-9/11; 2020-09-28: P1
| ENV53 | Regression | 2020-09-14: 9/14-9/25; 2020-10-05: P1 (10/7-10/9)
| ENV04 | UAT | 2020-09-28: 9/28-10/23; 2020-10-12: P1(10/12-10/23)
| ENV05 | Prod | 2020-10-26: 2020-10-25
9.7 | Scope Freeze \ Req Approval \ Design Review |  | 2020-08-03: 8/3-8/21
| ENV52 | MMIS Dev | 2020-09-21: 8/24-9/25; 2020-11-02: P1
| ENV57 | MMIS SIT | 2020-09-21: 9/21-10/16; 2020-11-02: P1
| ENV53 | Regression | 2020-10-19: 10/19-10/30; 2020-11-09: P1 (10/11-10/13)
| ENV04 | UAT | 2020-11-02: 11/2-11/27; 2020-11-16: P1(11/16-11/27)
| ENV05 | Prod | 2020-11-30: 2020-11-29
| SysDoc |  | 2020-11-16: Check out to QA - R9.6 & R9.7; 2020-11-30: Check in Doc \ Cognosante Review; 2020-12-14: Review \ Feedback \ Meetings \ Formatting Changes
9.8 | Scope Freeze \ Req Approval \ Design Review |  | 2020-09-07: 9/7-9/25
| ENV52 | MMIS Dev | 2020-10-26: 9/28-10/30; 2020-12-07: P1
| ENV57 | MMIS SIT | 2020-10-26: 10/26-11/20; 2020-12-07: P1
| ENV53 | Regression | 2020-11-23: 11/23-12/4; 2020-12-14: P1 (12/16-12/18)
| ENV04 | UAT | 2020-12-07: 12/7-1/1; 2020-12-21: P1(12/21-1/1)
| ENV05 | Prod | 2021-01-04: 2021-01-03
9.9 | Scope Freeze \ Req Approval \ Design Review |  | 2020-10-12: 10/12-10/30
| ENV52 | MMIS Dev | 2020-11-30: 11/2-12/4; 2021-01-11: P1
| ENV57 | MMIS SIT | 2020-11-30: 11/30-12/25; 2021-01-11: P1
| ENV53 | Regression | 2020-12-28: 12/28-1/8; 2021-01-18: P1 (1/20-1/22)
| ENV04 | UAT | 2021-01-11: 1/11-2/5; 2021-01-25: P1(1/25-2/5)
| ENV05 | Prod | 2021-02-08: 2021-02-07
| SysDoc |  | 2021-01-25: Check out to QA - R9.8 & R9.9; 2021-02-08: Check in Doc \ Cognosante Review; 2021-02-22: Review \ Feedback \ Meetings \ Formatting Changes
10 | Scope Freeze \ Req Approval \ Design Review |  | 2020-11-16: 11/16-12/4
| ENV52 | MMIS Dev | 2021-01-04: 12/7-1/8; 2021-02-15: P1
| ENV57 | MMIS SIT | 2021-01-04: 1/4-1/29; 2021-02-15: P1
| ENV53 | Regression | 2021-02-01: 2/1-2/12; 2021-02-22: P1 (2/14-2/26)
| ENV04 | UAT | 2021-02-15: 2/15-3/12; 2021-03-01: P1(3/1-3/12)
| ENV05 | Prod | 2021-03-15: 2021-03-14

## 20190108
Release | ENV | Phase | 2017-11-01 |  |  |  | 2017-12-01 |  |  |  | 2018-01-01 |  |  |  |  | 2018-02-01 |  |  |  | 2018-03-01 |  |  |  | 2018-04-01 |  |  |  |  | 2018-05-01 |  |  |  | 2018-06-01 |  |  |  | 2018-07-01 |  |  |  |  | 2018-08-01 |  |  |  | 2018-09-01 |  |  |  | 2018-10-01 |  |  |  |  | 2018-11-01 |  |  |  | 2018-12-01 |  |  |  |  | 2019-01-01 |  |  |  | 2019-02-01 |  |  |  | 2019-03-01 |  |  |  | 2019-04-01 |  |  |  |  | 2019-05-01 |  |  |  | 2019-06-01 |  |  |  | 2019-07-01 |  |  |  |  | 2019-08-01 |  |  |  | 2019-09-01 |  |  |  |  | 2019-10-01 |  |  |  | 2019-11-01 |  |  |  | 2019-12-01 |  |  |  |  | 2020-01-01 |  |  |  | 2020-02-01 |  |  |  | 2019-03-01
 | time axis 2017-11-06 to 2020-03-30
6.9 | Scope Freeze \ Req Approval \ Design Review |  | 2017-11-06: 11/6-12/1
| ENV52 | MMIS Dev | 2018-01-08: 12/4-1/12; 2018-02-19: P1
| ENV57 | MMIS SIT | 2018-01-08: 1/8-2/2; 2018-02-19: P1
| ENV53 | Regression | 2018-02-05: 2/5-2/16; 2018-02-26: 2/28-3/2
| ENV04 | UAT | 2018-02-19: 2/19-3/16; 2018-03-05: P1 (3/5-3/16)
| ENV05 | Prod | 2018-03-19: 2018-03-18
| SysDoc |  | 2018-03-05: Check out to QA - R6.8 & R6.9; 2018-03-19: Check in Doc \ Cognasante Review; 2018-04-02: Review \ Feedback \ Meetings \ Formatting Changes
7 | Scope Freeze \ Req Approval \ Design Review |  | 2017-12-25: 12/25-1/12
| ENV52 | MMIS Dev | 2018-02-12: 1/15-2/16; 2018-03-26: P1
| ENV57 | MMIS SIT | 2018-02-12: 2/12-3/9; 2018-03-26: P1
| ENV53 | Regression | 2018-03-12: 3/12-3/23; 2018-04-02: P1 (4/4-4/6)
| ENV04 | UAT | 2018-03-26: 3/26-4/20; 2018-04-09: P1(4/9-4/20)
| ENV05 | Prod | 2018-04-23: 2018-04-22
7.1 | Scope Freeze \ Req Approval \ Design Review |  | 2018-01-29: 1/29-2/23
| ENV52 | MMIS Dev | 2018-03-26: 2/19-3/30; 2018-05-07: P1
| ENV57 | MMIS SIT | 2018-03-26: 3/26-4/20; 2018-05-07: P1
| ENV53 | Regression | 2018-04-23: 4/23-5/4; 2018-05-14: P1 (5/16-5/18)
| ENV04 | UAT | 2018-05-07: 5/7-6/1; 2018-05-21: P1(5/21-6/1)
| ENV05 | Prod | 2018-06-04: 2018-06-03
| SysDoc |  | 2018-05-21: Check out to QA - R7.0 & R7.1; 2018-06-04: Check in Doc \ Cognasante Review; 2018-06-18: Review \ Feedback \ Meetings \ Formatting Changes
7.2 | Scope Freeze \ Req Approval \ Design Review |  | 2018-03-12: 3/12-3/30
| ENV52 | MMIS Dev | 2018-04-30: 4/2-5/4; 2018-06-11: P1
| ENV57 | MMIS SIT | 2018-04-30: 4/30-5/25; 2018-06-11: P1
| ENV53 | Regression | 2018-05-28: 5/28-6/8; 2018-06-18: P1 (6/20-6/22)
| ENV04 | UAT | 2018-06-11: 6/11-7/6; 2018-06-25: P1(6/25-7/6)
| ENV05 | Prod | 2018-07-09: 2018-07-08
7.3 | Scope Freeze \ Req Approval \ Design Review |  | 2018-04-16: 4/16-5/4
| ENV52 | MMIS Dev | 2018-06-04: 5/7-6/8; 2018-07-16: P1
| ENV57 | MMIS SIT | 2018-06-04: 6/4-6/29; 2018-07-16: P1
| ENV53 | Regression | 2018-07-02: 7/2-7/13; 2018-07-23: P1 (7/25-7/27)
| ENV04 | UAT | 2018-07-16: 7/16-8/10; 2018-07-30: P1(7/30-8/10)
| ENV05 | Prod | 2018-08-13: 2018-08-12
| SysDoc |  | 2018-07-30: Check out to QA - R7.2 & R7.3; 2018-08-13: Check in Doc \ Cognasante Review; 2018-08-27: Review \ Feedback \ Meetings \ Formatting Changes
7.4 | Scope Freeze \ Req Approval \ Design Review |  | 2018-05-21: 5/21-6/8
| ENV52 | MMIS Dev | 2018-07-09: 6/11-7/13; 2018-08-20: P1
| ENV57 | MMIS SIT | 2018-07-09: 7/9-8/3; 2018-08-20: P1
| ENV53 | Regression | 2018-08-06: 8/6-8/17; 2018-08-27: P1 (8/29-8/31)
| ENV04 | UAT | 2018-08-20: 8/20-9/14; 2018-09-03: P1(9/3-9/14)
| ENV05 | Prod | 2018-09-17: 2018-09-16
7.5 | Scope Freeze \ Req Approval \ Design Review |  | 2018-06-25: 6/25-7/13
| ENV52 | MMIS Dev | 2018-08-13: 7/16-8/17; 2018-09-24: P1
| ENV57 | MMIS SIT | 2018-08-13: 8/13-9/7; 2018-09-24: P1
| ENV53 | Regression | 2018-09-10: 9/10-9/21; 2018-10-01: P1 (10/3-10/5)
| ENV04 | UAT | 2018-09-24: 9/24-10/19; 2018-10-08: P1(10/8-10/19)
| ENV05 | Prod | 2018-10-22: 2018-10-21
| SysDoc |  | 2018-10-08: Check out to QA - R7.4 & R7.5; 2018-10-22: Check in Doc \ Cognasante Review; 2018-11-05: Review \ Feedback \ Meetings \ Formatting Changes
7.6 | Scope Freeze \ Req Approval \ Design Review |  | 2018-07-30: 7/30-8/17
| ENV52 | MMIS Dev | 2018-09-17: 8/20-9/21; 2018-10-29: P1
| ENV57 | MMIS SIT | 2018-09-17: 9/17-10/12; 2018-10-29: P1
| ENV53 | Regression | 2018-10-15: 10/15-10/26; 2018-11-05: P1 (11/7-11/9)
| ENV04 | UAT | 2018-10-29: 10/29-11/23; 2018-11-12: P1(11/12-11/23)
| ENV05 | Prod | 2018-11-26: 2018-11-25
7.7 | Scope Freeze \ Req Approval \ Design Review |  | 2018-09-03: 9/3-9/21
| ENV52 | MMIS Dev | 2018-10-22: 9/24-10/26; 2018-12-03: P1
| ENV57 | MMIS SIT | 2018-10-22: 10/22-11/16; 2018-12-03: P1
| ENV53 | Regression | 2018-11-19: 11/19-11/30; 2018-12-10: P1 (12/12-12/14)
| ENV04 | UAT | 2018-12-03: 12/3-12/28; 2018-12-17: P1(12/17-12/28)
| ENV05 | Prod | 2018-12-31: 2019-01-01
| SysDoc |  | 2018-12-17: Check out to QA - R7.6 & R7.7; 2018-12-31: Check in Doc \ Cognasante Review; 2019-01-14: Review \ Feedback \ Meetings \ Formatting Changes
7.8 | Scope Freeze \ Req Approval \ Design Review |  | 2018-10-08: 10/8-10/26
| ENV52 | MMIS Dev | 2018-11-26: 10/29-11/30; 2019-01-07: P1
| ENV57 | MMIS SIT | 2018-11-26: 11/26-12/21; 2019-01-07: P1
| ENV53 | Regression | 2018-12-24: 12/24-1/4; 2019-01-14: P1 (1/16-1/18)
| ENV04 | UAT | 2019-01-07: 1/7-2/1; 2019-01-21: P1(1/21-2/1)
| ENV05 | Prod | 2019-02-04: 2019-02-03
7.9 | Scope Freeze \ Req Approval \ Design Review |  | 2018-11-12: 11/12-11/30
| ENV52 | MMIS Dev | 2018-12-31: 12/3-1/4; 2019-02-11: P1
| ENV57 | MMIS SIT | 2018-12-31: 12/31-1/25; 2019-02-11: P1
| ENV53 | Regression | 2019-01-28: 1/28-2/8; 2019-02-18: P1 (2/20-2/22)
| ENV04 | UAT | 2019-02-18: 2/18-3/8; 2019-02-25: P1(2/25-3/8)
| ENV05 | Prod | 2019-03-11: 2019-03-10
| SysDoc |  | 2019-02-25: Check out to QA - R7.8 & R7.9; 2019-03-11: Check in Doc \ Cognasante Review; 2019-03-25: Review \ Feedback \ Meetings \ Formatting Changes
8 | Scope Freeze \ Req Approval \ Design Review |  | 2018-12-17: 12/17-1/4
| ENV52 | MMIS Dev | 2019-02-04: 1/7-2/8; 2019-03-18: P1
| ENV57 | MMIS SIT | 2019-02-04: 2/4-3/1; 2019-03-18: P1
| ENV53 | Regression | 2019-03-04: 3/4-3/15; 2019-03-25: P1 (3/27-3/29)
| ENV04 | UAT | 2019-03-25: 3/25-4/12; 2019-04-01: P1(4/1-4/12)
| ENV05 | Prod | 2019-04-15: 2019-04-14
8.1 | Scope Freeze \ Req Approval \ Design Review |  | 2019-01-21: 1/21-2/8
| ENV52 | MMIS Dev | 2019-03-11: 2/11-3/15; 2019-04-22: P1
| ENV57 | MMIS SIT | 2019-03-11: 3/11-4/5; 2019-04-22: P1
| ENV53 | Regression | 2019-04-08: 4/8-4/19; 2019-04-29: P1 (5/1-5/3)
| ENV04 | UAT | 2019-04-22: 4/22-5/17; 2019-05-06: P1(5/6-5/17)
| ENV05 | Prod | 2019-05-20: 2019-05-19
| SysDoc |  | 2019-05-06: Check out to QA - R8.0 & R8.1; 2019-05-20: Check in Doc \ Cognosante Review; 2019-06-03: Review \ Feedback \ Meetings \ Formatting Changes
8.2 | Scope Freeze \ Req Approval \ Design Review |  | 2019-02-25: 2/25-3/15
| ENV52 | MMIS Dev | 2019-04-15: 3/18-4/19; 2019-05-27: P1
| ENV57 | MMIS SIT | 2019-04-15: 4/15-5/10; 2019-05-27: P1
| ENV53 | Regression | 2019-05-13: 5/13-5/24; 2019-06-03: P1 (6/5-6/7)
| ENV04 | UAT | 2019-05-27: 5/27-6/21; 2019-06-10: P1(6/10-6/21)
| ENV05 | Prod | 2019-06-24: 2019-06-23
8.3 | Scope Freeze \ Req Approval \ Design Review |  | 2019-04-01: 4/1-4/19
| ENV52 | MMIS Dev | 2019-05-20: 4/22-5/24; 2019-07-01: P1
| ENV57 | MMIS SIT | 2019-05-20: 5/20-6/14; 2019-07-01: P1
| ENV53 | Regression | 2019-06-17: 6/17-6/28; 2019-07-08: P1 (7/10-7/12)
| ENV04 | UAT | 2019-07-01: 7/1-7/26; 2019-07-15: P1(7/15-7/26)
| ENV05 | Prod | 2019-07-29: 2019-07-28
| SysDoc |  | 2019-07-15: Check out to QA - R8.2 & R8.3; 2019-07-29: Check in Doc \ Cognosante Review; 2019-08-12: Review \ Feedback \ Meetings \ Formatting Changes
8.4 | Scope Freeze \ Req Approval \ Design Review |  | 2019-05-06: 5/6-5/24
| ENV52 | MMIS Dev | 2019-06-24: 5/27-6/28; 2019-08-05: P1
| ENV57 | MMIS SIT | 2019-06-24: 6/24-7/19; 2019-08-05: P1
| ENV53 | Regression | 2019-07-22: 7/22-8/2; 2019-08-12: P1 (8/14-8/16)
| ENV04 | UAT | 2019-08-05: 8/5-8/30; 2019-08-19: P1(8/19-8/30)
| ENV05 | Prod | 2019-09-02: 2019-09-01
8.5 | Scope Freeze \ Req Approval \ Design Review |  | 2019-06-10: 6/10-6/28
| ENV52 | MMIS Dev | 2019-07-29: 7/1-8/2; 2019-09-09: P1
| ENV57 | MMIS SIT | 2019-07-29: 7/29-8/23; 2019-09-09: P1
| ENV53 | Regression | 2019-08-26: 8/26-9/6; 2019-09-16: P1 (9/18-9/20)
| ENV04 | UAT | 2019-09-09: 9/9-10/4; 2019-09-23: P1(9/23-10/4)
| ENV05 | Prod | 2019-10-07: 2019-10-06
| SysDoc |  | 2019-09-23: Check out to QA - R8.4 & R8.5; 2019-10-07: Check in Doc \ Cognosante Review; 2019-10-21: Review \ Feedback \ Meetings \ Formatting Changes
8.6 | Scope Freeze \ Req Approval \ Design Review |  | 2019-07-15: 7/15-8/2
| ENV52 | MMIS Dev | 2019-09-02: 8/5-9/6; 2019-10-14: P1
| ENV57 | MMIS SIT | 2019-09-02: 9/2-9/27; 2019-10-14: P1
| ENV53 | Regression | 2019-09-30: 9/30-10/11; 2019-10-21: P1 (10/23-10/25)
| ENV04 | UAT | 2019-10-14: 10/14-11/8; 2019-10-28: P1(10/28-11/8)
| ENV05 | Prod | 2019-11-11: 2019-11-10
8.7 | Scope Freeze \ Req Approval \ Design Review |  | 2019-08-19: 8/19-9/6
| ENV52 | MMIS Dev | 2019-10-07: 9/9-10/11; 2019-11-18: P1
| ENV57 | MMIS SIT | 2019-10-07: 10/7-11/1; 2019-11-18: P1
| ENV53 | Regression | 2019-11-04: 11/4-11/15; 2019-11-25: P1 (11/27-11/29)
| ENV04 | UAT | 2019-11-18: 11/18-12/13; 2019-12-02: P1(12/2-12/13)
| ENV05 | Prod | 2019-12-16: 2019-12-15
| SysDoc |  | 2019-12-02: Check out to QA - R8.6 & R8.7; 2019-12-16: Check in Doc \ Cognosante Review; 2019-12-30: Review \ Feedback \ Meetings \ Formatting Changes
8.8 | Scope Freeze \ Req Approval \ Design Review |  | 2019-09-23: 9/23-10/11
| ENV52 | MMIS Dev | 2019-11-11: 10/14-11/15; 2019-12-23: P1
| ENV57 | MMIS SIT | 2019-11-11: 11/11-12/6; 2019-12-23: P1
| ENV53 | Regression | 2019-12-09: 12/9-12/20; 2019-12-30: P1 (1/1-1/3)
| ENV04 | UAT | 2019-12-23: 12/23-1/17; 2020-01-06: P1(1/6-1/17)
| ENV05 | Prod | 2020-01-20: 2020-01-19
8.9 | Scope Freeze \ Req Approval \ Design Review |  | 2019-10-28: 10/28-11/15
| ENV52 | MMIS Dev | 2019-12-16: 11/18-12/20; 2020-01-27: P1
| ENV57 | MMIS SIT | 2019-12-16: 12/16-1/10; 2020-01-27: P1
| ENV53 | Regression | 2020-01-13: 1/13-1/24; 2020-02-03: P1 (2/5-2/7)
| ENV04 | UAT | 2020-01-27: 1/27-2/21; 2020-02-10: P1(2/10-2/21)
| ENV05 | Prod | 2020-02-24: 2020-02-23
| SysDoc |  | 2020-02-10: Check out to QA - R8.8 & R8.9; 2020-02-24: Check in Doc \ Cognosante Review; 2020-03-09: Review \ Feedback \ Meetings \ Formatting Changes
9.0 | Scope Freeze \ Req Approval \ Design Review |  | 2019-12-02: 12/2-12/20
| ENV52 | MMIS Dev | 2020-01-20: 12/23-1/24; 2020-03-02: P1
| ENV57 | MMIS SIT | 2020-01-20: 1/20-2/14; 2020-03-02: P1
| ENV53 | Regression | 2020-02-17: 2/17-2/28; 2020-03-09: P1 (3/11-3/13)
| ENV04 | UAT | 2020-03-02: 3/2-3/27; 2020-03-16: P1(3/16-3/27)
| ENV05 | Prod | 2020-03-30: 2020-03-29

## 20180202
Release | ENV | Phase | 2017-06-01 |  |  |  | 2017-07-01 |  |  |  |  | 2017-08-01 |  |  |  | 2017-09-01 |  |  |  | 2017-10-01 |  |  |  |  | 2017-11-01 |  |  |  | 2017-12-01 |  |  |  | 2018-01-01 |  |  |  |  | 2018-02-01 |  |  |  | 2018-03-01 |  |  |  | 2018-04-01 |  |  |  |  | 2018-05-01 |  |  |  | 2018-06-01 |  |  |  | 2018-07-01 |  |  |  |  | 2018-08-01 |  |  |  | 2018-09-01 |  |  |  | 2018-10-01 |  |  |  |  | 2018-11-01 |  |  |  | 2018-12-01 |  |  |  |  | 2019-01-01
 | time axis 2017-06-05 to 2019-01-28
6.6 (Push out by 1 Week) | Scope Freeze \ Req Approval \ Design Review |  | 2017-06-19: 6/19-7/7
| ENV52 | MMIS Dev | 2017-08-07: 7/10-8/11; 2017-09-25: P1
| ENV57 | MMIS SIT | 2017-08-14: 8/16-9/8; 2017-09-25: P1
| ENV53 | Regression | 2017-09-11: 9/11-9/22; 2017-10-02: P1 (10/4-10/6)
| ENV04 | UAT | 2017-09-25: 9/25-10/20; 2017-10-09: P1(10/9-10/20)
| ENV05 | Prod | 2017-10-23: 2017-10-22
6.7 (2 weeks Pushout) | Scope Freeze \ Req Approval \ Design Review |  | 2017-08-21: 8/21-9/8
| ENV52 | MMIS Dev | 2017-10-02: 9/11-10/6; 2017-11-27: P1
| ENV57 | MMIS SIT | 2017-10-02: 10/2-10/27; 2017-11-27: P1
| ENV53 | Regression | 2017-10-30: 10/30-11/10; 2017-12-04: P1 (12/4-12/5)
| ENV04 | UAT | 2017-11-27: 11/28-12/15; 2017-12-04: P1(12/6-12/15
| ENV05 | Prod | 2017-12-18: 2017-12-17
| SysDoc |  | 2017-11-27: Check out to QA - R6.6 & R6.7; 2017-12-11: Check in Doc \ Cognasante Review; 2017-12-25: Review \ Feedback \ Meetings \ Formatting Changes
6.8 | Scope Freeze \ Req Approval \ Design Review |  | 2017-09-25: 9/25-10/13
| ENV52 | MMIS Dev | 2017-11-27: 10/16-12/1; 2018-01-08: P1
| ENV57 | MMIS SIT | 2017-11-20: 11/20-12/22; 2018-01-08: P1
| ENV53 | Regression | 2017-12-25: 12/25-1/5; 2018-01-15: P1 (1/17-1/19)
| ENV04 | UAT | 2018-01-08: 1/8-2/2; 2018-01-22: P1(1/22-2/2)
| ENV05 | Prod | 2018-02-05: 2018-02-04
6.9 | Scope Freeze \ Req Approval \ Design Review |  | 2017-11-06: 11/6-12/1
| ENV52 | MMIS Dev | 2018-01-08: 12/4-1/12; 2018-02-19: P1
| ENV57 | MMIS SIT | 2018-01-08: 1/8-2/2; 2018-02-19: P1
| ENV53 | Regression | 2018-02-05: 2/5-2/16; 2018-02-26: 2/28-3/2
| ENV04 | UAT | 2018-02-19: 2/19-3/16; 2018-03-05: P1 (3/5-3/16)
| ENV05 | Prod | 2018-03-19: 2018-03-18
| SysDoc |  | 2018-03-05: Check out to QA - R6.8 & R6.9; 2018-03-19: Check in Doc \ Cognasante Review; 2018-04-02: Review \ Feedback \ Meetings \ Formatting Changes
7 | Scope Freeze \ Req Approval \ Design Review |  | 2017-12-25: 12/25-1/12
| ENV52 | MMIS Dev | 2018-02-12: 1/15-2/16; 2018-03-26: P1
| ENV57 | MMIS SIT | 2018-02-12: 2/12-3/9; 2018-03-26: P1
| ENV53 | Regression | 2018-03-12: 3/12-3/23; 2018-04-02: P1 (4/4-4/6)
| ENV04 | UAT | 2018-03-26: 3/26-4/20; 2018-04-09: P1(4/9-4/20)
| ENV05 | Prod | 2018-04-23: 2018-04-22
7.1 | Scope Freeze \ Req Approval \ Design Review |  | 2018-01-29: 1/29-2/23
| ENV52 | MMIS Dev | 2018-03-26: 2/19-3/30; 2018-05-07: P1
| ENV57 | MMIS SIT | 2018-03-26: 3/26-4/20; 2018-05-07: P1
| ENV53 | Regression | 2018-04-23: 4/23-5/4; 2018-05-14: P1 (5/16-5/18)
| ENV04 | UAT | 2018-05-07: 5/7-6/1; 2018-05-21: P1(5/21-6/1)
| ENV05 | Prod | 2018-06-04: 2018-06-03
| SysDoc |  | 2018-05-21: Check out to QA - R7.0 & R7.1; 2018-06-04: Check in Doc \ Cognasante Review; 2018-06-18: Review \ Feedback \ Meetings \ Formatting Changes
7.2 | Scope Freeze \ Req Approval \ Design Review |  | 2018-03-12: 3/12-3/30
| ENV52 | MMIS Dev | 2018-04-30: 4/2-5/4; 2018-06-11: P1
| ENV57 | MMIS SIT | 2018-04-30: 4/30-5/25; 2018-06-11: P1
| ENV53 | Regression | 2018-05-28: 5/28-6/8; 2018-06-18: P1 (6/20-6/22)
| ENV04 | UAT | 2018-06-11: 6/11-7/6; 2018-06-25: P1(6/25-7/6)
| ENV05 | Prod | 2018-07-09: 2018-07-08
7.3 | Scope Freeze \ Req Approval \ Design Review |  | 2018-04-16: 4/16-5/4
| ENV52 | MMIS Dev | 2018-06-04: 5/7-6/8; 2018-07-16: P1
| ENV57 | MMIS SIT | 2018-06-04: 6/4-6/29; 2018-07-16: P1
| ENV53 | Regression | 2018-07-02: 7/2-7/13; 2018-07-23: P1 (7/25-7/27)
| ENV04 | UAT | 2018-07-16: 7/16-8/10; 2018-07-30: P1(7/30-8/10)
| ENV05 | Prod | 2018-08-13: 2018-08-12
| SysDoc |  | 2018-07-30: Check out to QA - R7.0 & R7.1; 2018-08-13: Check in Doc \ Cognasante Review; 2018-08-27: Review \ Feedback \ Meetings \ Formatting Changes
7.4 | Scope Freeze \ Req Approval \ Design Review |  | 2018-05-21: 5/21-6/8
| ENV52 | MMIS Dev | 2018-07-09: 6/11-7/13; 2018-08-20: P1
| ENV57 | MMIS SIT | 2018-07-09: 7/9-8/3; 2018-08-20: P1
| ENV53 | Regression | 2018-08-06: 8/6-8/17; 2018-08-27: P1 (8/29-8/31)
| ENV04 | UAT | 2018-08-20: 8/20-9/14; 2018-09-03: P1(9/3-9/14)
| ENV05 | Prod | 2018-09-17: 2018-09-16
7.5 | Scope Freeze \ Req Approval \ Design Review |  | 2018-06-25: 6/25-7/13
| ENV52 | MMIS Dev | 2018-08-13: 7/16-8/17; 2018-09-24: P1
| ENV57 | MMIS SIT | 2018-08-13: 8/13-9/7; 2018-09-24: P1
| ENV53 | Regression | 2018-09-10: 9/10-9/21; 2018-10-01: P1 (10/3-10/5)
| ENV04 | UAT | 2018-09-24: 9/24-10/19; 2018-10-08: P1(10/8-10/19)
| ENV05 | Prod | 2018-10-22: 2018-10-21
| SysDoc |  | 2018-10-08: Check out to QA - R7.0 & R7.1; 2018-10-22: Check in Doc \ Cognasante Review; 2018-11-05: Review \ Feedback \ Meetings \ Formatting Changes
7.6 | Scope Freeze \ Req Approval \ Design Review |  | 2018-07-30: 7/30-8/17
| ENV52 | MMIS Dev | 2018-09-17: 8/20-9/21; 2018-10-29: P1
| ENV57 | MMIS SIT | 2018-09-17: 9/17-10/12; 2018-10-29: P1
| ENV53 | Regression | 2018-10-15: 10/15-10/26; 2018-11-05: P1 (11/7-11/9)
| ENV04 | UAT | 2018-10-29: 10/29-11/23; 2018-11-12: P1(11/12-11/23)
| ENV05 | Prod | 2018-11-26: 2018-11-25
7.7 | Scope Freeze \ Req Approval \ Design Review |  | 2018-09-03: 9/3-9/21
| ENV52 | MMIS Dev | 2018-10-22: 9/24-10/26; 2018-12-03: P1
| ENV57 | MMIS SIT | 2018-10-22: 10/22-11/16; 2018-12-03: P1
| ENV53 | Regression | 2018-11-19: 11/19-11/30; 2018-12-10: P1 (12/12-12/14)
| ENV04 | UAT | 2018-12-03: 12/3-12/28; 2018-12-17: P1(12/17-12/28)
| ENV05 | Prod | 2018-12-31: 2018-12-30
| SysDoc |  | 2018-12-17: Check out to QA - R7.0 & R7.1; 2018-12-31: Check in Doc \ Cognasante Review; 2019-01-14: Review \ Feedback \ Meetings \ Formatting Changes

## 20180105
Release | ENV | Phase | 2017-06-01 |  |  |  | 2017-07-01 |  |  |  |  | 2017-08-01 |  |  |  | 2017-09-01 |  |  |  | 2017-10-01 |  |  |  |  | 2017-11-01 |  |  |  | 2017-12-01 |  |  |  | 2018-01-01 |  |  |  |  | 2018-02-01 |  |  |  | 2018-03-01 |  |  |  | 2018-04-01 |  |  |  |  | 2018-05-01 |  |  |  | 2018-06-01 |  |  |  | 2018-07-01 |  |  |  |  | 2018-08-01 |  |  |  | 2018-09-01 |  |  |  | 2018-10-01 |  |  |  |  | 2018-11-01 |  |  |  | 2018-12-01 |  |  |  |  | 2019-01-01
 | time axis 2017-06-05 to 2019-01-28
6.6 (Push out by 1 Week) | Scope Freeze \ Req Approval \ Design Review |  | 2017-06-19: 6/19-7/7
| ENV52 | MMIS Dev | 2017-08-07: 7/10-8/11; 2017-09-25: P1
| ENV57 | MMIS SIT | 2017-08-14: 8/16-9/8; 2017-09-25: P1
| ENV53 | Regression | 2017-09-11: 9/11-9/22; 2017-10-02: P1 (10/4-10/6)
| ENV04 | UAT | 2017-09-25: 9/25-10/20; 2017-10-09: P1(10/9-10/20)
| ENV05 | Prod | 2017-10-23: 2017-10-22
6.7 (2 weeks Pushout) | Scope Freeze \ Req Approval \ Design Review |  | 2017-08-21: 8/21-9/8
| ENV52 | MMIS Dev | 2017-10-02: 9/11-10/6; 2017-11-27: P1
| ENV57 | MMIS SIT | 2017-10-02: 10/2-10/27; 2017-11-27: P1
| ENV53 | Regression | 2017-10-30: 10/30-11/10; 2017-12-04: P1 (12/4-12/5)
| ENV04 | UAT | 2017-11-27: 11/28-12/15; 2017-12-04: P1(12/6-12/15
| ENV05 | Prod | 2017-12-18: 2017-12-17
| SysDoc |  | 2017-11-27: Check out to QA - R6.6 & R6.7; 2017-12-11: Check in Doc \ Cognasante Review; 2017-12-25: Review \ Feedback \ Meetings \ Formatting Changes
6.8 | Scope Freeze \ Req Approval \ Design Review |  | 2017-09-25: 9/25-10/13
| ENV52 | MMIS Dev | 2017-11-27: 10/16-12/1; 2018-01-08: P1
| ENV57 | MMIS SIT | 2017-11-20: 11/20-12/22; 2018-01-08: P1
| ENV53 | Regression | 2017-12-25: 12/25-1/5; 2018-01-15: P1 (1/17-1/19)
| ENV04 | UAT | 2018-01-08: 1/8-2/2; 2018-01-22: P1(1/22-2/2)
| ENV05 | Prod | 2018-02-05: 2018-02-04
6.9 | Scope Freeze \ Req Approval \ Design Review |  | 2017-11-06: 11/6-12/1
| ENV52 | MMIS Dev | 2018-01-08: 12/4-1/12; 2018-02-19: P1
| ENV57 | MMIS SIT | 2018-01-08: 1/8-2/2; 2018-02-19: P1
| ENV53 | Regression | 2018-02-05: 2/5-2/16; 2018-02-26: 2/28-3/2
| ENV04 | UAT | 2018-02-19: 2/19-3/16; 2018-03-05: P1 (3/5-3/16)
| ENV05 | Prod | 2018-03-19: 2018-03-18
| SysDoc |  | 2018-03-05: Check out to QA - R6.8 & R6.9; 2018-03-19: Check in Doc \ Cognasante Review; 2018-04-02: Review \ Feedback \ Meetings \ Formatting Changes
7 | Scope Freeze \ Req Approval \ Design Review |  | 2017-12-25: 12/25-1/12
| ENV52 | MMIS Dev | 2018-02-12: 1/15-2/16; 2018-03-26: P1
| ENV57 | MMIS SIT | 2018-02-12: 2/12-3/9; 2018-03-26: P1
| ENV53 | Regression | 2018-03-12: 3/12-3/23; 2018-04-02: P1 (4/4-4/6)
| ENV04 | UAT | 2018-03-26: 3/26-4/20; 2018-04-09: P1(4/9-4/20)
| ENV05 | Prod | 2018-04-23: 2018-04-22
7.1 | Scope Freeze \ Req Approval \ Design Review |  | 2018-01-29: 1/29-2/16
| ENV52 | MMIS Dev | 2018-03-19: 2/19-3/23; 2018-04-30: P1
| ENV57 | MMIS SIT | 2018-03-19: 3/19-4/13; 2018-04-30: P1
| ENV53 | Regression | 2018-04-16: 4/16-4/27; 2018-05-07: P1 (5/9-5/11)
| ENV04 | UAT | 2018-04-30: 4/30-5/25; 2018-05-14: P1(5/14-5/25)
| ENV05 | Prod | 2018-05-28: 2018-05-27
| SysDoc |  | 2018-05-14: Check out to QA - R7.0 & R7.1; 2018-05-28: Check in Doc \ Cognasante Review; 2018-06-11: Review \ Feedback \ Meetings \ Formatting Changes
7.2 | Scope Freeze \ Req Approval \ Design Review |  | 2018-03-05: 3/5-3/23
| ENV52 | MMIS Dev | 2018-04-23: 3/26-4/27; 2018-06-04: P1
| ENV57 | MMIS SIT | 2018-04-23: 4/23-5/18; 2018-06-04: P1
| ENV53 | Regression | 2018-05-21: 5/21-6/1; 2018-06-11: P1 (6/13-6/15)
| ENV04 | UAT | 2018-06-04: 6/4-6/29; 2018-06-18: P1(6/18-6/29)
| ENV05 | Prod | 2018-07-02: 2018-07-01
7.3 | Scope Freeze \ Req Approval \ Design Review |  | 2018-04-09: 4/9-4/27
| ENV52 | MMIS Dev | 2018-05-28: 4/30-6/1; 2018-07-09: P1
| ENV57 | MMIS SIT | 2018-05-28: 5/28-6/22; 2018-07-09: P1
| ENV53 | Regression | 2018-06-25: 6/25-7/6; 2018-07-16: P1 (7/19-7/20)
| ENV04 | UAT | 2018-07-09: 7/9-8/3; 2018-07-23: P1(7/23-8/3)
| ENV05 | Prod | 2018-08-06: 2018-08-05
| SysDoc |  | 2018-07-23: Check out to QA - R7.0 & R7.1; 2018-08-06: Check in Doc \ Cognasante Review; 2018-08-20: Review \ Feedback \ Meetings \ Formatting Changes
7.4 | Scope Freeze \ Req Approval \ Design Review |  | 2018-05-14: 5/14-6/1
| ENV52 | MMIS Dev | 2018-07-02: 6/4-7/6; 2018-08-13: P1
| ENV57 | MMIS SIT | 2018-07-02: 7/2-7/27; 2018-08-13: P1
| ENV53 | Regression | 2018-07-30: 7/30-8/10; 2018-08-20: P1 (8/22-8/24)
| ENV04 | UAT | 2018-08-13: 8/13-9/7; 2018-08-27: P1(8/27-9/7)
| ENV05 | Prod | 2018-09-10: 2018-09-09
7.5 | Scope Freeze \ Req Approval \ Design Review |  | 2018-06-18: 6/18-7/6
| ENV52 | MMIS Dev | 2018-08-06: 7/9-8/10; 2018-09-17: P1
| ENV57 | MMIS SIT | 2018-08-06: 8/6-8/31; 2018-09-17: P1
| ENV53 | Regression | 2018-09-03: 9/3-9/14; 2018-09-24: P1 (9/26-9/28)
| ENV04 | UAT | 2018-09-17: 9/17-10/12; 2018-10-01: P1(10/1-10/12)
| ENV05 | Prod | 2018-10-15: 2018-10-14
| SysDoc |  | 2018-10-01: Check out to QA - R7.0 & R7.1; 2018-10-15: Check in Doc \ Cognasante Review; 2018-10-29: Review \ Feedback \ Meetings \ Formatting Changes
7.6 | Scope Freeze \ Req Approval \ Design Review |  | 2018-07-23: 7/23-8/10
| ENV52 | MMIS Dev | 2018-09-10: 8/13-9/14; 2018-10-22: P1
| ENV57 | MMIS SIT | 2018-09-10: 9/10-10/5; 2018-10-22: P1
| ENV53 | Regression | 2018-10-08: 10/8-10/19; 2018-10-29: P1 (10/31-11/2)
| ENV04 | UAT | 2018-10-22: 10/22-11/16; 2018-11-05: P1(11/5-11/16)
| ENV05 | Prod | 2018-11-19: 2018-11-18
7.7 | Scope Freeze \ Req Approval \ Design Review |  | 2018-08-27: 8/27-9/14
| ENV52 | MMIS Dev | 2018-10-15: 9/17-10/19; 2018-11-26: P1
| ENV57 | MMIS SIT | 2018-10-15: 10/15-11/9; 2018-11-26: P1
| ENV53 | Regression | 2018-11-12: 11/12-11/23; 2018-12-03: P1 (12/5-12/7)
| ENV04 | UAT | 2018-11-26: 11/26-12/21; 2018-12-10: P1(12/10-12/21)
| ENV05 | Prod | 2018-12-24: 2018-12-23
| SysDoc |  | 2018-12-10: Check out to QA - R7.0 & R7.1; 2018-12-24: Check in Doc \ Cognasante Review; 2019-01-07: Review \ Feedback \ Meetings \ Formatting Changes

## 20171128
Release | ENV | Phase |  |  |  | 2016-11-01 |  |  |  | 2016-12-01 |  |  |  | 2017-01-01 |  |  |  |  | 2017-02-01 |  |  |  | 2017-03-01 |  |  |  | 2017-04-01 |  |  |  | 2017-05-01 |  |  |  |  | 2017-06-01 |  |  |  | 2017-07-01 |  |  |  |  | 2017-08-01 |  |  |  | 2017-09-01 |  |  |  | 2017-10-01 |  |  |  |  | 2017-11-01 |  |  |  | 2017-12-01 |  |  |  | 2018-01-01 |  |  |  |  | 2018-02-01 |  |  |  | 2018-03-01 |  |  |  | 2018-04-01 |  |  |  |  | 2018-05-01 |  |  |  | 2018-06-01 |  |  |  | 2018-07-01 |  |  |  |  | 2018-08-01 |  |  |  | 2018-09-01 |  |  |  | 2018-10-01 |  |  |  |  | 2018-11-01 |  |  |  | 2018-12-01
 | time axis 2016-10-17 to 2018-12-31
5.9 | Scope Freeze \ Req Approval \ Design Review |  | 2016-10-17: 10/17-11/4; 2016-11-07: 1; 2016-11-14: 2; 2016-11-21: 3; 2016-11-28: 4; 2016-12-05: 5
| ENV52 | MMIS Dev | 2016-12-05: 11/7-12/9; 2017-01-16: P1
| ENV57 | MMIS SIT | 2016-12-05: 12/5-12/30; 2017-01-16: P1
| ENV53 | Regression | 2017-01-02: 1/2 - 1/13; 2017-01-23: P1 (1/25-1/27)
| ENV04 | UAT | 2017-01-16: 1/16-2/10; 2017-01-30: P1 (1/30-2/10)
| ENV05 | Prod | 2017-02-13: 2017-02-12
| SysDoc |  | 2017-01-30: Check out to QA - R5.8 & R5.9; 2017-02-13: Check in Doc \ Cognasante Review; 2017-02-27: Review \ Feedback \ Meetings \ Formatting Changes
6 | Scope Freeze \ Req Approval \ Design Review |  | 2016-11-21: 11/21-12/9; 2016-12-12: 1; 2016-12-19: 2; 2016-12-26: 3; 2017-01-02: 4; 2017-01-09: 5
| ENV52 | MMIS Dev | 2017-01-09: 12/12-1/13; 2017-02-20: P1
| ENV57 | MMIS SIT | 2017-01-09: 1/9-2/3; 2017-02-20: P1
| ENV53 | Regression | 2017-02-06: 2/6 - 2/17; 2017-02-27: P1 (3/1-3/3)
| ENV04 | UAT | 2017-02-20: 2/20-3/17; 2017-03-06: P1 (3/6-3/17)
| ENV05 | Prod | 2017-03-20: 2017-03-19
6.1 | Scope Freeze \ Req Approval \ Design Review |  | 2016-12-26: 12/26-1/13
| ENV52 | MMIS Dev | 2017-02-13: 1/16-2/17; 2017-03-27: P1
| ENV57 | MMIS SIT | 2017-02-13: 2/13-3/10; 2017-03-27: P1
| ENV53 | Regression | 2017-03-13: 3/13-3/24; 2017-04-03: P1 (4/5-4/7)
| ENV04 | UAT | 2017-03-27: 3/27-4/21; 2017-04-10: P1(4/10-4/21)
| ENV05 | Prod | 2017-04-24: 2016-04-23
| SysDoc |  | 2017-04-10: Check out to QA - R6.0&R6.1; 2017-04-24: Check in Doc \ Cognasante Review; 2017-05-08: Review \ Feedback \ Meetings \ Formatting Changes
6.2 | Scope Freeze \ Req Approval \ Design Review |  | 2017-01-30: 1/30-2/17
| ENV52 | MMIS Dev | 2017-03-20: 2/20-3/24; 2017-05-08: P1
| ENV57 | MMIS SIT | 2017-03-20: 3/20-4/14; 2017-05-08: P1
| ENV53 | Regression | 2017-04-17: 4/17-4/28; 2017-05-15: P1(5/17-5/19)
| ENV04 | UAT | 2017-05-08: 5/8-6/2; 2017-05-22: P1(5/22-6/2)
| ENV05 | Prod | 2017-06-05: 2017-06-04
6.3 | Scope Freeze \ Req Approval \ Design Review |  | 2017-03-06: 3/6-3/24
| ENV52 | MMIS Dev | 2017-04-24: 4/25-5/19; 2017-06-19: P1
| ENV57 | MMIS SIT | 2017-05-15: 5/15-6/9; 2017-06-19: P1
| ENV53 | Regression | 2017-06-12: 6/12-6/16; 2017-06-26: P1 (6/28-6/30)
| ENV04 | UAT | 2017-06-19: (6/19-7/7); 2017-07-03: P1(7/3-7/7)
| ENV05 | Prod | 2017-07-10: 2017-07-09
| SysDoc |  | 2017-07-03: Check out to QA - R6.2 & R6.3; 2017-07-17: Check in Doc \ Cognasante Review; 2017-07-31: Review \ Feedback \ Meetings \ Formatting Changes
6.4 | Scope Freeze \ Req Approval \ Design Review | bar: 2017-05-01 to 2017-05-15
| ENV52 | MMIS Dev | 2017-06-12: 5/22-6/2
| ENV57 | MMIS SIT | 2017-06-19: 6/19-7/7
| ENV53 | Regression | 2017-07-10: 7/10-7/14
| ENV04 | UAT | 2017-07-17: 7/17-8/4; 2017-07-24: 7/24-8/4
| ENV05 | Prod | 2017-08-07: 2017-08-06
6.5 | Scope Freeze \ Req Approval \ Design Review |  | 2017-05-15: 5/15-6/2
| ENV52 | MMIS Dev | 2017-07-03: 6/5-7/7; 2017-08-14: P1
| ENV57 | MMIS SIT | 2017-07-03: 7/3-7/28; 2017-08-14: P1
| ENV53 | Regression | 2017-07-31: 7/31-8/11; 2017-08-21: P1 (8/23-8/25); 2017-08-28: Dry run by New Team
| ENV04 | UAT | 2017-08-14: 8/14-9/8; 2017-08-28: P1(8/28-9/8)
| ENV05 | Prod | 2017-09-11: 2017-09-10
| SysDoc |  | 2017-08-28: Check out to QA - R6.4 & R6.5; 2017-09-11: Check in Doc \ Cognasante Review; 2017-09-25: Review \ Feedback \ Meetings \ Formatting Changes
6.6 (Push out by 1 Week) | Scope Freeze \ Req Approval \ Design Review |  | 2017-06-19: 6/19-7/7
| ENV52 | MMIS Dev | 2017-08-07: 7/10-8/11; 2017-09-25: P1
| ENV57 | MMIS SIT | 2017-08-14: 8/16-9/8; 2017-09-25: P1
| ENV53 | Regression | 2017-09-11: 9/11-9/22; 2017-10-02: P1 (10/4-10/6)
| ENV04 | UAT | 2017-09-25: 9/25-10/20; 2017-10-09: P1(10/9-10/20)
| ENV05 | Prod | 2017-10-23: 2017-10-22
6.7 (2 weeks Pushout) | Scope Freeze \ Req Approval \ Design Review |  | 2017-08-21: 8/21-9/8
| ENV52 | MMIS Dev | 2017-10-02: 9/11-10/6; 2017-11-27: P1
| ENV57 | MMIS SIT | 2017-10-02: 10/2-10/27; 2017-11-27: P1
| ENV53 | Regression | 2017-10-30: 10/30-11/10; 2017-12-04: P1 (12/4-12/5)
| ENV04 | UAT | 2017-11-27: 11/28-12/15; 2017-12-04: P1(12/6-12/15
| ENV05 | Prod | 2017-12-18: 2017-12-17
| SysDoc |  | 2017-11-27: Check out to QA - R6.6 & R6.7; 2017-12-11: Check in Doc \ Cognasante Review; 2017-12-25: Review \ Feedback \ Meetings \ Formatting Changes
6.8 - Release with 5 Weeks UAT | Scope Freeze \ Req Approval \ Design Review |  | 2017-09-25: 9/25-10/13
| ENV52 | MMIS Dev | 2017-11-27: 10/16-12/1; 2018-01-08: P1
| ENV57 | MMIS SIT | 2017-11-20: 11/20-12/22; 2018-01-08: P1
| ENV53 | Regression | 2017-12-25: 12/25-1/5; 2018-01-15: P1 (1/17-1/19)
| ENV04 | UAT | 2018-01-08: 1/8-2/2; 2018-01-22: P1(1/22-2/2)
| ENV05 | Prod | 2018-02-05: 2018-02-04
6.9 | Scope Freeze \ Req Approval \ Design Review |  | 2017-11-06: 11/6-12/1
| ENV52 | MMIS Dev | 2018-01-08: 12/4-1/12; 2018-02-19: P1
| ENV57 | MMIS SIT | 2018-01-08: 1/8-2/2; 2018-02-19: P1
| ENV53 | Regression | 2018-02-05: 2/5-2/16; 2018-02-26: 2/28-3/2
| ENV04 | UAT | 2018-02-19: 2/19-3/16; 2018-03-05: P1 (3/5-3/16)
| ENV05 | Prod | 2018-03-19: 2018-03-18
| SysDoc |  | 2018-03-05: Check out to QA - R6.8 & R6.9; 2018-03-19: Check in Doc \ Cognasante Review; 2018-04-02: Review \ Feedback \ Meetings \ Formatting Changes
7 | Scope Freeze \ Req Approval \ Design Review |  | 2017-12-25: 12/25-1/12
| ENV52 | MMIS Dev | 2018-02-12: 1/15-2/16; 2018-03-26: P1
| ENV57 | MMIS SIT | 2018-02-12: 2/12-3/9; 2018-03-26: P1
| ENV53 | Regression | 2018-03-12: 3/12-3/23; 2018-04-02: P1 (4/4-4/6)
| ENV04 | UAT | 2018-03-26: 3/26-4/20; 2018-04-09: P1(4/9-4/20)
| ENV05 | Prod | 2018-04-23: 2018-04-22
7.1 | Scope Freeze \ Req Approval \ Design Review |  | 2018-01-29: 1/29-2/16
| ENV52 | MMIS Dev | 2018-03-19: 2/19-3/23; 2018-04-30: P1
| ENV57 | MMIS SIT | 2018-03-19: 3/19-4/13; 2018-04-30: P1
| ENV53 | Regression | 2018-04-16: 4/16-4/27; 2018-05-07: P1 (5/9-5/11)
| ENV04 | UAT | 2018-04-30: 4/30-5/25; 2018-05-14: P1(5/14-5/25)
| ENV05 | Prod | 2018-05-28: 2018-05-27
| SysDoc |  | 2018-05-14: Check out to QA - R7.0 & R7.1; 2018-05-28: Check in Doc \ Cognasante Review; 2018-06-11: Review \ Feedback \ Meetings \ Formatting Changes
7.2 | Scope Freeze \ Req Approval \ Design Review |  | 2018-03-05: 3/5-3/23
| ENV52 | MMIS Dev | 2018-04-23: 3/26-4/27; 2018-06-04: P1
| ENV57 | MMIS SIT | 2018-04-23: 4/23-5/18; 2018-06-04: P1
| ENV53 | Regression | 2018-05-21: 5/21-6/1; 2018-06-11: P1 (6/13-6/15)
| ENV04 | UAT | 2018-06-04: 6/4-6/29; 2018-06-18: P1(6/18-6/29)
| ENV05 | Prod | 2018-07-02: 2018-07-01

## 20170817
Release | ENV | Phase |  |  |  | 2016-11-01 |  |  |  | 2016-12-01 |  |  |  | 2017-01-01 |  |  |  |  | 2017-02-01 |  |  |  | 2017-03-01 |  |  |  | 2017-04-01 |  |  |  | 2017-05-01 |  |  |  |  | 2017-06-01 |  |  |  | 2017-07-01 |  |  |  |  | 2017-08-01 |  |  |  | 2017-09-01 |  |  |  | 2017-10-01 |  |  |  |  | 2017-11-01 |  |  |  | 2017-12-01 |  |  |  | 2018-01-01 |  |  |  |  | 2018-02-01 |  |  |  | 2018-03-01 |  |  |  | 2018-04-01 |  |  |  |  | 2018-05-01 |  |  |  | 2018-06-01 |  |  |  | 2018-07-01 |  |  |  |  | 2018-08-01 |  |  |  | 2018-09-01 |  |  |  | 2018-10-01 |  |  |  |  | 2018-11-01 |  |  |  | 2018-12-01
 | time axis 2016-10-17 to 2018-12-31
5.9 | Scope Freeze \ Req Approval \ Design Review |  | 2016-10-17: 10/17-11/4; 2016-11-07: 1; 2016-11-14: 2; 2016-11-21: 3; 2016-11-28: 4; 2016-12-05: 5
| ENV52 | MMIS Dev | 2016-12-05: 11/7-12/9; 2017-01-16: P1
| ENV57 | MMIS SIT | 2016-12-05: 12/5-12/30; 2017-01-16: P1
| ENV53 | Regression | 2017-01-02: 1/2 - 1/13; 2017-01-23: P1 (1/25-1/27)
| ENV04 | UAT | 2017-01-16: 1/16-2/10; 2017-01-30: P1 (1/30-2/10)
| ENV05 | Prod | 2017-02-13: 2017-02-12
| SysDoc |  | 2017-01-30: Check out to QA - R5.8 & R5.9; 2017-02-13: Check in Doc \ Cognasante Review; 2017-02-27: Review \ Feedback \ Meetings \ Formatting Changes
6 | Scope Freeze \ Req Approval \ Design Review |  | 2016-11-21: 11/21-12/9; 2016-12-12: 1; 2016-12-19: 2; 2016-12-26: 3; 2017-01-02: 4; 2017-01-09: 5
| ENV52 | MMIS Dev | 2017-01-09: 12/12-1/13; 2017-02-20: P1
| ENV57 | MMIS SIT | 2017-01-09: 1/9-2/3; 2017-02-20: P1
| ENV53 | Regression | 2017-02-06: 2/6 - 2/17; 2017-02-27: P1 (3/1-3/3)
| ENV04 | UAT | 2017-02-20: 2/20-3/17; 2017-03-06: P1 (3/6-3/17)
| ENV05 | Prod | 2017-03-20: 2017-03-19
6.1 | Scope Freeze \ Req Approval \ Design Review |  | 2016-12-26: 12/26-1/13
| ENV52 | MMIS Dev | 2017-02-13: 1/16-2/17; 2017-03-27: P1
| ENV57 | MMIS SIT | 2017-02-13: 2/13-3/10; 2017-03-27: P1
| ENV53 | Regression | 2017-03-13: 3/13-3/24; 2017-04-03: P1 (4/5-4/7)
| ENV04 | UAT | 2017-03-27: 3/27-4/21; 2017-04-10: P1(4/10-4/21)
| ENV05 | Prod | 2017-04-24: 2016-04-23
| SysDoc |  | 2017-04-10: Check out to QA - R6.0&R6.1; 2017-04-24: Check in Doc \ Cognasante Review; 2017-05-08: Review \ Feedback \ Meetings \ Formatting Changes
6.2 | Scope Freeze \ Req Approval \ Design Review |  | 2017-01-30: 1/30-2/17
| ENV52 | MMIS Dev | 2017-03-20: 2/20-3/24; 2017-05-08: P1
| ENV57 | MMIS SIT | 2017-03-20: 3/20-4/14; 2017-05-08: P1
| ENV53 | Regression | 2017-04-17: 4/17-4/28; 2017-05-15: P1(5/17-5/19)
| ENV04 | UAT | 2017-05-08: 5/8-6/2; 2017-05-22: P1(5/22-6/2)
| ENV05 | Prod | 2017-06-05: 2017-06-04
6.3 | Scope Freeze \ Req Approval \ Design Review |  | 2017-03-06: 3/6-3/24
| ENV52 | MMIS Dev | 2017-04-24: 4/25-5/19; 2017-06-19: P1
| ENV57 | MMIS SIT | 2017-05-15: 5/15-6/9; 2017-06-19: P1
| ENV53 | Regression | 2017-06-12: 6/12-6/16; 2017-06-26: P1 (6/28-6/30)
| ENV04 | UAT | 2017-06-19: (6/19-7/7); 2017-07-03: P1(7/3-7/7)
| ENV05 | Prod | 2017-07-10: 2017-07-09
| SysDoc |  | 2017-07-03: Check out to QA - R6.2 & R6.3; 2017-07-17: Check in Doc \ Cognasante Review; 2017-07-31: Review \ Feedback \ Meetings \ Formatting Changes
6.4 | Scope Freeze \ Req Approval \ Design Review | bar: 2017-05-01 to 2017-05-15
| ENV52 | MMIS Dev | 2017-06-12: 5/22-6/2
| ENV57 | MMIS SIT | 2017-06-19: 6/19-7/7
| ENV53 | Regression | 2017-07-10: 7/10-7/14
| ENV04 | UAT | 2017-07-17: 7/17-8/4; 2017-07-24: 7/24-8/4
| ENV05 | Prod | 2017-08-07: 2017-08-06
6.5 | Scope Freeze \ Req Approval \ Design Review |  | 2017-05-15: 5/15-6/2
| ENV52 | MMIS Dev | 2017-07-03: 6/5-7/7; 2017-08-14: P1
| ENV57 | MMIS SIT | 2017-07-03: 7/3-7/28; 2017-08-14: P1
| ENV53 | Regression | 2017-07-31: 7/31-8/11; 2017-08-21: P1 (8/23-8/25); 2017-08-28: Dry run by New Team
| ENV04 | UAT | 2017-08-14: 8/14-9/8; 2017-08-28: P1(8/28-9/8)
| ENV05 | Prod | 2017-09-11: 2017-09-10
| SysDoc |  | 2017-08-28: Check out to QA - R6.4 & R6.5; 2017-09-11: Check in Doc \ Cognasante Review; 2017-09-25: Review \ Feedback \ Meetings \ Formatting Changes
6.6 (Push out by 1 Week) | Scope Freeze \ Req Approval \ Design Review |  | 2017-06-19: 6/19-7/7
| ENV52 | MMIS Dev | 2017-08-07: 7/10-8/11; 2017-09-25: P1
| ENV57 | MMIS SIT | 2017-08-14: 8/16-9/8; 2017-09-25: P1
| ENV53 | Regression | 2017-09-11: 9/11-9/22; 2017-10-02: P1 (10/4-10/6)
| ENV04 | UAT | 2017-09-25: 9/25-10/20; 2017-10-09: P1(10/9-10/20)
| ENV05 | Prod | 2017-10-23: 2017-10-22
6.7 (2 weeks Pushout) | Scope Freeze \ Req Approval \ Design Review |  | 2017-08-21: 8/21-9/8
| ENV52 | MMIS Dev | 2017-10-02: 9/11-10/6; 2017-11-13: P1
| ENV57 | MMIS SIT | 2017-10-02: 10/2-10/27; 2017-11-13: P1
| ENV53 | Regression | 2017-10-30: 10/30-11/10; 2017-11-20: P1 (11/22-11/24)
| ENV04 | UAT | 2017-11-13: 11/13-12/8; 2017-11-27: P1(11/27-12/8)
| ENV05 | Prod | 2017-12-11: 2017-12-10
| SysDoc |  | 2017-11-27: Check out to QA - R6.6 & R6.7; 2017-12-11: Check in Doc \ Cognasante Review; 2017-12-25: Review \ Feedback \ Meetings \ Formatting Changes
6.8 - Release with 5 Weeks UAT | Scope Freeze \ Req Approval \ Design Review |  | 2017-09-25: 9/25-10/13
| ENV52 | MMIS Dev | 2017-11-20: 10/16-11/24; 2018-01-08: P1
| ENV57 | MMIS SIT | 2017-11-20: 11/20-12/15; 2018-01-08: P1
| ENV53 | Regression | 2017-12-18: 12/18-12/29; 2018-01-15: P1 (1/17-1/19)
| ENV04 | UAT | 2018-01-01: 1/2-2/2; 2018-01-22: P1(1/22-2/2)
| ENV05 | Prod | 2018-02-05: 2018-02-04
6.9 | Scope Freeze \ Req Approval \ Design Review |  | 2017-11-06: 11/6-11/24
| ENV52 | MMIS Dev | 2018-01-01: 11/27-1/5; 2018-02-12: P1
| ENV57 | MMIS SIT | 2018-01-01: 1/1-1/26; 2018-02-12: P1
| ENV53 | Regression | 2018-01-29: 1/29-2/9; 2018-02-19: 2/21-2/23
| ENV04 | UAT | 2018-02-12: 2/12-3/9; 2018-02-26: P1 (2/26-3/9)
| ENV05 | Prod | 2018-03-12: 2017-03-11
| SysDoc |  | 2018-02-26: Check out to QA - R6.8 & R6.9; 2018-03-12: Check in Doc \ Cognasante Review; 2018-03-26: Review \ Feedback \ Meetings \ Formatting Changes
7 | Scope Freeze \ Req Approval \ Design Review |  | 2017-12-18: 12/18-1/5
| ENV52 | MMIS Dev | 2018-02-05: 1/8-2/9; 2018-03-19: P1
| ENV57 | MMIS SIT | 2018-02-05: 2/5-3/2; 2018-03-19: P1
| ENV53 | Regression | 2018-03-05: 3/5-3/16; 2018-03-26: P1 (3/28-3/30)
| ENV04 | UAT | 2018-03-19: 3/19-4/13; 2018-04-02: P1(4/2-4/13)
| ENV05 | Prod | 2018-04-16: 2017-04-15
7.1 | Scope Freeze \ Req Approval \ Design Review |  | 2018-01-22: 1/22-2/9
| ENV52 | MMIS Dev | 2018-03-12: 2/12-3/16; 2018-04-23: P1
| ENV57 | MMIS SIT | 2018-03-12: 3/12-4/6; 2018-04-23: P1
| ENV53 | Regression | 2018-04-09: 4/9-4/20; 2018-04-30: P1 (5/2-5/4)
| ENV04 | UAT | 2018-04-23: 4/23-5/18; 2018-05-07: P1(5/7-5/18)
| ENV05 | Prod | 2018-05-21: 2017-05-20
| SysDoc |  | 2018-05-07: Check out to QA - R7.0 & R7.1; 2018-05-21: Check in Doc \ Cognasante Review; 2018-06-04: Review \ Feedback \ Meetings \ Formatting Changes
7.2 | Scope Freeze \ Req Approval \ Design Review |  | 2018-02-26: 2/26-3/16
| ENV52 | MMIS Dev | 2018-04-16: 3/19-4/20; 2018-05-28: P1
| ENV57 | MMIS SIT | 2018-04-16: 4/16-5/7; 2018-05-28: P1
| ENV53 | Regression | 2018-05-14: 5/14-5/25; 2018-06-04: P1 (6/6-6/8)
| ENV04 | UAT | 2018-05-28: 5/28-6/22; 2018-06-11: P1(6/11-6/22)
| ENV05 | Prod | 2018-06-25: 2017-06-24

## Release Calendar v6.6 (hidden)
Release | Dev | QA Test | State UAT | Model Office/TP Testing | Prod | Break Fix
3.00.00.00 |  |  |  | 5/1-5/17 | 5/1-5/17 | 5/1-5/17
3.01.00.00 | 3/25-4/12 | 4/12-5/10 | 4/19-5/17 | 5/18-6/15 | 5/18-6/15 | 5/18-6/15
3.02.00.00-Full Release | 4/12-5/6 | 5/7-5/24 | 5/18-6/1
3.02.01.00- 2nd Full Release | 5/6-5/24 | 5/24-6/7 | 6/1-6/8
3.02.02.00-Potential patch | 5/24-6/7 | 6/7-6/14 | 6/8-6/14 | 6/15-7/19 | 6/15-7/19 | 6/15-7/19
3.03.00.00- Full Release | 5/24-6/14 | 6/14-6/28 | 6/21-7/5
3.03.01.00 2nd Full Release | 6/14-6/28 | 6/28-7/11 | 7/6-7/11
3.03.02.00- Potential/Partial | 6/28-7/11 | 7/12-7/19 | 7/12-8/02 | 8/02-9/06 | 8/02-9/06 | 8/02-9/06
3.04.00.00- Full Release | 6/28-8/02 | 7/19-8/16 | 8/11-8/23
3.04.01.00 - Full Release | 8/02-8/16 | 8/16-8/30 | 8/23-8/30
3.04.02.00- Potential/Partial | 8/16-8/30 | 8/30-9/06 | 8/30-9/06 | 9/06-10/11 | 9/06-10/11 | 9/06-10/11
3.05.00.00- Full Release | 8/16-9/06 | 9/06-9/20 | 9/13-9/27
3.05.01.00 2nd Full Release | 9/06-9/20 | 9/20-10/04 | 9/27-10/04
3.05.02.00- Potential/Partial | 9/20-10/04 | 10/04-10/11 | 10/04-10/11 | 10/11-11/15 | 10/11-11/15 | 10/11-11/15
3.06.00.00- Full Release | 9/20-10/11 | 10/11-10/25 | 10/18-11/01
3.06.01.00 2nd Full Release | 10/11-10/25 | 10/25-11/08 | 11/01-11/08
3.06.02.00- Potential/Partial | 10/25-11/08 | 11/08-11/15 | 11/08-11/15 | 11/15-12/20 | 11/15-12/20 | 11/15-12/20
3.07.00.00- Full Release | 10/25-11/15 | 11/15-11/29 | 11/22-12/06
3.07.01.00 2nd Full Release | 11/15-11/29 | 11/29-12/13 | 12/06-12/13
3.07.02.00- Potential/Partial | 11/29-12/13 | 12/13-12/20 | 12/13-12/20 | cancelled
3.08.00.00- Full Release | 11/29-12/27 | 12/27-01/11 | 01/11-02/01
3.08.01.00- Potential/Partial (care management patch) | 12/27-1/11 | 1/3/-1/18 | 01/18-02/01 | 02/01-5/25 | 02/01-5/25 | 02/01-5/25
3.08.02.01- Potential/Partial | 03/03-03/07 | 03/07-03/12 | 03/12-03/13 | 03/14-5/25 | 03/14-5/25 | 03/14-5/25
3.08.02.02- Potential/Partial | 03/03-03/07 | 03/07-03/14 | 03/17-03/21 | 03/23-5/25 | 03/23-5/25 | 03/23-5/25
3.08.02.05- Potential/Partial | 03/10-03/14 | 03/14-03/21 | 03/21-03/28 | 03/30-5/25 | 03/30-5/25 | 03/30-5/25
3.08.02.06- Potential/Partial | 04/14-04/16 | 04/16-04/18 | 04/18-04/25 | 04/27-5/25 | 04/27-5/25 | 04/27-5/25
3.08.02.08- Potential/Partial | 04/23-04/25 | 04/25-04/30 | 04/30-05/02 | 05/04-5/25 | 05/04-5/25 | 05/04-5/25
3.08.02.09- Potential/Partial | 05/01-05/05 | 05/05-05/07 | 05/07-05/09 | 05/09-5/25 | 05/09-5/25 | 05/09-5/25
3.09.00.00- Full Release | 01/27-02/07 | 02/07-02/28
3.09.01.00- Full Release | 02/07-03/07 | 02/28-03/31
3.09.2.00- Full Release | 03/17-03/27 | 03/21-04/11 | 03/29-4/18
3.09.3.01- Partial | 04/21-05/2 | 05/2-05/8
3.09.3.02- Partial | 05/02-05/08 | 05/08-05/09 | 05/10-05/23 | 05/25-07/20 | 05/25-07/20 | 05/25-07/20
3.10.00.00- Full Release | 03/31-05/16 | 05/16-05/30
3.10.01.00- Full Release | 05/16-05/30 | 05/30-06/06
3.10.02.00- Full Release | 05/30-06/18 | 06/18-06/30 | 06/30-7/20
3.10.02.00- Potential/Partial | 06/30-07/07 | 07/07-07/10 | 07/11-07/20 | 07/20-9/20 | 07/20-9/20 | 07/20-9/20
3.10.02.01- Potential/Partial | 07/07-07/11 | 07/14-07/15 | 07/15-07/20 | 07/20-9/20 | 07/20-9/20 | 07/20-9/20
4.00.00.00- Full Release | 06/30-08/11 | 08/11-09/05
4.00.01.00- Full Release | 08/11-08/25 | 08/18-09/05 | 09/05-09/28
4.00.02.00- Potential/Partial | 09/01-09/12 | 09/01-09/12 | 09/12-09/28 | 09/28-12/07 | 09/28-12/07 | 09/28-12/07
4.01.00.00- Full Release | 09/08-09/26 | 09/26-10/10
4.01.01.00- Full Release | 09/28-10/10 | 10/10-11/04 | 11/04-12/07
4.01.02.09- Potential /Partial | 11/17-11/28 | 11/17-11/28 | 11/28-12/07 | 12/07/2014-2/8/2015 | 12/07/2014-2/8/2015 | 12/07/2014-2/8/2015 | Full
4.01.02.10- Potential /Partial | 11/24-11/27 | 11/27-12/2 | 12/2-12/9 | 12/9/2014-2/8/2015 | 12/9/2014-2/8/2015 | 12/9/2014-2/8/2015 | IF
4.01.02.15- Potential /Partial | 12/15-12/17 | 12/17-12/19 | 12/19-12/24 | 12/24/2014-2/8/2015 | 12/24/2014-2/8/2015 | 12/24/2014-2/8/2015 | IF
4.01.02.16- Potential /Partial | 12/22-12/26 | 12/24-12/26 | 12/26-12/30 | 12/30/2014-2/8/2015 | 12/30/2014-2/8/2015 | 12/30/2014-2/8/2015 | ES
4.01.02.17- Potential /Partial | 12/30/2014-1/2/2015 | 1/2/2015-1/5/2015 | 1/5/2015-1/6/2015 | 1/6/2015-2/8/2015 | 1/6/2015-2/8/2015 | 1/6/2015-2/8/2015 | IF
4.01.02.18- Potential /Partial | 1/16/2015-1/18/2015 | 1/18/2015-1/19/2015 | 1/19/2015-1/20/2015 | 1/20/2015-2/8/2015 | 1/20/2015-2/8/2015 | 1/20/2015-2/8/2015 | IF
4.02.00.00- Full Release | 10/27-12/12 | 12/08-12/26
4.02.01.00- Full Release | 12/12-12/19 | 12/19-12/29 | 12/29/2014-2/1/2015
4.02.02.01- Full Release | 12/19/2014-01/02/2015 | 01/02/2015-01/06/2015 | 01/06/2015-2/1/2015
4.02.02.10- Potential /Partial | 1/2/2015-1/19/2015 | 1/19/2015-1/21/2015 | 1/22/2015-2/8/2015 | 2/8/2015-4/11/2015 | 2/8/2015-4/11/2015 | 2/8/2015-4/11/2015 | Full
4.02.02.14- Potential /Partial | 2/19/2015-2/10/2015 | 2/10/2015-2/11/2015 | 2/11/2015-2/12/2015 | 2/12/2015-4/11/2015 | 2/12/2015-4/11/2015 | 2/12/2015-4/11/2015 | ES
4.02.02.16- Potential /Partial (Patch 6) | 1/26/2015-2/9/2015 | 2/9/2015-2/16/2015 | 2/16/2015-2/22/2015 | 2/22/2015-4/11/2015 | 2/22/2015-4/11/2015 | 2/22/2015-4/11/2015 | All
4.02.02.19- Potential /Partial (Capitation Phase 1) | 1/13-1/28 - Dev 1/29-2/6 - QA
4.02.02.20- Potential /Partial (Capitation Phase 2) | 1/23-2/6 - Dev 2/10-2/19 - QA | 2/20-2/26 | 2/26-3/6 | 3/8-4/11 | 3/8-4/11 | 3/8-4/11
4.03.00.00- Full Release | 12/22/2015-2/13/2015 | 02/23/2015 - 03/13/2015
4.03.01.00- Full Release | 2/16/2015-3/6/2015 | 3/6/2015-03/16/2015 | 3/16/2015-4/10/2015
4.03.02.00- Potential /Partial | 3/23/2015-3/27/2015 | 3/23/2015-3/27/2015 | 3/27/2015-4/10/2015 | 4/12/2015-5/31/2015 | 4/12/2015-5/31/2015 | 4/12/2015-5/31/2015
4.04.00.00- Full Release - ICD10 GO LIVE | 7/2014-1/9/2015 | 7/2014-1/9/2015 | 2/16/2015-5/8/2015 (ENV82)
4.04.00.00- Full Release - ICD10 GO LIVE |  |  | 5/8/2015-6/5/2015 | 6/6/2015-7/11/2015 | 6/6/2015-7/11/2015 | 6/6/2015-7/11/2015
4.05.00.00- Full Release | 3/2/2015-4/3/2015 | 4/13/2015-5/8/2015
4.05.02.00-Full Release | 4/3/2015-5/8/2015 | 5/8/2015-5/20/2015
4.05.03.00- Full Release (ICD10 CODE MERGE) | 5/25/2015-5/29/2015 | 5/29/2015 - 6/12/2015 | 6/15/2015-7/10/2015
4.05.03.01- Potential /Partial | 6/12/2015-6/19/2015 | 6/19/2015-6/26/2015 | 6/26/2015-7/10/2015 | 7/10/2015-9/12/2015 | 7/10/2015-9/12/2015 | 7/10/2015-9/12/2015
4.05.03.02- Potential /Partial (MCM\PAP) | 6/5/2015-6/26/2015 | 7/6/2015-7/17/2015 | 7/17/2015-8/7/2015 | 8/9/2015-9/12/2015 | 8/9/2015-9/12/2015 | 8/9/2015-9/12/2015
4.06.00.00- Full Release | 6/22/2015-7/17/2015 | 7/27/2015-8/14/2015
4.06.01.00- Full Release | 7/27/2015-8/7/2015 | 8/7/2015-8/14/2015 | 8/17/2015-9/11/2015
4.06.02.00- Potential /Partial | 8/10/2015-8/21/2015 | 8/21/2015-8/28/2015 | 8/28/2015-9/11/2015 | 9/13/2015-10/17/2015 | 9/13/2015-10/17/2015 | 9/13/2015-10/17/2015